## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anurai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2021-2022 | 1184/TD | 02/12/2021 | 22/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 8.21 | 6.31 | 76.84 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tube well (Additional) Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1289) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000497/2021-2022 | 1992/TD | 07/03/2022 | 28/03/2022 | AQUATECH ENGINEER | 12.17 | 11.85 | 97.33 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 1st Tube well Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1407) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000495/2021-2022 | 1991/TD | 07/03/2022 | 28/03/2022 | AQUATECH ENGINEER | 12.17 | 11.65 | 95.78 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Renovation work of Spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum at Anurai Mouza within Anurai W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000602/2021-2022 | 493 / CSD | 16/11/2021 | 07/12/2021 | SUBRATA KUMAR BERA | 2.43 | 2.26 | 93.07 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Electric quotation Bill of T/W-III of Anurai water suplly scheme under MMD PHE Dte. under Marishda CCC | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000228/2022-2023 | 2004006184/QUOT/03 | 30/07/2022 | 30/07/2023 | WBSEDCL | 0.7 | 0.7 | 100 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Supply & Delivery of different dia. Sluice Valve for Augmentation of Anurai Water Supply Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 426/TD | 27/05/2022 | 11/06/2022 | PARTHA CONSTRUCTION | 4.59 | 4.59 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Anurai Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000888/2022-2023 | 441 / CSD | 20/03/2023 | 04/04/2023 | KAMAL KUMAR BERA | 0.95 | 0.95 | 100 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Additional Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000265/2022-2023 | 1088/TD | 25/08/2022 | 04/10/2022 | ABHIJIT BERA | 5.47 | 5.31 | 97.22 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additiona Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai - III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000329/2022-2023 | 843/TD | 20/07/2022 | 19/08/2022 | ABHIJIT BERA | 3.63 | 3.57 | 98.24 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Instalation of display Board at different work site of Augmentation of Anurai- 1 no, Bhajachauli- 1 no, Dhanghara- 1 no, Basudebberiya- 1 no, Shankarpur- 1 no, Mukutshila Zone-II- 1 no. & Chandibhetti- 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/000510/2022-2023 | 810 / CSD | 21/10/2022 | 05/11/2022 | SAURAV HAZRA | 0.81 | 0.81 | 99.85 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 1265/TD | 13/12/2021 | 13/12/2021 | Resource Division | 42.96 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2021-2022 | 1729/TD | 02/02/2022 | 02/02/2022 | Resource Division | 13.95 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001012/2022-2023 | 1861/W/MMD | 22/09/2022 | 20/01/2023 | SUBHAM ENTERPRISE | 11.67 | 8.29 | 71.03 | 20
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Land Filling & Construction of Approch Road for 3rd TW site of Anurai W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000904/2022-2023 | 307/CSD | 27/02/2023 | 14/03/2023 | ABHIJIT BERA | 1.25 | 1.23 | 98.78 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Augmentation of Anurai Water Supply Scheme by Providing Laying Distribution System and FHTC in In Contai-III & Deshpran Block Of in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000301/2021-2022 | 1639/TD | 19/01/2022 | 06/08/2025 | MAHAVIR PUMPS MFG. PVT. LTD. | 391.92 | 332.51 | 84.84 | 90
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Supply & delivery D.I. Specials for Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000401/2022-2023 | 690 / CSD | 22/09/2022 | 07/10/2022 | SUBRATA KUMAR BERA | 0.76 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional 3rd Tube well under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001272/2022-2023 | 2201/W/MMD | 14/12/2022 | 30/03/2025 | A G ENTERPRISE | 12.25 | 11.41 | 93.18 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | Assistant Engineer | Junior Engineer | ORD/000699/2022-2023 | 1992/TD | 01/12/2022 | 31/12/2022 | SUBRATA KUMAR BERA | 4.49 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000278/2024-2025 | 2906/TD | 10/09/2024 | 20/10/2024 | RAI CONSTRUCTION | 12.9 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Laying of Left out Distribution pipe line by HDPE pipes with allied works for providing FHTC for Augmentation of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000764/2025-2026 | 2262/CSD | 09/10/2025 | 08/12/2025 | ANJANI ENTERPRISE | 0.94 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | SM/09334 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Anurai W/S Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-136 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 1535/TD | 18/07/2023 | 31/08/2024 | DEBABRATA DAS | 21.39 | 11.3 | 52.83 | 100
Total | [13 empty] | 565.63 | 412.76 | 72.97