## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Majna Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000166/2021-2022 | 1170/TD | 01/12/2021 | 08/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.34 | 4.04 | 39.08 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Majna Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000661/2021-2022 | 2216/TD | 22/03/2022 | 06/04/2022 | BIBEKANANDA DAS | 4.06 | 4.06 | 100 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Majna W/S Scheme (T/W-III) , Contai-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000106/2023-2024 | 855/CDD | 10/07/2023 | 09/08/2023 | MENAKA ENTERPRISE | 14.61 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Majna BPHC Premises for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side & South Side) | Assistant Engineer | Junior Engineer | ORD/000415/2022-2023 | 373/TD | 17/05/2022 | 14/06/2022 | BIBEKANANDA DAS | 3.85 | 3.5 | 90.85 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site( Mouza- Nayabasan ,J.L. No-294, Plot No- 319), for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for West side & North Side) | Assistant Engineer | Junior Engineer | ORD/000412/2022-2023 | 344/TD | 13/05/2022 | 10/06/2022 | PARTHA CONSTRUCTION | 4.84 | 3.82 | 78.76 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 1264/TD | 13/12/2021 | 13/12/2021 | Resource Division | 13.16 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2021-2022 | 1902/TD | 23/02/2022 | 23/02/2022 | Resource Division | 13.73 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2021-2022 | 2217/TD | 24/03/2022 | 24/03/2022 | Resource Division | 20.19 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 82/TD | 08/04/2022 | 08/04/2022 | Resource Division | 20.19 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Electric Quotation for MAJNA Water Supply Scheme T/W-III, (Ref. ID-204068438) |  |  | BILL/01930/2023-2024 | BP-2023-24-235 | 08/09/2023 | 08/09/2023 | WBSEDCL | 3.52 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Name of Work: i) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Majna PWSS within Contai -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Laying rising main and other allied works Augmentation of Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000861/2022-2023 | 3217/TD | 14/03/2023 | 23/04/2023 | SUBRATA KUMAR BERA | 19.54 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Supply Scheme for Majna, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001912/2022-2023 | 813/W/MMD | 24/03/2023 | 20/09/2023 | MEGA SOLAR ENERGY | 11.34 | 4.67 | 41.19 | 58
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Augmentation of ground water based Majna Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir of Capacity 250 cum. And staging height 20.00 mtr. With allied work including Sub Soil Investigation within Contai-I Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000403/2021-2022 | 1845/TD | 15/02/2022 | 14/08/2022 | DAS ENTERPRISE | 324.35 | 303.34 | 93.52 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Laying of Distribution pipe line by UPVC pipes with allied works due to Construction of drain by Local Panchayet of Majna and its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 1714/CSD | 31/08/2023 | 30/09/2023 | SUBRATA KUMAR BERA | 2.66 | 2.65 | 99.85 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Supply Scheme for Majna | SM/09335 | Augmentation | Repair and Renovation of Pump House and others allied works for OHR & 2nd Tube well site at Majna Water Supply Scheme in Contai - Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2024-2025 | 3398/TD | 28/10/2024 | 27/11/2024 | SUBRATA KUMAR BERA | 1.92 | 0 | 0 | 100
Total | [13 empty] | 468.28 | 326.08 | 69.63