## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bar Basudevpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000189/2021-2022 | 1198/TD | 02/12/2021 | 22/12/2021 | RADIANT | 4.28 | 4.21 | 98.28 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 1300/TD | 20/12/2021 | 20/12/2021 | Resource Division | 19.51 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (446 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-II) | Assistant Engineer | Junior Engineer | ORD/000337/2021-2022 | 1770/TD | 08/02/2022 | 20/03/2022 | SHAKEEL KHAN | 53.9 | 17.85 | 33.12 | 55
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (646 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 1769/TD | 08/02/2022 | 20/12/2023 | ZENITH CONSTRUCTION | 84.54 | 50.24 | 59.43 | 75
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-IV) | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 1772/TD | 08/02/2022 | 10/03/2022 | FARID UDDIN AHMED | 47.43 | 43.13 | 90.95 | 80
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Additional Laying Distribution System of 200 mm dia upvc pipe line and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia(sec 2-14) and 180 mm dia(sec-20-23) of pipe line of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000307/2022-2023 | 1147/TD | 31/08/2022 | 20/09/2022 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.88 | 24.11 | 96.89 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Barbasudebpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001138/2022-2023 | 2119/W/MMD | 28/11/2022 | 28/03/2023 | M/S B.M. ELECTRICAL | 11.26 | 10.32 | 91.65 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. |  |  | ORD/000283/2022-2023 | 217/S&WSD | 23/11/2022 | 23/12/2022 | SUMAN KUMAR DEY | 0.89 | 0.35 | 39.2 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part- III) | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 1771/TD | 08/02/2022 | 10/03/2022 | MAA KALI CONSTRUCTION | 47.34 | 46.29 | 97.78 | 100
10 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-II), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000053/2022-2023 | 108/CDD | 12/04/2022 | 12/05/2022 | MENAKA ENTERPRISE | 18.28 | 17.82 | 97.47 | 100
11 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCHEME (REPLACEMENT TW-II), IN HALDIA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000216/2022-2023 | 402/CMSD-II | 01/08/2022 | 16/08/2022 | MENAKA ENTERPRISE | 3.17 | 2.01 | 63.28 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Barbasudevpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 1383/TD | 23/09/2022 | 07/11/2022 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.13 | 3.88 | 94 | 100
13 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | PROVIDING DRILLING CREW AND ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000167/2022-2023 | 107/CDD | 12/04/2022 | 12/05/2022 | MENAKA ENTERPRISE | 18.28 | 17.62 | 96.38 | 100
14 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), IN HALDIA BLOCK UNDER PURRBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000215/2022-2023 | 154/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 3.17 | 2.07 | 65.33 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Barbasudebpur Water Supply Scheme,with in Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000484/2022-2023 | 1886/TD | 24/11/2022 | 01/03/2025 | MAA ANANDAMAYEE | 104.61 | 74.3 | 71.02 | 96
16 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | Driller In Charge | Junior Engineer | ORD/000364/2022-2023 | 379/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 3.44 | 2.56 | 74.42 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2021-2022 | 1834/TD | 15/02/2022 | 15/02/2022 | Resource Division | 9.79 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Laying of additional 90mm dia. distribution pipe line and cannel crossing by M.S. structure for 140mm dia. distribution pipe laying of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. (Phase - II) | Assistant Engineer | Junior Engineer | ORD/000663/2022-2023 | 2348/TD | 10/01/2023 | 30/01/2023 | MAA KALI CONSTRUCTION | 13.75 | 13.66 | 99.35 | 0
19 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001518/2022-2023 | 362/W/MMD | 09/03/2023 | 05/09/2023 | SHIVAM ENTERPRISE | 12.63 | 11.88 | 94.06 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Laying of proposed Rising main line and inter connection at Barbasudevpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000337/2023-2024 | 802/TD | 30/05/2023 | 19/06/2023 | PULAK KUMAR SAMANTA | 6.22 | 4.72 | 75.92 | 100
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Augumentation of ground water based Barbasudebpur PWSS to accommodate FHTC in Haldia block under Haldia Sub Division of Tamluk Division in purba medinipur district under JJM program under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000426/2023-2024 | 623/HESD | 17/08/2023 | 01/09/2023 | SHIVAM ENTERPRISE | 3.5 | 3.24 | 92.38 | 75
22 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Fuel Charges for the month of January 2023 |  |  | BILL/00142/2022-2023 | BP-2022-23-353 | 09/03/2023 | 09/03/2023 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | FUEL CHARGE MONTH OF FEBRUARY 2023 |  |  | BILL/00194/2022-2023 | BP-2022-23-387 | 29/03/2023 | 29/03/2023 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Fuel Charges bill |  |  | BILL/00100/2022-2023 | BP-2022-23-326 | 06/02/2023 | 06/02/2023 | MIRA SERVICE STATION | 0.46 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09336 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (for Barbasudevpur PWSS, Lakshya PWSS, Chaitanyapur Zone-II PWSS, Manoharpur PWSS) (Phase-VI) | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 767/HSD | 27/02/2024 | 05/03/2024 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
Total | [13 empty] | 496.72 | 351.09 | 70.68