## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Haipur PWSS Block-Contai-I in the district of Purba Medinipur.(Phase-II) | Assistant Engineer |  | ORD/000296/2021-2022 | 1637/TD | 19/01/2022 | 20/03/2022 | SRIMANTA KUMAR MAITY | 118.38 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000082/2021-2022 | 429/CMSD-II (D) | 30/09/2021 | 15/10/2021 | S B S ENTERPRISE | 0.41 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000083/2021-2022 | 428/CMSD-II (D) | 30/09/2021 | 15/10/2021 | S B S ENTERPRISE | 0.96 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | Supply & Delivery of different dia C.I.D.F. Sluice Valve for Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the district of Purba Medinipur (Phase-II) under Contai Sub- Division, of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000046/2022-2023 | 12/A/CSD | 05/04/2022 | 20/04/2022 | SRIMANTA KUMAR MAITY | 1.89 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | SEALING BORE- HOLE ANNULAR SPACE AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAIPUR PWSS UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000202/2021-2022 | 188/CMSD-I (D) | 30/09/2021 | 07/10/2021 | MENAKA ENTERPRISE | 0.6 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | Supply & Delivery of 12 1/4" dia RR Bit for Drilling work at haipur PWSS, Dist. Purba Midnapore under CDD,PHE Dte. |  |  | ORD/000133/2022-2023 | 253/CMSD-I(D) | 23/06/2022 | 08/07/2022 | DAS ENTERPRISE | 4.65 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | SUPPLY & DELIBVERY OF 9 7/8'' DIA RR BIT FOR DRILLING WORK AT HAIPUR PWSS, DISTRICT PURBA MEDINIPUR AND OTHER PWSS UNDER CDD, PHE DTE. |  |  | ORD/000248/2022-2023 | 249/CMSD-I | 22/06/2022 | 07/07/2022 | M.S. ENTERPRISE | 4.21 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | REPAIRING OF DAMAGE TRUCK DRIVER CABIN, STEEL BODY, CHEQUER PLATE, CHASSIS AND TRUCK BODY PAINTING OF GOVT VEHICLE NO. WMK 6422 (TATA) UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000276/2022-2023 | 77/CMSD-I | 01/04/2022 | 16/04/2022 | M/S B.P.TRADING CORPORATION | 2.36 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | SUPPLY & DELIVERY OF COMPRESSOR PIPE AND HOSE AT SITE FOR COMPRESSOR UNIT ATTACHED WITH RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000274/2021-2022 | 65/CMSD-I (D) | 22/03/2022 | 29/03/2022 | PADMA ENGINEERING & CO. | 0.98 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | SM/09339 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
Total | [13 empty] | 148.28 | 0 | 0