## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Mrityunjay Pradhan, Booth no 146, Plot No.-1033, Mouza-Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 147, JL No.-32,Plot No.-525, Mouza-Gharrang, G.P.-Haludbari |  | Junior Engineer | ORD/000683/2021-2022 | 1983/TD | 04/03/2022 | 25/03/2022 | AHINDRA BARIK | 3.79 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Deuli, Plot No. 220, J.L.No. 49 & Mouza - Padubar, Plot No. 3301, J.L.No. 6 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000715/2021-2022 | 2106/TD | 17/03/2022 | 01/04/2022 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Barida, Plot No. 2164/3203, J.L.No.6 & Mouza -Tentulia, Plot No. 48, J.L.No.3 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District |  | Junior Engineer | ORD/000768/2021-2022 | 2143/TD | 17/03/2022 | 01/04/2022 | SOURAV DAS | 3.57 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Basanti Mayer Mandir Mouza -Jagannathkarbar, JL.No- 213, Plot No.- 12 & Bathuary fourth star Club ICDS Mouza - Bathuary, JL. No- 244, Plot No.- 863 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000781/2021-2022 | 2157/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 3.34 | 93.57 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Barabhagia Paschim SSK Mouza -Barabhagia, JL.No- 236, Plot No.- 358 & Pirijkhanbar Mouza - Pirijkhanbar, JL. No- 225, Plot No.- 658 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000782/2021-2022 | 2158/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 0.05 | 1.39 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near House of Kalipada Manna Mouza -Uttar Tajpur, JL.No- 250, Plot No.- 455 & Palpara Sammilita Mouza - Uttar Tajpur, JL. No- 250, Plot No.- 2816 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000783/2021-2022 | 2159/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 3.42 | 95.76 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Maity Para Mouza -Daudpur, JL.No- 217, Plot No.-1060 & Balighai Hat Samity Mouza - Mallikpur, JL. No- 176, Plot No.- 04/05 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000784/2021-2022 | 2160/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 3.34 | 93.73 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Giri O Maity Para Mouza -Bhatda, JL.No- 180, Plot No.-2465 & Jana Para Mouza - Bhatda, JL. No- 180, Plot No.- 1115 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000785/2021-2022 | 2161/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 3.23 | 90.61 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandanpur Patna, Plot No. 480, J.L.No. 13 & Mouza - Bagbrajakishor, Plot No. 8, J.L.No. 7 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000717/2021-2022 | 2108/TD | 17/03/2022 | 01/04/2022 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Champabani, Plot No. 137, J.L.No. 80 & Mouza - Mirzapur, Plot No. 197, J.L.No. 74 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000721/2021-2022 | 2112/TD | 17/03/2022 | 01/04/2022 | DIPANKAR MAITY | 3.57 | 3.48 | 97.55 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza-Bodhra, Plot No. 233, J.L.No. 228 & Mouza-Jhaugeriya, Plot No. 377, J.L.No. 207 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000694/2021-2022 | 2088/TD | 17/03/2022 | 01/04/2022 | DEBABRATA DAS | 3.57 | 3.31 | 92.64 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Srinibas Das's House Mouza - Erenda, JL.No- 155, Plot No.- 900 & Beltalia Maa Chandi SSK Mouza - Erenda, JL. No- 155, Plot No.- 690 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000780/2021-2022 | 2156/TD | 17/03/2022 | 01/04/2022 | FIROZ KHAN | 3.57 | 3.36 | 94.2 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Gurupada Das House, Mouza -Shyambaribar, JL.No- 266 Plot No.-1207 & Maity Para near Ajit Maity House, Mouza - Dulalpur, JL. No- 256, Plot No.- 908 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000794/2021-2022 | 2170/TD | 17/03/2022 | 01/04/2022 | S.A. ENTERPRISE | 3.57 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Jaydev Jana, Booth no 140, Plot No.-1644, Mouza-Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 141, JL No.-18,Plot No.-540, Mouza-Keshabchak, G.P.-Haludbari | Assistant Engineer |  | ORD/000680/2021-2022 | 1982/TD | 04/03/2022 | 25/03/2022 | AHINDRA BARIK | 3.79 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Uttam Purakait, J.L. No.-64, Plot No.-379, Mouza-Kadirpur, G.P.-Janka b)Near house of Sunil Das, J.L. No.-69, Plot No.-1453, Mouza-Paschim Panikhya, G.P.-Janka |  | Junior Engineer | ORD/000656/2021-2022 | 1971/TD | 04/03/2022 | 25/03/2022 | S. A. ENTERPRISE | 3.79 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Gopalpur, Plot No. 20, J.L.No. 210 & Mouza-Jamra Shyampur,Plot No. 205, J.L.No. 218 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000696/2021-2022 | 2090/TD | 17/03/2022 | 01/04/2022 | DEBABRATA DAS | 3.57 | 3.39 | 95.13 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Uttar Gobra, Plot No. 65, J.L.No. 526 & Mouza - Akna, Plot No. 101, J.L.No. 302 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000726/2021-2022 | 2114/TD | 17/03/2022 | 01/04/2022 | AHINDRA BARIK | 3.57 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Dublabari, Plot No. 491, J.L.No. 240 & Mouza - Chandpur, Plot No. 289, J.L.No. 237 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000705/2021-2022 | 2099/TD | 17/03/2022 | 01/04/2022 | PRALAY RANJAN PATRA | 3.57 | 3.21 | 89.83 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Purusottampur, Plot No. 902, J.L.No. 11 & Mouza - Mukundapur Uttar, Plot No. 98, J.L.No. 19 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000716/2021-2022 | 2107/TD | 17/03/2022 | 01/04/2022 | MAHAPRABHU ENTERPRISE | 3.57 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Sanbalisai, Plot No. 107, J.L.No. 150 & Mouza - Hirapur, Plot No. 60, J.L.No. 48 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000727/2021-2022 | 2115/TD | 17/03/2022 | 01/04/2022 | AHINDRA BARIK | 3.57 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Foolbari Gram near Nayek & Bar Para, J.L. No. 249, Dag No. 812 & near Kandarpur Masasa Mandir in front of Sukumar Bhunia's house, J.L. No. 252 Dag No. 758 under Satilapur G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000741/2021-2022 | 2127/TD | 17/03/2022 | 01/04/2022 | PULAK KUMAR SAMANTA | 3.57 | 3.33 | 93.34 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Mohitosh Maity, J.L. No.-98, Plot No.-790, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Pabitra Pramanik, J.L. No.-98, Plot No.-103, Mouza- Thanaberia , G.P.-Nijkasba |  | Junior Engineer | ORD/000647/2021-2022 | 1962/TD | 04/03/2022 | 25/03/2022 | KAMAL KUMAR BERA | 3.79 | 3.78 | 99.68 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Shilaberia, J.L. No.-83, Plot No.-415, Mouza- Shilaberia , G.P.-Nijkasba b)At Shilaberia, J.L. No.-83, Plot No.-770, Mouza- Shilaberia , G.P.-Nijkasba |  | Junior Engineer | ORD/000649/2021-2022 | 1964/TD | 04/03/2022 | 25/03/2022 | SUBHRANGSHU SEKHAR GIRI | 3.79 | 3.73 | 98.33 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Shilaberia, J.L. No.-83, Plot No.-38, Mouza- Shilaberia , G.P.-Nijkasba b)At Shilaberia, J.L. No.-83, Plot No.-98, Mouza- Shilaberia , G.P.-Nijkasba |  | Junior Engineer | ORD/000650/2021-2022 | 1965/TD | 04/03/2022 | 25/03/2022 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.71 | 97.92 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Sisir Maity, J.L. No.-98, Plot No.-55, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Nijkasba Purba Shoni Mondir, J.L. No.-119, Plot No.-628, Mouza- Nijkasba , G.P.-Nijkasba |  | Junior Engineer | ORD/000648/2021-2022 | 1963/TD | 04/03/2022 | 25/03/2022 | SUBHRANGSHU SEKHAR GIRI | 3.79 | 3.74 | 98.77 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Subhasis Das, J.L. No.-120, Plot No.-391, Mouza-Kadirabadchar, G.P.-Khejuri b)Near house of Bhagirath Mandal, J.L. No.-120, Plot No.-379, Mouza- Kadirabadchar , G.P.-Khejuri |  | Junior Engineer | ORD/000672/2021-2022 | 1974/TD | 04/03/2022 | 25/03/2022 | GIRI CONSTRUCTION | 3.79 | 3.78 | 99.68 | 0
27 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Pradip Mandal, J.L. No.-59, Plot No.-471, Mouza-Kasaria, G.P.-Khejuri b)Near house of Amitabh Mandal, J.L. No.-59, Plot No.-1149, Mouza- Kasaria , G.P.-Khejuri |  | Junior Engineer | ORD/000673/2021-2022 | 1975/TD | 04/03/2022 | 25/03/2022 | ABHIJIT BERA | 3.79 | 3.78 | 99.68 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dendari, Plot No. 16, J.L.No. 38 & Mouza - Purba Mukundapur, Plot No. 749, J.L.No. 211 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000730/2021-2022 | 2118/TD | 17/03/2022 | 01/04/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.4 | 95.47 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 141, Plot No.-744, Mouza- Keshabchak,J.L. No.-21, G.P.-Haludbari b) Booth no 146, JL No.-35,Plot No.-184, Mouza- Katickhali , G.P.-Haludbari |  | Junior Engineer | ORD/000679/2021-2022 | 1981/TD | 04/03/2022 | 25/03/2022 | BISWA NIRMAN ENTERPRISE. | 3.79 | 3.72 | 98.17 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)JL No.-21,Plot No.-1461, Mouza-Halutbari, G.P.-Haludbari b) JL No.-23,Plot No.-190, Mouza-Narsulachak, G.P.-Haludbari |  | Junior Engineer | ORD/000687/2021-2022 | 1985/TD | 04/03/2022 | 25/03/2022 | M/S SREE DURGA ENTERPRISE | 3.79 | 3.79 | 99.94 | 0
31 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Ullaspur, Plot No. 587, J.L.No. 71 & Mouza - Jasteghari, Plot No. 262/1087, J.L.No. 44 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000714/2021-2022 | 2105/TD | 17/03/2022 | 01/04/2022 | SUBRATA KUMAR BERA | 3.57 | 3.05 | 85.42 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Subhash Guria, J.L. No.-96, Plot No.-90, Mouza-Matilal Chak, G.P.-Nijkasba b)At Das Para, J.L. No.-95, Plot No.-347, Mouza- Lakshan chak, G.P.-Nijkasba |  | Junior Engineer | ORD/000653/2021-2022 | 1968/TD | 04/03/2022 | 25/03/2022 | JASODA ENTERPRISE | 3.79 | 3.78 | 99.68 | 0
33 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dahadaya, Plot No. 804, J.L.No. 98 & Mouza - Haropur, Plot No. 527, J.L.No. 96 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000731/2021-2022 | 2119/TD | 17/03/2022 | 01/04/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.42 | 95.94 | 0
34 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Alankarpur, Plot No. 124, J.L.No. 97 & Mouza - Ghersai, Plot No. 408, J.L.No. 88 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000732/2021-2022 | 2120/TD | 17/03/2022 | 01/04/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.36 | 94.07 | 0
35 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)JL No.-21,Plot No.-409, Mouza-Halutbari, G.P.-Haludbari b)JL No.-21,Plot No.-344, Mouza-Halutbari, G.P.-Haludbari |  | Junior Engineer | ORD/000689/2021-2022 | 1986/TD | 04/03/2022 | 25/03/2022 | M/S SREE DURGA ENTERPRISE | 3.79 | 3.73 | 98.32 | 0
36 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Malay Kumar Aari, J.L. No.-46, Plot No.-651, Mouza-Bar Kasaria, G.P.-Khejuri b)Near house of Asutosh Mahakal, J.L. No.-37, Plot No.-1291, Mouza- Kastala , G.P.-Khejuri |  | Junior Engineer | ORD/000671/2021-2022 | 1973/TD | 04/03/2022 | 25/03/2022 | GIRI ENTERPRISE | 3.79 | 3.78 | 99.68 | 0
37 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Uttar Bagpura, Plot No. 135, J.L.No. 202 & Mouza - Biswanathpur, Plot No. 962, J.L.No. 233 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000739/2021-2022 | 2125/TD | 17/03/2022 | 01/04/2022 | MAITY CONSTRUCTION | 3.57 | 3.32 | 93.14 | 0
38 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza- Biswanathpur, Plot No. 574, J.L.No. 233 & Mouza - Talgachhari, Plot No. 332/151, J.L.No. 108 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000740/2021-2022 | 2126/TD | 17/03/2022 | 01/04/2022 | KOUSHIK MALLICK | 3.57 | 3.34 | 93.6 | 0
39 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bansbani, Plot No. 8, J.L.No. 70 & Mouza - Kantabani, Plot No. 63, J.L.No. 35 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000724/2021-2022 | 2113/TD | 17/03/2022 | 01/04/2022 | PARIA ENTERPRISE | 3.57 | 3.28 | 91.94 | 0
40 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at infront of Kalikapur Masjit, J.L. No. 250, Dag No. 669 & in Keshobpur Gram in front of Badal Shamal's house, J.L. No. 254 Dag No. 814 under Satilapur G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000742/2021-2022 | 2128/TD | 17/03/2022 | 01/04/2022 | PULAK KUMAR SAMANTA | 3.57 | 3.41 | 95.63 | 0
41 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Amadpur, Plot No. 59, J.L.No. 189 & Mouza - Kourpur, Plot No. 191, J.L.No. 187 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000762/2021-2022 | 2137/TD | 17/03/2022 | 01/04/2022 | DHANANJOY DAS | 3.57 | 3.57 | 99.96 | 0
42 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Amdai, Plot No. 120, J.L.No.55 & Mouza - Bindhya, Plot No. 91, J.L.No. 124 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000763/2021-2022 | 2138/TD | 17/03/2022 | 01/04/2022 | DHANANJOY DAS | 3.57 | 3.48 | 97.55 | 0
43 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Simulia, Plot No. 128, J.L.No.103 & Mouza -Chatla, Plot No. 2384, J.L.No. 93 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000765/2021-2022 | 2140/TD | 17/03/2022 | 01/04/2022 | DHANANJOY DAS | 3.57 | 3.48 | 97.55 | 0
44 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Schedule for Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Parimal Kanti Das, J.L. No.-43, Plot No.-189, Mouza-Mansinghabar, , G.P.-Khejuri b)Near house of Nilmani Dhali, J.L. No.-55, Plot No.-116, Mouza-Satsimali , G.P.-Khejuri |  | Junior Engineer | ORD/000674/2021-2022 | 1976/TD | 04/03/2022 | 25/03/2022 | PARTHA CONSTRUCTION | 3.79 | 3.78 | 99.68 | 0
45 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Bolkushda, Plot No. 734, J.L.No.90 & Mouza -Erendabar, Plot No. 184, J.L.No. 147 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000766/2021-2022 | 2141/TD | 17/03/2022 | 01/04/2022 | DHANANJOY DAS | 3.57 | 3.55 | 99.42 | 0
46 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Bahiya, Plot No. 128, J.L.No.51 & Mouza -Ghabi, Plot No. 82/6, J.L.No.66 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000770/2021-2022 | 2145/TD | 17/03/2022 | 01/04/2022 | AJIT KUMAR SOM | 3.57 | 3.43 | 96.26 | 0
47 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Chhatri, Plot No. 2481, J.L.No.184 & Mouza -Boyespur, Plot No. 297, J.L.No.10 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000771/2021-2022 | 2146/TD | 17/03/2022 | 01/04/2022 | AJIT KUMAR SOM | 3.57 | 3.43 | 96.27 | 0
48 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kalyanpur, Plot No. 498, J.L.No.54 & Mouza -Kiya, Plot No. 511, J.L.No.15 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000774/2021-2022 | 2149/TD | 17/03/2022 | 01/04/2022 | KAMAL KUMAR ROY | 3.57 | 3.47 | 97.21 | 100
49 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza Tajpur, Plot No. 171, J.L.No. 244 & Mouza-Jaldha, Plot No. 631, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000693/2021-2022 | 2087/TD | 17/03/2022 | 01/04/2022 | BASANTA KUMAR MAITY | 3.57 | 3.16 | 88.54 | 0
50 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Basudev Das, J.L. No.-47, Plot No.-443, Mouza-Sathkhanda, , G.P.-Khejuri b)Near house of Prajapati Mandal, J.L. No.-77, Plot No.-156, Mouza-Dhobaghata Bamanchak , G.P.-Khejuri |  | Junior Engineer | ORD/000675/2021-2022 | 1977/TD | 04/03/2022 | 25/03/2022 | SWARUPANANDA DAS | 3.79 | 3.78 | 99.68 | 0
51 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Alakranjan Paria, J.L. No.-39, Plot No.-395, Mouza-Kunjapur, , G.P.-Khejuri b)Near house of Sisir karan, J.L. No.-41, Plot No.-300, Mouza-Satkumari , G.P.-Khejuri |  | Junior Engineer | ORD/000676/2021-2022 | 1978/TD | 04/03/2022 | 25/03/2022 | BIBEKANANDA DAS | 3.79 | 3.78 | 99.68 | 0
52 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Shipur, Plot No. 607, J.L.No.96 & Mouza - Barandia, Plot No. 84, J.L.No.84 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000778/2021-2022 | 2154/TD | 17/03/2022 | 01/04/2022 | SAI TUBE CO. | 3.57 | 3.2 | 89.68 | 0
53 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Satkania, Plot No. 183, J.L.No.95 & Mouza - Vetia, Plot No. 51, J.L.No.77 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur D |  | Junior Engineer | ORD/000779/2021-2022 | 2155/TD | 17/03/2022 | 01/04/2022 | SAI TUBE CO. | 3.57 | 3.16 | 88.66 | 0
54 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza-Chandpur, Plot No. 156, J.L.No. 237 & MOuza-Kshirpal, Plot No. 521, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000695/2021-2022 | 2089/TD | 17/03/2022 | 01/04/2022 | BASANTA KUMAR MAITY | 3.57 | 3.3 | 92.58 | 0
55 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 160, Plot No.-3128, Mouza- Dekhali,J.L. No.-20, G.P.-Haludbari b) Near Natun Bazar Kali Mandir, Booth no 161, JL No.-20,Plot No.-1040, Mouza- Dekhali , G.P.-Haludbari. |  | Junior Engineer | ORD/000677/2021-2022 | 1979/TD | 04/03/2022 | 25/03/2022 | GITA ENTERPRISE | 3.79 | 3.75 | 98.91 | 0
56 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Booth no 145, Plot No.-1868, Mouza- Katickhali,J.L. No.-35, G.P.-Haludbari b) Booth no 145, JL No.-35,Plot No.-1486, Mouza- Katickhali , G.P.-Haludbari. |  | Junior Engineer | ORD/000678/2021-2022 | 1980/TD | 04/03/2022 | 25/03/2022 | SUBHENDU HAZRA | 3.79 | 3.77 | 99.4 | 0
57 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Gholai, Plot No. 7, J.L.No.111 & Mouza - Bahalia, Plot No. 427, J.L.No. 91 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000764/2021-2022 | 2139/TD | 17/03/2022 | 01/04/2022 | AJIT KUMAR SOM | 3.57 | 3.31 | 92.8 | 0
58 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At SSK School, J.L. No.-96, Mouza-Matilal Chak, G.P.-Nijkasba b)At Barik Pally, J.L. No.-96, Plot No.-133, Mouza- Matilal Chak, G.P.-Nijkasba |  | Junior Engineer | ORD/000654/2021-2022 | 1969/TD | 04/03/2022 | 25/03/2022 | JASODA ENTERPRISE | 3.79 | 3.78 | 99.68 | 0
59 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kasbagola, Plot No. 2176, J.L.No.62 & Mouza -Kalyanpur, Plot No. 582/713, J.L.No.54 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000769/2021-2022 | 2144/TD | 17/03/2022 | 01/04/2022 | AJIT KUMAR SOM | 3.57 | 3.44 | 96.59 | 0
60 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Mahabishra, Plot No. 1547, J.L.No.145 & Mouza -Bahalia, Plot No. 885, J.L.No.92 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000772/2021-2022 | 2147/TD | 17/03/2022 | 01/04/2022 | KAMAL KUMAR ROY | 3.57 | 3.44 | 96.29 | 100
61 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Chirulia, Plot No. 526, J.L.No.102 & Mouza -Negua, Plot No. 115, J.L.No.119 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000773/2021-2022 | 2148\TD | 17/03/2022 | 01/04/2022 | KAMAL KUMAR ROY | 3.57 | 3.44 | 96.27 | 100
62 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Alangiri, Plot No. 3959, J.L.No.48 & Mouza - Satkhanda, Plot No. 201, J.L.No.43 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000775/2021-2022 | 2150/TD | 17/03/2022 | 01/04/2022 | SAI TUBE CO. | 3.57 | 3.48 | 97.66 | 0
63 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Kudi, Plot No. 817, J.L.No.39 & Mouza - Chhatri, Plot No. 1475, J.L.No.184 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000776/2021-2022 | 2151/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.37 | 94.4 | 0
64 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Sannihari, Plot No. 714, J.L.No.32 & Mouza - Chhatri, Plot No. 2925, J.L.No.184 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000777/2021-2022 | 2152/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.3 | 92.53 | 0
65 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Alipur Sukanta SSK, Mouza -Alipur, JL.No- 183, Plot No.-406 & Bhatda Sahoo Para, Mouza - Bhatda, JL. No- 180, Plot No.- 2315 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000786/2021-2022 | 2162/TD | 17/03/2022 | 01/04/2022 | SAI TUBE CO. | 3.57 | 3.24 | 90.92 | 0
66 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bakharpur, Plot No. 140, J.L.No. 4 & Mouza - Kandagram, Plot No. 343, J.L.No. 1 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000718/2021-2022 | 2109/TD | 17/03/2022 | 01/04/2022 | SUBRATA KUMAR BERA | 3.57 | 2.96 | 82.99 | 0
67 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Dakshin Badhia, Plot No. 3584, J.L.No. 6 & Mouza - Paschim Santesswarpur, Plot No. 1072, J.L.No. 8 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000719/2021-2022 | 2110/TD | 17/03/2022 | 01/04/2022 | SUBRATA KUMAR BERA | 3.57 | 3.22 | 90.36 | 0
68 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Medinipur, Plot No. 720, J.L.No. 66 & Mouza - Dakshin Simulia, Plot No. 650, J.L.No. 84 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000720/2021-2022 | 2111/TD | 17/03/2022 | 01/04/2022 | SUBRATA KUMAR BERA | 3.57 | 3.28 | 91.9 | 0
69 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua (Maktab) Gram near Sk. Atauddin's house, J.L. No. 200, Dag No. 701 & Bararankua (Maktab) Gram near Sk. Nawas Ali's house, J.L. No. 200 Dag No. 562 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000751/2021-2022 | 2130/TD | 17/03/2022 | 01/04/2022 | LAKSHMI NARAYAN ENTERPRISE | 3.57 | 3.15 | 88.14 | 0
70 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua Gram near Swapan Bar's house, J.L. No. 200, Dag No. 792 & Bararankua Gram near Joydeb Mondal's house, J.L. No. 200 Dag No. 1048 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000752/2021-2022 | 2131/TD | 17/03/2022 | 01/04/2022 | LAKSHMI NARAYAN ENTERPRISE | 3.57 | 3.18 | 89.13 | 0
71 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 1098, J.L.No. 234 & Mouza - Lachhimpur, Plot No. 523, J.L.No. 219 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000697/2021-2022 | 2091/TD | 17/03/2022 | 01/04/2022 | BASANTA KUMAR MAITY | 3.57 | 3.39 | 95.13 | 0
72 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Jhamra Shyampur, Plot No. 352, J.L.No. 218 & Mouza - Tajpur, Plot No. 325, J.L.No. 244 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000698/2021-2022 | 2092/TD | 17/03/2022 | 01/04/2022 | BASANTA KUMAR MAITY | 3.57 | 3.19 | 89.52 | 0
73 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Tajpur, Plot No. 420, J.L.No. 244 & Mouza - Kshirpal, Plot No. 304, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000699/2021-2022 | 2093/TD | 17/03/2022 | 01/04/2022 | ABHIJIT BERA | 3.57 | 3.46 | 97 | 0
74 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandpur, Plot No. 513, J.L.No. 237 & Mouza - Chandpur, Plot No. 107, J.L.No. 237 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000707/2021-2022 | 2100/TD | 17/03/2022 | 01/04/2022 | CHARUBALA ENTERPRISE | 3.57 | 3.5 | 98.17 | 0
75 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bahadurpur, Plot No. 81, J.L.No. 209 & Mouza - Jhaugeria, Plot No. 173, J.L.No. 207 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000701/2021-2022 | 2095/TD | 17/03/2022 | 01/04/2022 | KAMAL KUMAR BERA | 3.57 | 3.42 | 95.91 | 0
76 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Verichawli, Plot No. 47, J.L.No. 239 & Mouza - Panchadaria, Plot No. 277, J.L.No. 221 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000700/2021-2022 | 2094/TD | 17/03/2022 | 01/04/2022 | KAMAL KUMAR BERA | 3.57 | 3.38 | 94.73 | 0
77 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Somaibasan, Plot No. 10, J.L.No. 89 & Mouza - Jagadispur, Plot No. 398, J.L.No. 87 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000733/2021-2022 | 2121/TD | 17/03/2022 | 01/04/2022 | KOUSHIK MALLICK | 3.57 | 3.51 | 98.28 | 0
78 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Jaldha, Plot No. 298, J.L.No. 242 & Mouza - Jaldha, Plot No. 773, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000704/2021-2022 | 2098/TD | 17/03/2022 | 01/04/2022 | DAS ENTERPRISE. | 3.57 | 3.37 | 94.57 | 0
79 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Kshirpal, Plot No. 336, J.L.No. 238 & Mouza - Kshirpal, Plot No. 885, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000710/2021-2022 | 2103/TD | 17/03/2022 | 01/04/2022 | GITA ENTERPRISE | 3.57 | 3.21 | 90.07 | 0
80 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Susanta Mondal's house, mouza - Dadanpatrabarh, J.L. No. 284, Dag No. 1141 & near SK Asef' House, mouza - Dakshin Purosottompur Arkboniya, J.L. No. 286, Dag No.1691 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000757/2021-2022 | 2136/TD | 17/03/2022 | 01/04/2022 | MRINAL KANTI PRADHAN | 3.57 | 3.29 | 92.2 | 0
81 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) At Anchal Para, J.L. No.-106, Mouza- Dakshin Kalagechia, G.P.-Nijkasba b)At Dakshin Matilal Chak, J.L. No.-96, Plot No.-665, Mouza- Matilal Chak , G.P.-Nijkasba |  | Junior Engineer | ORD/000651/2021-2022 | 1966/TD | 04/03/2022 | 25/03/2022 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.76 | 99.09 | 0
82 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) At Das Para, J.L. No.-95, Plot No.-751, Mouza- Lakshan chak, G.P.-Nijkasba b)At Sen Pally, J.L. No.-95, Plot No.-63, Mouza- Lakshan chak, G.P.-Nijkasba |  | Junior Engineer | ORD/000652/2021-2022 | 1967/TD | 04/03/2022 | 25/03/2022 | BADAL CHANDRA GOLE | 3.79 | 3.79 | 100 | 0
83 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)At Khatua Para, J.L. No.-58, Mouza-Paschim Bhanganmari, G.P.-Janka b)At Jhati Hari, J.L. No.-101, Plot No.-155, Mouza-Oashil Chak, G.P.-Janka |  | Junior Engineer | ORD/000655/2021-2022 | 1970/TD | 04/03/2022 | 25/03/2022 | PARIA ENTERPRISE | 3.79 | 3.78 | 99.68 | 0
84 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Sahadeb Manna Booth no 159, Plot No.-3899, G.P.-Haludbari b) Near house of Basudev Mandal Booth no 146, JL No.-35,Plot No.-342, Mouza-Katickhali, G.P.-Haludbari |  | Junior Engineer | ORD/000685/2021-2022 | 1984/TD | 04/03/2022 | 25/03/2022 | MRINAL KANTI PRADHAN | 3.79 | 3.79 | 100 | 0
85 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Srikanta Bera, J.L. No.-49, Plot No.-712, Mouza-Khejuri, G.P.-Khejuri b)Near house of Bhakti Nayak, J.L. No.-49, Plot No.-2453, Mouza-Khejuri, G.P.-Khejuri |  | Junior Engineer | ORD/000657/2021-2022 | 1972/TD | 04/03/2022 | 25/03/2022 | SACHINDRA NATH GIRI | 3.79 | 3.78 | 99.68 | 0
86 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Kultikri Sub-Centre, Mouza -Kultikri, JL.No- 197, Plot No.-1471 & Aranga Hat near GP office, Mouza - Paniparul, JL. No- 203, Plot No.- 3700 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000787/2021-2022 | 2163/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.37 | 94.4 | 0
87 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Giri Para Sunil Giri House, Mouza -Debidaspur, JL.No- 207, Plot No.-678 & Paniparul SSK, Mouza - Paniparul, JL. No- 203, Plot No.- 3910 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000788/2021-2022 | 2164/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.43 | 96.26 | 0
88 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Madhupur, Plot No. 240, J.L.No. 52 & Mouza - Dihibirkul, Plot No. 565, J.L.No. 51 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000728/2021-2022 | 2116/TD | 17/03/2022 | 01/04/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.35 | 94.07 | 0
89 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Barendranath Das House, Mouza -Kultikri, JL.No- 197, Plot No.-1718 & Near Kultikri Samsan math Parikshit Mandal House, Mouza - Kultikri, JL. No- 197, Plot No.- 614 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000789/2021-2022 | 2165/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.42 | 95.8 | 0
90 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Paniparul Pry.Health Centre, Mouza -Paniparul, JL.No- 203, Plot No.-2476 & Paniparul Hat, Mouza - Paniparul, JL. No- 203, Plot No.- 2021 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000790/2021-2022 | 2166/TD | 17/03/2022 | 01/04/2022 | SOM CONSTRUCTION | 3.57 | 3.4 | 95.35 | 0
91 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Gayendranath Garu House, Mouza -Dubda, JL.No- 191, Plot No.-6574 & Near Prasanta Sahoo Hazra House, Mouza - Dubda, JL. No- 191, Plot No.- 2092 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000791/2021-2022 | 2167/TD | 17/03/2022 | 01/04/2022 | ANUPAM CONSTRUCTION | 3.57 | 3.44 | 96.28 | 100
92 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 2 nos. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a) Near house of Sudarshan Singha, J.L. No.-98, Plot No.-527, Mouza- Thanaberia , G.P.-Nijkasba b) Near house of Anukul Das, J.L. No.-98, Plot No.-15, Mouza- Thanaberia , G.P.-Nijkasba |  | Junior Engineer | ORD/000634/2021-2022 | 1961/TD | 04/03/2022 | 25/03/2022 | M/S. NEW DINDA ENTERPRISE | 3.79 | 3.78 | 99.68 | 0
93 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Near Sudam Bera House, Mouza -Meheshpur, JL.No- 264 Plot No.-1699 & Basudevpur Hat, Mouza - Basudevpur, JL. No- 259, Plot No.- 5100 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000793/2021-2022 | 2169/TD | 17/03/2022 | 01/04/2022 | SAURAV HAZRA | 3.57 | 3.54 | 99.13 | 0
94 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Bararankua Gram near Amalendu Maity's house, J.L. No. 200, Dag No. 975 under Balisai G.P & near Abdul Rasid' House mouza - Sonamui, J.L. No. 282, Dag No. 325 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000753/2021-2022 | 2132/TD | 17/03/2022 | 01/04/2022 | MRINAL KANTI PRADHAN | 3.57 | 3.39 | 95.01 | 0
95 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Nejam's house, mouza - Sonamui, J.L. No. 282, Dag No. 114 & near Batul Das' Shop mouza - Silampur, J.L. No. 246, Dag No. 614 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000754/2021-2022 | 2133/TD | 17/03/2022 | 01/04/2022 | M/S SREE DURGA ENTERPRISE | 3.57 | 3.55 | 99.37 | 0
96 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Ramnagar, Plot No. 17, J.L.No. 205 & Mouza - Ghritapura, Plot No. 304, J.L.No. 107 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000735/2021-2022 | 2122/TD | 17/03/2022 | 01/04/2022 | KOUSHIK MALLICK | 3.57 | 3.19 | 89.39 | 0
97 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Dakshin Basulipat, Plot No. 238, J.L.No. 203 & Mouza - Barsolemanpur, Plot No. 230, J.L.No. 146 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000736/2021-2022 | 2123/TD | 17/03/2022 | 01/04/2022 | MAITY CONSTRUCTION | 3.57 | 3.29 | 92.2 | 0
98 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near Bishnu Pada Shyamal's house, mouza - Dadanpatrabarh, J.L. No. 284, Dag No. 1293 & near Parul Santra' House, mouza - Dadanpatrabarh, J.L. No. 284, Dag No.663 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000756/2021-2022 | 2135/TD | 17/03/2022 | 01/04/2022 | MRINAL KANTI PRADHAN | 3.57 | 3.32 | 93.14 | 0
99 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 1069, J.L.No. 228 & Mouza - Jashipur, Plot No. 998, J.L.No. 235 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000702/2021-2022 | 2096/TD | 17/03/2022 | 01/04/2022 | DAS ENTERPRISE. | 3.57 | 3.17 | 88.82 | 0
100 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Tengramari, Plot No. 988, J.L.No. 235 & Mouza - Tengramari, Plot No. 116, J.L.No. 242 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000703/2021-2022 | 2097/TD | 17/03/2022 | 01/04/2022 | DAS ENTERPRISE. | 3.57 | 3.09 | 86.64 | 0
101 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Bodhra, Plot No. 375, J.L.No. 234 & Mouza - Jaldha, Plot No. 551, J.L.No. 238 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000709/2021-2022 | 2102/TD | 17/03/2022 | 01/04/2022 | CHARUBALA ENTERPRISE | 3.57 | 3.41 | 95.54 | 0
102 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Durgapur, Plot No. 1446, J.L.No. 48 & Mouza - Dakshin Mukundapur, Plot No. 1473, J.L.No. 42 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000713/2021-2022 | 2104/TD | 17/03/2022 | 01/04/2022 | SUBRATA KUMAR BERA | 3.57 | 3.06 | 85.75 | 0
103 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Arjuni, Plot No. 173, J.L.No. 35 & Mouza - Koniara, Plot No. 101, J.L.No. 37 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000729/2021-2022 | 2117/TD | 17/03/2022 | 01/04/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.57 | 3.31 | 92.67 | 0
104 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 1 no. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Tapan Ari, Booth no 161, Plot No.-1086, Mouza-Dekhali,J.L. No.-20, G.P.-Haludbari |  | Junior Engineer | ORD/000110/2022-2023 | 209/CSD | 19/05/2022 | 02/06/2022 | MRINAL KANTI PRADHAN | 1.9 | 1.89 | 99.61 | 0
105 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 1 no. 100 mm x 40 mm dia x 240 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at different location after effect of "YASS" in Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. Location: a)Near house of Radhakrishna Das, J.L. No.-56, Plot No.-26, Mouza-Chak Arabari, G.P.-Khejuri |  | Junior Engineer | ORD/000111/2022-2023 | 241 / CSD | 27/05/2022 | 10/06/2022 | GIRI CONSTRUCTION | 1.9 | 1.89 | 99.68 | 0
106 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Deuli Gram near Sudhangshu Patra & Tapan Bar's Salt factory, J.L. No. 248, Dag No. 212 under Satilapur GP & in Narandia Gram near Kamal Maity house,, J.L. No. 198 Dag No. 634 under Balisai G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000743/2021-2022 | 2129/TD | 17/03/2022 | 01/04/2022 | JASODA ENTERPRISE | 3.57 | 3.11 | 87.18 | 0
107 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at near SK Kasim's house, mouza - Mandarmoni, J.L. No. 245, Dag No. 102 & near S.T Para Pond mouza - Dadanpatrabarh, J.L. No. 284, Dag No.127 under Kalindi G.P after effect of "YASS" in Ramnagar- II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000755/2021-2022 | 2134/TD | 17/03/2022 | 01/04/2022 | M/S SREE DURGA ENTERPRISE | 3.57 | 3.54 | 99.21 | 0
108 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza - Chandpur, Plot No. 226, J.L.No. 237 & Mouza - Lachhimpur, Plot No. 275, J.L.No. 219 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000708/2021-2022 | 2101/TD | 17/03/2022 | 01/04/2022 | CHARUBALA ENTERPRISE | 3.57 | 3.41 | 95.54 | 0
109 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Purba Asti SSK, Mouza -Asti, JL.No- 195 Plot No.-496/497 & Bankim Pukur Par, Mouza - Dubda, JL. No- 191, Plot No.- 4222 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000792/2021-2022 | 2168/TD | 17/03/2022 | 07/04/2022 | ANUPAM CONSTRUCTION | 3.57 | 3.44 | 96.28 | 100
110 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Kainthore, Plot No. 244, J.L.No.144 & Mouza -Bartana, Plot No. 3897, J.L.No. 12 after effect of "YASS" in Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000767/2021-2022 | 2142/TD | 17/03/2022 | 01/04/2022 | DHANANJOY DAS | 3.57 | 3.33 | 93.34 | 0
111 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Mouza -Ramnagar Purba, Plot No.354 , J.L.No. 205 & Mouza - Uttar Bagpura, Plot No. 20, J.L.No. 202 after effect of "YASS" in Ramnagar- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000738/2021-2022 | 2124/TD | 17/03/2022 | 01/04/2022 | MAITY CONSTRUCTION | 3.57 | 3.32 | 93.14 | 0
112 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Sinking of 100 mm x 40 mm dia x 220 mtr (av.) depth India Mark-II Tube well with PVC pipes including cost of all materials and construction of Platform (as per Depmental Drawing) at Dakshin Shyamharibar, Mouza -Shyamharibar, JL.No- 266 Plot No.-3611 after effect of "YASS" in Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  | Junior Engineer | ORD/000761/2021-2022 | 724/DSD | 17/03/2022 | 01/04/2022 | SANTANU PATTANAYAK | 1.78 | 1.77 | 99.35 | 0
113 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 316/TD | 11/05/2022 |  | Resource Division | 26.83 | 0 | 0 | 0
114 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 811/TD | 13/07/2022 |  | Resource Division | 8.84 | 0 | 0 | 0
115 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Indian Mark-II Tube Well at different location after effect of YAAS in Khejuri-II, Ramngar-I & II and Egra-I & II Block under Tamluk Division within Purba Medinipur District (Part-B) | SM/09340 | Disaster | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 810/TD | 13/07/2022 |  | Resource Division | 26.83 | 0 | 0 | 0
Total | [13 empty] | 462.75 | 342.86 | 74.09