## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Land filling with earth at H/W site at Narikeldaha Water Supply scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division. PHE Dte. | Assistant Engineer |  | ORD/000207/2022-2023 | 860/TD | 21/07/2022 | 28/07/2022 | GHOSH ENTERPRISE | 4.79 | 0 | 0 | 100
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000578/2021-2022 | 2049/TD | 14/03/2022 | 04/04/2022 | AQUATECH ENGINEERS | 15.11 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000580/2021-2022 | 2050/TD | 14/03/2022 | 04/04/2022 | AQUATECH ENGINEERS | 15.11 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Land filling with earth at 2nd. T/W site at Narikeldaha W/S scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer |  | ORD/000166/2022-2023 | 712/TSD | 16/06/2022 | 23/06/2022 | GHOSH ENTERPRISE | 1.43 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Bill for WBSEDCL for Quotation charges of Narikeldaha PWSS under Moyna Block under Tamluk Division, PHE Dte. |  |  | VCH/000572/2022-2023 | BP-2022-23-272 | 29/08/2022 | 29/08/2022 | WBSEDCL | 9.17 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied work under Narikeldaha & its adjoining moujas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer |  | ORD/000155/2021-2022 | 1154/TD | 30/11/2021 | 28/06/2022 | ARABINDA GHOSH | 523.45 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001259/2022-2023 | 2189/W/MMD | 12/12/2022 | 11/04/2023 | MENAKA ENTERPRISE | 13.09 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001258/2022-2023 | 2188/W/MMD | 12/12/2022 | 11/04/2023 | S.S.GHORAI | 13.09 | 0 | 0 | 75
9 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Additional work of Plinth protection, surface drain, septic tank, soak well, plumbing work, brick work,water arrangement of Toilet at 2nd T/W site for Narikeldaha Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000350/2022-2023 | 1172/TSD | 07/09/2022 | 02/10/2022 | GHOSH ENTERPRISE | 2.27 | 0 | 0 | 100
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Construction of M.S. Structure over irrigation canal to support 200 mm dia. DI (K-7) distribution pipe under Narikeldaha Water Supply Scheme at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=40.00 Mtr ) | Assistant Engineer |  | ORD/000395/2022-2023 | 1429/TD | 26/09/2022 | 21/10/2022 | KRISHNENDU SEKHAR DAS | 4.48 | 0 | 0 | 100
11 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 1685/TD | 31/01/2022 | 31/01/2022 | Resource Division | 12.47 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Material Requisition To Resource Division |  |  | RTOR000076/2021-2022 | 1832/TD | 15/02/2022 | 15/02/2022 | Resource Division | 36.27 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 1681/TD | 28/01/2022 | 28/01/2022 | Resource Division | 3.98 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Interconnection with laying of 150 mm dia DI (K-9) rising main from H/W site tube well to 2nd T/W site at Narikeldaha PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000231/2022-2023 | 972/TD | 03/08/2022 | 18/08/2022 | GHOSH ENTERPRISE | 5.7 | 0 | 0 | 100
15 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Functional Household Tap Connection (FHTC=798 nos)at Narikeldaha water supply scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000467/2023-2024 | 1447/TD | 13/07/2023 | 12/08/2023 | GHOSH ENTERPRISE | 31.51 | 0 | 0 | 100
16 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Laying Distribution system of Left-out portion of pipe line at Narikeldaha Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000566/2023-2024 | 2046/TD | 25/08/2023 | 24/09/2023 | GHOSH ENTERPRISE | 88.3 | 0 | 0 | 100
17 | PURBA MEDINIPUR | Moyna | Tamluk Division | Narikeldaha Piped Water Supply Scheme. | SM/09342 | New | Installation of display Board (80 nos.) at different work site for PHE Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000445/2024-2025 | 3544/TD | 14/11/2024 | 09/12/2024 | MISHRA ENTERPRISE | 13.33 | 0 | 0 | 100
Total | [13 empty] | 793.56 | 0 | 0