## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Protection arrangement of damaged boundary wall at Chapbasan store due to Amphan of Chapbasan W/S Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. |  |  | ORD/000936/2020-2021 | 03/Camp/TSD | 22/05/2020 | 22/05/2020 | MAA ANANDAMAYEE | 0.66 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Bahichberia water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000041/2020-2021 | 3357/TD | 26/03/2021 | 20/04/2021 | TARUN KOLEY | 4.85 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Repairing, renovation & construction of Boundary wall at Gobindanagar Zone-II Water Supply Scheme & its adjoining Mouzas Water Supply Scheme within Panskura-I Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2020-2021 | 3359/TD | 26/03/2021 | 20/04/2021 | MADAN MOHAN MAITY | 4.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying of UPVC Pipe line under Gogras Keshabbarh Water Supply Scheme & its adjoining mouzas W/S Scheme within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte.(PART-B). | Assistant Engineer |  | ORD/000051/2020-2021 | 3367/TD | 26/03/2021 | 20/04/2021 | TARUN KOLEY | 3.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Simulia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000052/2020-2021 | 3368/TD | 26/03/2021 | 20/04/2021 | GHOSH ENTERPRISE | 4.82 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Thekuachak Zone- I Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer, Headquaters |  | ORD/000053/2020-2021 | 3369/TD | 26/03/2021 | 20/04/2021 | GHOSH ENTERPRISE | 4.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Erasal H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000042/2020-2021 | 3358/TD | 26/03/2021 | 20/04/2021 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.8 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of Boundary wall and repairing & Renovation of old wall at Chapbasan Store of Chapbasan water supply scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. (Part-II) . | Assistant Engineer | Junior Engineer | ORD/000050/2020-2021 | 3366/TD | 26/03/2021 | 20/04/2021 | M/S MONDAL CONSTRUCTION & CO. | 4.63 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of Boundary wall and Lantern net of OHR at H/W site and Earth filling at 2nd T/W Site and damage portion of pipe line of Muradpur Water Supply Scheme under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000044/2020-2021 | 3360/TD | 26/03/2021 | 20/04/2021 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.83 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Construction of guard wall for protection of rising main line & additional work of septic tank, plinth protection work at 2nd T/W site for Alinan Zone -I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000046/2020-2021 | 3362/TD | 26/03/2021 | 20/04/2021 | TAPAS SANTRA | 4.79 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000047/2020-2021 | 3363/TD | 26/03/2021 | 20/04/2021 | J.M. CONSTRUCTION | 3.93 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying distribution system of UPVC Pipe line by different dia. UPVC pipes for Nodal point (3-21,21-23,23-63) damaged of Dakshin Mechogram Water Supply Scheme at H/W site within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2020-2021 | 3377/TD | 26/03/2021 | 20/04/2021 | PURNA CHANDRA BARH | 4.85 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | 125mm. dia. Eucalyptus bullah pilling for protecting the pipe line at pond side and damage portion of pipe line at Rashikachak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000055/2020-2021 | 3371/TD | 26/03/2021 | 20/04/2021 | BAGLAMUKHI SECURITY SERVICE | 4.84 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Khejurberia H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. (Rate as per PWD 2nd Corrigendum , w.e.f. 04.06.2018) | Assistant Engineer | Junior Engineer | ORD/000094/2020-2021 | 3379/TD | 26/03/2021 | 20/04/2021 | J.S. CONSTRUCTION | 4.82 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Thekuachak Zone- II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer, Headquaters |  | ORD/000088/2020-2021 | 3373/TD | 26/03/2021 | 20/04/2021 | SWAPAN KUMAR MAITY | 4.84 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Jalpai Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000089/2020-2021 | 3374/TD | 26/03/2021 | 20/04/2021 | J.M. CONSTRUCTION | 4.85 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000090/2020-2021 | 3375/TD | 26/03/2021 | 20/04/2021 | S.K. MONDAL | 3.93 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying of 90mm dia. UPVC Pipe line under Gogras Keshabbarh W/S Scheme & its adjoining mouzas Water Supply Scheme within Panskura Block under Tamluk Sub- Division of Tamluk Division, PHE Dte.(PART-A). | Assistant Engineer |  | ORD/000091/2020-2021 | 3376/TD | 26/03/2021 | 20/04/2021 | TARUN KOLEY | 4.76 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Dakshin Dhalhara Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000093/2020-2021 | 3378/TD | 26/03/2021 | 20/04/2021 | BAGLAMUKHI SECURITY SERVICE | 4.85 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of part Boundary wall & repairing & renovation of old wall at Dakshin Gumai H/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. (Rate as per PWD 2nd Corrigemdum , w.e.f. 04.06.2018) | Assistant Engineer | Junior Engineer | ORD/000938/2020-2021 | 611/TSD | 12/11/2020 | 07/12/2020 | M/S MONDAL CONSTRUCTION & CO. | 1.92 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Relaying of pipe line of Erasal & its adjoining mouzas W/S Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000939/2020-2021 | 610/TSD | 12/11/2020 | 07/12/2020 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.72 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Alinan zone - I water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000940/2020-2021 | 614/TSD | 12/11/2020 | 07/12/2020 | TAPAS SANTRA | 2.91 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Acceptance-cum-work order for New construction of part Boundary wall & repairing & renovation of old wall at Khejurberia 2nd T/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000937/2020-2021 | 619/TSD | 13/11/2020 | 08/12/2020 | RAI CONSTRUCTION | 1.6 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line and its allied works for Dakshin Gumai Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000045/2020-2021 | 3361/TD | 26/03/2021 | 20/04/2021 | M/S MONDAL CONSTRUCTION & CO. | 4.85 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Gobindanagar Zone-I water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000048/2020-2021 | 3364/TD | 26/03/2021 | 20/04/2021 | MRITYUNJOY PARIA | 4.84 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Relaying of pipe line of Chatra & its adjoining mouzas W/S Scheme at Sahid Matangani Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000049/2020-2021 | 3365/TD | 26/03/2021 | 20/04/2021 | BAGLAMUKHI SECURITY SERVICE | 4.85 | 0 | 0 | 0
27 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-laying Distribution system of pipe line and its allied works for Bargodagodar water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000040/2020-2021 | 3356/TD | 26/03/2021 | 20/04/2021 | S.K. MONDAL | 4.84 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Protection arrangement at h/w site of Erashal W/S Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. |  |  | ORD/000949/2020-2021 | 04/Camp/TSD | 22/05/2020 | 25/05/2020 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.22 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Renovation & repairing of Guard Room, Gunman Room, Godown & 2nd T/W pump house of Chapbasan Water Supply Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2020-2021 | 3372/TD | 26/03/2021 | 20/04/2021 | S.D. CONSTRUCTION | 4.05 | 0 | 0 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | New construction of part Boundaty wall & repairing & renovation of old wall (H/W & 2nd)site at Bahichberia pwss under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000944/2020-2021 | 620/TSD | 13/11/2020 | 08/12/2020 | S.D. CONSTRUCTION | 2.9 | 0 | 0 | 0
31 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | 125mm. dia.Eucalyptus bullah pilling for protecting the pipe line at pond side of Habichak & its adjoining mouzas W/S Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000948/2020-2021 | 621/TSD | 13/11/2020 | 08/12/2020 | SWADHIN KUMAR CHAKRABORTY | 2.91 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall, OHR due to AMPHAN Cyclone of different piped water supply schemes under Tamluk Sub-Division. | SM/09354 | Disaster | Re-Laying Distribution system of pipe line damaged due to AMPHAN and its allied works for Alinan zone - II water supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000945/2020-2021 | 615/TSD | 12/11/2020 | 07/12/2020 | TARUN KOLEY | 2.92 | 0 | 0 | 0
Total | [13 empty] | 125.37 | 0 | 0