## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Gholepukuria Zone-I Water supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2020-2021 | 3400/TD | 26/03/2021 | 10/04/2021 | ZENITH CONSTRUCTION | 4.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of SONACHURA Water Supply Scheme within Nandigram -I Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2020-2021 | 3401/TD | 26/03/2021 | 10/04/2021 | RAJ KUMAR SINGHA | 4.37 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Work for repair and construction of damaged Boundary Wall due to Amphoon Cyclone at Natshal Lakshya Store (Zone-I) Water Supply scheme Head work site cum store under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000069/2020-2021 | 3403/TD | 26/03/2021 | 10/04/2021 | ZENITH CONSTRUCTION | 4.78 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at Head Work Site of Tabakhali Water Supply Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000070/2020-2021 | 3404/TD | 26/03/2021 | 10/04/2021 | NARAYAN CHANDRA DAS | 4.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Asodtalia Water supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2020-2021 | 3397/TD | 26/03/2021 | 10/04/2021 | RAJ KUMAR SINGHA | 3.69 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of CHAITANYAPUR (Zone-I) Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000064/2020-2021 | 3398/TD | 26/03/2021 | 10/04/2021 | RAJ KUMAR SINGHA | 4.47 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Begunberia Water supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000057/2020-2021 | 3382/TD | 26/03/2021 | 10/04/2021 | RAJ KUMAR SINGHA | 3.79 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Work for repair of damaged pipe line due to Amphoon cyclone of Tabakhali Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2020-2021 | 3385/TD | 26/03/2021 | 10/04/2021 | NARAYAN CHANDRA DAS | 4.49 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Gholepukuria Zone-II Water Supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2020-2021 | 3384/TD | 26/03/2021 | 10/04/2021 | ZENITH CONSTRUCTION | 4.85 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2020-2021 | 3383/TD | 26/03/2021 | 10/04/2021 | RAJ KUMAR SINGHA | 3.97 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged switch room -cum chlorine room with water supply & sanitary arrangement due to Amphoon cyclone at Head work site of Dhenkua water supply scheme under Haldia Sub-Division of Tamluk Division PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000123/2021-2022 | 1052/TD | 02/11/2021 | 17/11/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.16 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair Construction and upgradation of damaged Boundary Wall due to Amphoon Cyclone at the office of the Assistant Engineer, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000327/2021-2022 | 1711/TD | 01/02/2022 | 18/03/2022 | RAI CONSTRUCTION | 4.74 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair Construction and upgradation of damaged Boundary Wall due to Amphoon Cyclone at the office of the Assistant Engineer, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000328/2021-2022 | 1712/TD | 01/02/2022 | 18/03/2022 | MODERN CONSTRUCTION | 4.45 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Natshal Lakhya (Zone-II ) Water supply Scheme within Mahisadal Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2020-2021 | 857/HSD | 18/03/2021 | 02/04/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 1.17 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repairing of defunct Mark-II Tube Well during Amphan- 2020 at different place (25 nos.) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000339/2022-2023 | 1290/TD | 13/09/2022 | 23/09/2022 | TAPAN BERA | 4.38 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Work Order for repairing of defunct Mark-II Tube well during Amphan - 2020 at different places (11 nos) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000356/2022-2023 | 574/HSD | 22/08/2022 | 29/08/2022 | TAPAN BERA | 1.93 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repairing of defunct Mark-II Tube Well during Amphan- 2020 at different place (25 nos.) within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000340/2022-2023 | 1291/TD | 13/09/2022 | 23/09/2022 | TAPAN BERA | 4.38 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Damaged pipeline, pump house and boundary wall due to AMPHAN Cyclone of different piped water supply schemes in Sutahata, Mahishadal, Haldia, Nandigram-I and Nandigram-II block. | SM/09355 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Dhenkua Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2020-2021 | 3399/TD | 26/03/2021 | 10/04/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.73 | 0 | 0 | 0
Total | [13 empty] | 71.89 | 0 | 0