## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under RAMNAGAR Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000095/2021-2022 | 647/TD | 08/09/2021 | 28/09/2021 | SNEHESH SEN | 3.8 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under HALDIA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000096/2021-2022 | 648/TD | 08/09/2021 | 28/09/2021 | LOKENATH ENTERPRISES | 3.97 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under RANISAI Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000097/2021-2022 | 649/TD | 08/09/2021 | 28/09/2021 | LOKENATH ENTERPRISES | 3.9 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under TAMALDA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000091/2021-2022 | 643/TD | 08/09/2021 | 28/09/2021 | SOM CONSTRUCTION | 3.94 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under BADHIA Water Supply Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000094/2021-2022 | 646/TD | 08/09/2021 | 28/09/2021 | SOM CONSTRUCTION | 3.2 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Chirulia Chatla Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000092/2021-2022 | 644/TD | 08/09/2021 | 28/09/2021 | SOM CONSTRUCTION | 3.87 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Kasbagola W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000355/2020-2021 | 320/A/DSD | 28/12/2020 | 17/01/2021 | DHANANJOY DAS | 2.89 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under NARANDIHA W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000354/2020-2021 | 319/A/DSD | 28/12/2020 | 17/01/2021 | CHARUBALA ENTERPRISE | 2.92 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Repairing of existing Boundary Wall & Door,Window,Ventilator of Digha S.G. Hospital due to combats Super Cyclonic Storm "AMPHAN" within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000358/2020-2021 | 322/DSD | 28/12/2020 | 17/01/2021 | LOKENATH ENTERPRISES | 1.95 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Kudi W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000349/2020-2021 | 315/DSD | 24/12/2020 | 13/01/2021 | AJIT KUMAR SOM | 2.92 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Paniparul W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000357/2020-2021 | 320/C/DSD | 28/12/2020 | 17/01/2021 | AJIT KUMAR SOM | 2.65 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under SANKARPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000346/2020-2021 | 315/A/DSD | 24/12/2020 | 13/01/2021 | MAITY CONSTRUCTION | 2.7 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under KANPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000348/2020-2021 | 324/A/DSD | 28/12/2020 | 17/01/2021 | MAITY CONSTRUCTION | 2.99 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Madhabpur W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000356/2020-2021 | 320/B/DSD | 28/12/2020 | 17/01/2021 | S.D. CONSTRUCTION | 2.87 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Astichak W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000352/2020-2021 | 314/DSD | 24/12/2020 | 13/01/2021 | ANUPAM CONSTRUCTION | 2.87 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under BAGMARI W/S Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000353/2020-2021 | 318/A/DSD | 28/12/2020 | 17/01/2021 | LAKSHMI NARAYAN ENTERPRISE | 2.89 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under CHANDANPUR W/S Scheme under Digha Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000350/2020-2021 | 324/DSD | 28/12/2020 | 17/01/2021 | BASANTA KUMAR MAITY | 2.61 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Bathuary. W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000351/2020-2021 | 314/A/DSD | 24/12/2020 | 13/01/2021 | BHOWMIK & SONS | 2.11 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under DIGHA AUGMENTATION(E.Z.) Water Supply Scheme under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000050/2021-2022 | 370/TD | 19/07/2021 | 08/08/2021 | CHARUBALA ENTERPRISE | 3.86 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary Wall & Door, Windows of Main Building of Digha SG Hospital and other piped water supply scheme due to combats Cyclonic Storm AMPHAN in different blocks under Digh Sub-Di | SM/09356 | Disaster | Relaying damaged pipeline & others allied works due to combats cyclonic Storm "AMPHAN" under Mandarmoni Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000093/2021-2022 | 645/TD | 08/09/2021 | 28/09/2021 | KAMAL KUMAR ROY | 3.02 | 0 | 0 | 0
Total | [13 empty] | 61.94 | 0 | 0