## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-28-30,50-51,57-58,41-42,44-46,30-31,6-7,11-14,78-76,291-293,18-20,165-167,122-123,91-92 & 90-91 under Barasubarnanagar W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000343/2020-2021 | 339 / CSD | 10/11/2020 | 01/12/2020 | JASODA ENTERPRISE | 2.48 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-98-99,99-100,100-101,59-61,76-77,18-19,51-24,13-14 & 72-68 under Sofiabad W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000344/2020-2021 | 340 / CSD | 10/11/2020 | 01/12/2020 | KAMAL KUMAR BERA | 1.99 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Madhakhali W/S Scheme of Contai Sub- Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000336/2020-2021 | 399 / CSD | 24/12/2020 | 14/01/2021 | SUBHRANGSHU SEKHAR GIRI | 2.45 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Mukutshila Zone-II W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000329/2020-2021 | 347/CSD | 24/11/2020 | 15/12/2020 | SUBRATA KUMAR BERA | 2.78 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between 126-127,127-129,79-82,3-4,84-89,90-92,60-62,39-41,12-16,68-72,101-99,74-75 & 87-88 under HAIPUR W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000338/2020-2021 | 411 / CSD | 29/12/2020 | 19/01/2021 | SRIMANTA KUMAR MAITY | 2.37 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Baghaput W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000331/2020-2021 | 372 / CSD | 09/12/2020 | 30/12/2020 | M/S MONDAL CONSTRUCTION & CO. | 1.89 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Sapai W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000333/2020-2021 | 380 / CSD | 14/12/2020 | 04/01/2021 | AHINDRA BARIK | 1.65 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Kanakpur W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000341/2020-2021 | 331 / CSD | 05/11/2020 | 26/11/2020 | SRIMANTA KUMAR MAITY | 1.51 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bagmari W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000342/2020-2021 | 333 / CSD | 09/11/2020 | 30/11/2020 | BIBEKANANDA DAS | 1.77 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Murisai W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000332/2020-2021 | 377 / CSD | 11/12/2020 | 01/01/2021 | MRINAL KANTI PRADHAN | 1.93 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Kumirda W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000334/2020-2021 | 390 / CSD | 21/12/2020 | 11/01/2021 | PARIA ENTERPRISE | 2.56 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Contai Municipality W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000335/2020-2021 | 396 / CSD | 21/12/2020 | 11/01/2021 | SUBHRANGSHU SEKHAR GIRI | 0.99 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN"in between N.P. 103-105,106-117,127-128,142-144,160-161,111-158,118-120,157-801,120-156,140-135,164-805,170-171 &136-135 under Bamunia W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000339/2020-2021 | 341/CSD | 10/11/2020 | 01/12/2020 | GIRI CONSTRUCTION | 2.46 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Pratapdighi W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000340/2020-2021 | 338 / CSD | 10/11/2020 | 01/12/2020 | GIRI CONSTRUCTION | 2.99 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-125-128,13-16,125-126,134-135,150-153 & 174-175 under BANKIPUT W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000345/2020-2021 | 345 / CSD | 23/11/2020 | 14/12/2020 | GITA ENTERPRISE | 2.46 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Nijkasba W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000337/2020-2021 | 410 / CSD | 29/12/2020 | 19/01/2021 | PURNA CHANDRA BARH | 1.15 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Jalpai Part-II Water supply Scheme within Nandigram-II Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000811/2020-2021 | 854/HSD | 18/03/2021 | 02/04/2021 | BHOWMIK & SONS | 2.54 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Dariapur Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000189/2020-2021 | 2762/TD | 27/01/2021 | 26/02/2021 | S. A. ENTERPRISE | 4.81 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-II Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000076/2020-2021 | 3392/TD | 26/03/2021 | 16/04/2021 | SRIMANTA KUMAR MAITY | 4.82 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at Head work site of Begunberia Water Supply. Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000068/2020-2021 | 3402/TD | 26/03/2021 | 10/04/2021 | RAI CONSTRUCTION | 4.6 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-I Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000075/2020-2021 | 3391/TD | 26/03/2021 | 16/04/2021 | SRIMANTA KUMAR MAITY | 4.84 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Amtalia Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000077/2020-2021 | 2138/TD | 09/11/2020 | 30/11/2020 | PARIA ENTERPRISE | 4.84 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Khejuri Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000079/2020-2021 | 3393/TD | 26/03/2021 | 16/04/2021 | GIRI ENTERPRISE | 4.82 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-130-150,182-183,184-161,152-156,93-96,156-160,164-170,111-114,129-131,135-139,140-150,156-157,164-165,121-123,191-192 &160-161 under HAIPUR Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000080/2020-2021 | 3394/TD | 26/03/2021 | 16/04/2021 | SRIMANTA KUMAR MAITY | 3.46 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Talda Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000082/2020-2021 | 3396/TD | 26/03/2021 | 16/04/2021 | BADAL CHANDRA GOLE | 4.26 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000083/2020-2021 | 3380/TD | 26/03/2021 | 16/04/2021 | SRIMANTA KUMAR MAITY | 3.22 | 0 | 0 | 0
27 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Bhajachauli Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000071/2020-2021 | 3387/TD | 26/03/2021 | 16/04/2021 | BIBEKANANDA DAS | 4.81 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Chandiveti Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000072/2020-2021 | 3388/TD | 26/03/2021 | 16/04/2021 | SUSANTA KUMAR KAR | 4.21 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm "AMPHAN" under Durmuth Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000073/2020-2021 | 3389/TD | 26/03/2021 | 16/04/2021 | PRANAB KUMAR DAS | 4.84 | 0 | 0 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" in between N.P.-71-72,72-79,76-80,80-86,92-98,16-17,88-89,99-118,18-26,54-64,52-48,34-35,35-36,32-34,8-10,5-7 & 29-30 under BANKIPUT Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000114/2020-2021 | 2139/TD | 09/11/2020 | 30/11/2020 | GITA ENTERPRISE | 3.35 | 0 | 0 | 0
31 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Supercyclonic Storm "AMPHAN" under Amarshikasba Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000074/2020-2021 | 3390/TD | 26/03/2021 | 16/04/2021 | M/S. NEW DINDA ENTERPRISE | 4.43 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Contai S.A. Zone-III Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000326/2020-2021 | 3381/TD | 26/03/2021 | 16/04/2021 | PRANAB KUMAR DAS | 3.4 | 0 | 0 | 0
33 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Contai Saline Area Zone-IV W/S Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000330/2020-2021 | 368 / CSD | 03/12/2020 | 24/12/2020 | SUBHENDU HAZRA | 1.23 | 0 | 0 | 0
34 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repair of pump house due to Amphoon Cyclone at 1st Tube well site of Solat water supply scheme under Haldia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000803/2021-2022 | 293/HSD | 15/09/2021 | 30/09/2021 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 1.04 | 0 | 0 | 0
35 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repair of damaged Boundary Wall due to Amphoon Cyclone at 2nd Tube well site of Begunberia W/S. Scheme under Haldia Sub-Division in Tamluk Division, P.H.E. Dte. Purba Medinipur. (As per deptt. Drawing and design) | Assistant Engineer | Junior Engineer | ORD/000809/2020-2021 | 856/HSD | 18/03/2021 | 02/04/2021 | SK. MD. MAINUL ISLAM | 2.91 | 0 | 0 | 0
36 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repair of damaged pipe line due to Amphoon cyclone of Mahammadpur Water supply Scheme within Nandigram-I Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000810/2020-2021 | 855 | 18/03/2021 | 02/04/2021 | TAPAN BERA | 2.01 | 0 | 0 | 0
37 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats supercyclonic Storm "AMPHAN" under Aladarput Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000084/2020-2021 | 2134/TD | 09/11/2020 | 30/11/2020 | MRINAL KANTI PRADHAN | 3.33 | 0 | 0 | 0
38 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying of damaged pipeline & others allied works due to combats Super cyclonic Storm 'AMPHAN' under Dariapur W/S Scheme under Tamluk Division, PHE Dte |  |  | VCH/000253/2022-2023 | BP-2022-23-92 | 14/06/2022 | 14/06/2022 | S.A. ENTERPRISE | 4.81 | 0 | 0 | 0
39 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Construction of Double Durma Mat works for temporary protection of Govt. materials of Ghatua store under Cotai Sub-Division of Tamluk Division P.H.E. Dte,Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000806/2020-2021 | 34 / CSD | 27/05/2020 | 03/06/2020 | BAGLAMUKHI SECURITY SERVICE | 0.37 | 0 | 0 | 0
40 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repairing of existing Store Room cum Guard Room with sanitary & water supply arrangements including Plinth Protection of Ghatua Store due to combats cyclonic Storm "AMPHAN" within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000266/2022-2023 | 1089/TD | 25/08/2022 | 04/10/2022 | M/S. NEW DINDA ENTERPRISE | 5.79 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Construction of Double Durma Mat works for temporary protection of Govt. materials of Mukutshila store under Cotai Sub-Division of Tamluk Division P.H.E. Dte,Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000807/2020-2021 | 35 / CSD | 27/05/2020 | 03/06/2020 | BAGLAMUKHI SECURITY SERVICE | 0.22 | 0 | 0 | 0
42 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Relaying damaged pipeline & others allied works due to combats Super Cyclonic Storm "AMPHAN" under Junbani Water Supply Scheme under Contai Sub- Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000081/2020-2021 | 3395/TD | 26/03/2021 | 16/04/2021 | BASANTA KUMAR MAITY | 4.79 | 0 | 0 | 0
43 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 100 Cum after effect of AMPHAN at Contai-II (Deshpran) Block within Bankiput W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000254/2021-2022 | 544 / CSD | 01/12/2021 | 22/12/2021 | GITA ENTERPRISE | 1.65 | 0 | 0 | 0
44 | PURBA MEDINIPUR |  | Tamluk Division | Relaying of damaged pipeline & others allied works and repairing of existing Boundary wall, Office Room, Store Room and Pump House with Sanitary & water supply arrangement including Plinth Protection of store room due to combats Cyclonic Storm AMPHAN in d | SM/09357 | Disaster | Repairing & Renovation of existing Sherkhanchak Laboratory Building with sanitary & water supply arrangements including Plinth Protection,Drain,Internal road due to super cyclonic Storm "AMPHAN" within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000317/2022-2023 | 516 / CSD | 08/08/2022 | 07/09/2022 | THE GOD FATHER TRADING & CO. | 2.38 | 0 | 0 | 0
Total | [13 empty] | 131.19 | 0 | 0