## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kasbagola Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2021-2022 | 1200/TD | 02/12/2021 | 22/12/2021 | RADIANT | 3.78 | 3.78 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Augmentation of ground water based Kasbagola Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Egra-I Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000426/2021-2022 | 1910/TD | 23/02/2022 | 22/08/2022 | KISHORE GHOSH | 287.79 | 156.81 | 54.49 | 70
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Sinking of 300 mm. x 200 mm. dia. x 230 mtr. deep tube well by direct rotary rig method using UPVC pipe and UPVC Deep Well Screen (RDS) at Kasbagola PWSS, Block- EGRA-I under Digha Sub-Division of Tamluk Division Dist- Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000575/2021-2022 | 2048/TD | 14/03/2022 | 04/04/2022 | KISHORE GHOSH | 13.75 | 10.69 | 77.8 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2021-2022 | 1955/TD | 04/03/2022 | 04/03/2022 | Resource Division | 11.7 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2021-2022 | 2189/TD | 21/03/2022 | 21/03/2022 | Resource Division | 14.39 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001925/2022-2023 | 844/W/MMD | 24/03/2023 | 11/07/2025 | ECO ENTERPRISE | 35.55 | 13.97 | 39.3 | 25
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Repairing of Pump house, Construction of Boundary Wall, Laying Rising main pipe line & Supply under JJM with allied work for Kasbagola PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000200/2023-2024 | 401/TD | 27/04/2023 | 24/06/2025 | ANUSKA ENTERPRISE | 26.15 | 14.62 | 55.89 | 95
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Construction of Pump House, Boundary Wall, of 3rd Tube Well site with allied works of Kasbagola & its adjoining mouzas W/S Scheme within Egra -I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000292/2023-2024 | 594/TD | 17/05/2023 | 16/07/2023 | CHAKRABORTY CONSTRUCTION | 13.42 | 5.07 | 37.75 | 90
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Requirement of additional pipeline to accommodate FHTC under JJM for Augmentation of Kasbagola PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000749/2023-2024 | 3191/TD | 11/12/2023 | 05/01/2024 | KISHORE GHOSH | 31.07 | 29.75 | 95.75 | 95
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Supply of CIDF sluice valve for Augmentation of Kasbagola PWSS within Egra-I Block under Digha Sub Division of Tamluk division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000620/2023-2024 | 2334/TD | 08/09/2023 | 18/09/2023 | KISHORE GHOSH | 3.38 | 3.38 | 100 | 100
11 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Kasbagola W/S Scheme (T/W-I) , Egra-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000130/2023-2024 | 859/CDD | 10/07/2023 | 22/04/2024 | PADMA ENGINEERING & CO. | 18.23 | 15.33 | 84.08 | 100
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Electric Quotiaton for Kasbagola Water Supply Scheme T/W-III (Ref. ID-204005246) |  |  | BILL/00380/2023-2024 | BP-2023-24-66 | 06/06/2023 | 06/06/2023 | WBSEDCL | 0.61 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Alamgiri Birbara Khosbagola Road from 5.80 Km. to 6.20 Km., 6.40 Km. to 6.50 Km. & 6.80 Km. to 7.00 Km. for laying water pipe line of Kasbagola PWSS. |  |  | BILL/00990/2024-2025 | BP-2024-25-493 | 01/10/2024 | 01/10/2024 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.24 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Quotation for new service connection at TW-4 of Kasbagola ws scheme under MMD, PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004773721 Con ID-204332518 |  |  | BILL/01328/2024-2025 | BP-2024-25-359 | 01/07/2024 | 01/07/2024 | WBSEDCL | 4.68 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Construction of Pump House (3.6mx 3.0m), Boundary Wall, Proposed Rising & Interconnection, Supply and delivery of different dia D.I. specials & fittings with allied works under JJM at 4th TW site for Augmentation of Kasbagola Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000592/2024-2025 | 490/TD | 06/02/2025 | 01/02/2026 | AYSAN KHAN | 15.06 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09402 | Augmentation | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division |  |  | BILL/00706/2025-2026 |  | 20/08/2025 | 20/08/2025 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.11 | 0 | 0 | 0
Total | [13 empty] | 486.68 | 253.4 | 52.07