## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000399/2021-2022 | 1862/TD | 17/02/2022 | 09/03/2022 | MAHAPRABHU ENTERPRISE | 4.83 | 4.63 | 95.8 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dwariberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2021-2022 | 1606/TD | 14/01/2022 | 03/02/2022 | RADIANT | 3.58 | 3.56 | 99.36 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Dwariberia Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000034/2022-2023 | 133/TD | 19/04/2022 | 10/05/2022 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Work order for Make approach road to access Rig Machine for Boring of Tube well at Head work site of Dwariberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000263/2022-2023 | 572/HSD | 17/08/2022 | 24/08/2022 | TAPAN BERA | 1.36 | 1.36 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (1003 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000392/2021-2022 | 1851/TD | 16/02/2022 | 28/03/2022 | SUDIPTA ROY | 75.32 | 73.42 | 97.48 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (737 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000394/2021-2022 | 1853/TD | 16/02/2022 | 28/03/2022 | JAI BHARAT COMMERCIAL CORPORATION | 74.58 | 74.45 | 99.83 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-J) | Assistant Engineer | Junior Engineer | ORD/000401/2021-2022 | 1864/TD | 17/02/2022 | 09/03/2022 | TARUN KHATUA | 4.85 | 4.84 | 99.86 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (101 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000526/2021-2022 | 2000/TD | 08/03/2022 | 28/03/2022 | A. K. SIKDAR | 35.52 | 35.15 | 98.96 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000397/2021-2022 | 1860/TD | 17/02/2022 | 09/03/2022 | SAYAN MAITY | 4.85 | 4.82 | 99.39 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000395/2021-2022 | 1854/TD | 16/02/2022 | 08/03/2022 | BUNBA CONSTRUCTION | 10.38 | 10.26 | 98.84 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. " (Part-M) | Assistant Engineer | Junior Engineer | ORD/000396/2021-2022 | 1855/TD | 16/02/2022 | 08/03/2022 | TAPAN BERA | 10.79 | 10.79 | 99.95 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000400/2021-2022 | 1863/TD | 17/02/2022 | 09/03/2022 | MODERN CONSTRUCTION | 4.85 | 4.81 | 99.21 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000398/2021-2022 | 1861/TD | 17/02/2022 | 09/03/2022 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.8 | 4.8 | 99.89 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (927 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000393/2021-2022 | 1852/TD | 16/02/2022 | 28/03/2022 | PALCON | 74.59 | 69.74 | 93.5 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Work Order for Laying of UPVC pipe line at Dwariberia Water supply Scheme (Node point 182-182A) within Haldia Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000262/2022-2023 | 571/HSD | 17/08/2022 | 01/09/2022 | TAPAN BERA | 1.57 | 1.57 | 100 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Repairing & renovation of Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Dwariberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000253/2022-2023 | 1045/TD | 16/08/2022 | 30/09/2022 | TARUN KHATUA | 4.09 | 3.82 | 93.33 | 100
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dwariberia water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001140/2022-2023 | 2121/W/MMD | 28/11/2022 | 28/03/2023 | PRANAB KUMAR DAS | 11.12 | 9.38 | 84.33 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2021-2022 | 1874/TD | 18/02/2022 | 18/02/2022 | Resource Division | 16 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2021-2022 | 2069/TD | 16/03/2022 | 16/03/2022 | Resource Division | 16.85 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (456 FHTC) of Dwariberia Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 1904/TD | 07/06/2024 | 09/06/2025 | SK. NUR ISLAM | 56.28 | 5.91 | 10.5 | 50
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Dwariberia & its adjoining moujas Water Supply Scheme within Haldia Block including supply of all labour & materials under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 1887/TD | 24/11/2022 | 01/03/2025 | MAA ANANDAMAYEE | 131.54 | 96.5 | 73.36 | 98
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Boundary wall including land development at Headwork site of Dwariberia Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000644/2023-2024 | 2596/TD | 10/10/2023 | 27/02/2025 | ELITE CONSTRUCTION | 18.69 | 7.13 | 38.17 | 1
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09444 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2024-2025 | 804/TD | 18/03/2025 | 18/03/2025 | Resource Division | 2.81 | 0 | 0 | 0
Total | [13 empty] | 588.29 | 445.97 | 75.81