## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Talda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2021-2022 | 1611/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.97 | 92.29 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000383/2021-2022 | 1823/TD | 11/02/2022 | 03/03/2022 | SUBRATA KUMAR BERA | 18.89 | 18.64 | 98.66 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-F) | Assistant Engineer | Junior Engineer | ORD/000380/2021-2022 | 1820/TD | 11/02/2022 | 03/03/2022 | M/S. NEW DINDA ENTERPRISE | 23.24 | 23.09 | 99.32 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- K) | Assistant Engineer | Junior Engineer | ORD/000385/2021-2022 | 1825/TD | 11/02/2022 | 03/03/2022 | SUKOMAL BERA | 14.52 | 14.44 | 99.45 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. . (PART-G) | Assistant Engineer | Junior Engineer | ORD/000381/2021-2022 | 1821/TD | 11/02/2022 | 03/03/2022 | BADAL CHANDRA GOLE | 19.35 | 19.13 | 98.83 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-H) | Assistant Engineer | Junior Engineer | ORD/000382/2021-2022 | 1822/TD | 11/02/2022 | 03/03/2022 | GIRI ENTERPRISE | 19.36 | 19.19 | 99.11 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- L) | Assistant Engineer | Junior Engineer | ORD/000386/2021-2022 | 1826/TD | 11/02/2022 | 03/03/2022 | ANUPAM CONSTRUCTION | 9.6 | 9.53 | 99.27 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000084/2022-2023 | 437-A/TD | 30/05/2022 | 19/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.88 | 7.88 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Talda,Murisai & Anurai Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000112/2022-2023 | 278 / CSD | 14/06/2022 | 29/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.34 | 2.34 | 100 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000361/2021-2022 | 1816/TD | 11/02/2022 | 28/03/2022 | M/S SREE DURGA ENTERPRISE | 95.89 | 89.58 | 93.43 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000377/2021-2022 | 1817/TD | 11/02/2022 | 23/03/2022 | AJIT KUMAR SOM | 77.52 | 75.76 | 97.73 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District.(PART- M) | Assistant Engineer | Junior Engineer | ORD/000387/2021-2022 | 1827/TD | 11/02/2022 | 03/03/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.62 | 9.54 | 99.2 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000379/2021-2022 | 1819/TD | 11/02/2022 | 03/03/2022 | SUBHENDU HAZRA | 24.07 | 23.63 | 98.19 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000094/2022-2023 | 451/TD | 31/05/2022 | 20/06/2022 | RAMASISH ENTERPRISE | 0.24 | 0.24 | 100 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Instalation of display Board at different work site of Augmentation of Talda- 1 no, Sapai- 1 no, Baghaput- 1 no & Kumirda - 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000512/2022-2023 | 812 / CSD | 21/10/2022 | 05/11/2022 | ABHIJIT BERA | 0.46 | 0.46 | 100 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2021-2022 | 1875/TD | 18/02/2022 | 18/02/2022 | Resource Division | 17.42 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2021-2022 | 2190/TD | 21/03/2022 | 21/03/2022 | Resource Division | 39.93 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000378/2021-2022 | 1818/TD | 11/02/2022 | 23/03/2022 | GIRI CONSTRUCTION | 58.08 | 56.04 | 96.48 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Providing FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-01) | Assistant Engineer | Junior Engineer | ORD/000049/2022-2023 | 287/TD | 05/05/2022 | 04/07/2022 | DAS CONSTRUCTION | 124.25 | 89.94 | 72.38 | 95
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube well of Talda Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001156/2023-2024 | 607/TD | 16/02/2024 | 07/03/2024 | KALPANA BUILDERS | 14.29 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Talda Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000118/2022-2023 | 613/TD | 21/06/2022 | 12/07/2022 | M/S BISWANATH CONSTRUCTION | 13.38 | 10.35 | 77.4 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Repairing Of Pump House ( House No-I & II) and Boundary Wall of Pump House No- II under Augmentation of Talda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000280/2023-2024 | 485/TD | 10/05/2023 | 09/06/2023 | M/S SREE DURGA ENTERPRISE | 3.65 | 0 | 0 | 100
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- J) | Assistant Engineer | Junior Engineer | ORD/000384/2021-2022 | 1824/TD | 11/02/2022 | 03/03/2022 | DHANANJOY DAS | 19.35 | 18.93 | 97.84 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Laying Distribution System (Nodal-36-89,89-131 & 131-139A,Part) of pipe line and its allied works for Talda water supply scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000741/2023-2024 | 3068/TD | 30/11/2023 | 25/12/2023 | ACHINTA KUMAR HALDER | 10.08 | 8.42 | 83.53 | 80
25 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of TALDA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-III, WBSEDCL SUPPLY OFFICE: MARISHDA C.C.C. Ref. Memo No- 2004815942/QUOT/03 DT. 10-07-2024 Application NO-2004815942 Application type-New connection Consumer Id- 204353932 |  |  | BILL/01697/2024-2025 | C072443922958 | 29/07/2024 | 29/07/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Talda, Block Contai III, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000169/2023-2024 | 1412/W/MMD | 02/06/2023 | 20/05/2025 | SHIVAM ENTERPRISE | 12.63 | 0 | 0 | 90
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | SM/09445 | Augmentation | Construction of Pump House & Boundary Wall and others allied works for 3rd Tube well site under Talda Water Supply Scheme (Augmentation) in Contai III Block within Contai Sub Division under Tamluk Division, PHE Dte. |  |  | ORD/000268/2024-2025 | 2897/TD | 10/09/2024 | 20/10/2024 | BISWA NIRMAN ENTERPRISE. | 11.34 | 0 | 0 | 0
Total | [13 empty] | 654.8 | 501.11 | 76.53