## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 570 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000351/2021-2022 | 1791/TD | 08/02/2022 | 10/03/2022 | SNEHESH SEN | 86.32 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 260 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000354/2021-2022 | 1794/TD | 08/02/2022 | 05/03/2022 | AHINDRA BARIK | 30.12 | 0 | 0 | 70
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 110 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000358/2021-2022 | 1798/TD | 08/02/2022 | 28/02/2022 | S.A. ENTERPRISE | 11.89 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Dismantling of existing OHR (Capacity 55000 Gallons) at Head work Site of Murisai Water Supply Scheme including carriage of old materials to store under Contai Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2021-2022 | 453/TD | 06/08/2021 | 05/09/2021 | M/S B. N. ENTERPRISES | 7.62 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Murisai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2021-2022 | 1610/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000083/2022-2023 | 436-A/TD | 30/05/2022 | 19/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 6.67 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 419 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000352/2021-2022 | 1792/TD | 08/02/2022 | 10/03/2022 | LOKENATH ENTERPRISES | 64.86 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 620 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000350/2021-2022 | 1790/TD | 08/02/2022 | 10/03/2022 | MAITY CONSTRUCTION | 89.06 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 210 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000353/2021-2022 | 1793/TD | 08/02/2022 | 05/03/2022 | MRINAL KANTI PRADHAN | 35.66 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000102/2022-2023 | 478/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 13.41 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Canal crossing of Distribution pipe line for Augmentation of Murisai & its adjoining mouzas W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (N.P.-410-415 & N.P.-181-190) (Length = 2nos x15.00 Mtr.= 30.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000355/2022-2023 | 1282/TD | 12/09/2022 | 03/10/2022 | AHINDRA BARIK | 3.63 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001910/2022-2023 | 811/W/MMD | 24/03/2023 | 20/09/2023 | SUJOY RANJAN BHOWMICK | 13.75 | 0 | 0 | 60
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000093/2022-2023 | 450/TD | 31/05/2022 | 20/06/2022 | RAMASISH ENTERPRISE | 0.31 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Laying Distribution main for Augmentation of Murisai Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. N.P. 4-8, & 8-12 | Assistant Engineer | Junior Engineer | ORD/000393/2022-2023 | 1426/TD | 26/09/2022 | 11/10/2022 | CHANDA AGENCIES | 4.18 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 1345/TD | 23/12/2021 | 23/12/2021 | Resource Division | 20.82 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2021-2022 | 1835/TD | 15/02/2022 | 15/02/2022 | Resource Division | 14.73 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Instalation of display Board at different work site of Augmentation of Murisai-3 nos., Junbani-1 no., Bhagwanpur Zone-I- 1 no.,Bhagwanpur Zone-II- 1 no., Contai Saline Area Zone-III (Phase-A)- 1no. & Contai Saline Area Zone-III (Phase-B)- 1no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000511/2022-2023 | 811 / CSD | 21/10/2022 | 05/11/2022 | MRINAL KANTI PRADHAN | 0.93 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 04/10/2023 | KALPANA BUILDERS | 34.03 | 0 | 0 | 40
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Murisai PWSS at Contai-III Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000152/2024-2025 | 2063/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Instalation of display Board at different work site of Baharchandberia Retrofitting PWSS in Contai - II (Deshopran) Block, Kanaidighi, Paschim Kamarda, Murisai Retrofitting PWSS in Contai - III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001186/2023-2024 | 2334/CSD | 29/12/2023 | 13/01/2024 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Quotation for new service connection at TW-III of Murisai w/s scheme under MMD, PHE Dte. Block-Contai-III, MARISHDA CCC Application n0-2004764433 Con ID-204324522 |  |  | BILL/01234/2024-2025 | BP-2024-25-285 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 180 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-G) | Assistant Engineer | Junior Engineer | ORD/000356/2021-2022 | 1796/TD | 08/02/2022 | 05/10/2025 | JASODA ENTERPRISE | 25.5 | 0 | 0 | 100
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-F) | Assistant Engineer | Junior Engineer | ORD/000355/2021-2022 | 1795/TD | 08/02/2022 | 05/03/2022 | ABHIJIT BERA | 25.4 | 0 | 0 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 75 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART- J) | Assistant Engineer | Junior Engineer | ORD/000359/2021-2022 | 1799/TD | 08/02/2022 | 23/09/2025 | LAKSHMI NARAYAN ENTERPRISE | 9.86 | 0 | 0 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 31/05/2025 | AQUATECH ENGINEERS | 45.52 | 0 | 0 | 98
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Retrofitting to accommodate of 155 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-H) | Assistant Engineer | Junior Engineer | ORD/000357/2021-2022 | 1797/TD | 08/02/2022 | 30/04/2025 | PARIA ENTERPRISE | 22.19 | 0 | 0 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Boundary Wall, Raising Main under JJM with allied work for Augmentation of Murisai Water Supply Scheme in Contai III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2024-2025 | 2898/TD | 10/09/2024 | 26/07/2025 | MRINAL KANTI PRADHAN | 53.73 | 0 | 0 | 40
28 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at Murisai Water supply scheme, Contai - III block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001859/2024-2025 | 782/W/MMD | 24/02/2025 | 23/08/2025 | PADMA ENGINEERING CO. | 14.81 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Strengthening of existing approach road for Replacement of 2nd Tube Well at Murisai Water Supply Scheme within Contai-III Block within Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001280/2024-2025 | 2468/CSD | 25/10/2024 | 01/11/2024 | GANAPATI CONSTRUCTION | 0.97 | 0 | 0 | 100
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | SM/09446 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Augmentation of Murisai W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000347/2022-2023 | 1283/TD | 12/09/2022 | 17/12/2024 | MRINAL KANTI PRADHAN | 3.82 | 0 | 0 | 100
Total | [13 empty] | 651.56 | 0 | 0