## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Golaranji Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2021-2022 | 1615/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.46 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000035/2022-2023 | 134/TD | 19/04/2022 | 10/05/2022 | MENAKA ENTERPRISE | 13.26 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000534/2023-2024 | 1835/TD | 08/08/2023 | 28/08/2023 | RAMESH & SHANTI ENGINEERING WORKS | 4.2 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 1249/TD | 13/12/2021 | 13/12/2021 | Resource Division | 10.87 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2021-2022 | 1273/TD | 12/09/2022 | 12/09/2022 | Resource Division | 18.08 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001914/2022-2023 | 816/W/MMD | 24/03/2023 | 20/09/2023 | MEGA SOLAR ENERGY | 11.79 | 0 | 0 | 85
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Golaranji W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000179/2023-2024 | 1412/CDD | 20/09/2023 | 16/02/2024 | MENAKA ENTERPRISE | 11.26 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of GOLARANIJ W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609771/QUOT/03 DT. 21-02-2024 Application NO- 2004609771 Application type-New connection Reference Id- 204223235 |  |  | BILL/04385/2023-2024 | BP-2023-24-823 | 13/03/2024 | 13/03/2024 | WBSEDCL | 5.82 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Augmentation of ground water based Golaranij Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Potashpur-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000381/2022-2023 | 1370/TD | 23/09/2022 | 26/11/2024 | KISHORE GHOSH | 392.47 | 0 | 0 | 70
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site and 2nd Tube Well site at Golaranij Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2024-2025 | 3318/TD | 22/10/2024 | 21/11/2024 | BADAL CHANDRA GOLE | 4.92 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Laying Distribution Pipe Line With allied Works of Left Out Area for Augmentation Of Golaranij Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/001201/2023-2024 | 738/TD | 28/02/2024 | 29/11/2024 | KISHORE GHOSH | 44.24 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | SM/09447 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer | Junior Engineer | ORD/000714/2022-2023 | 1212/TD | 06/09/2022 | 05/11/2022 | BADAL CHANDRA GOLE | 3.81 | 0 | 0 | 100
Total | [13 empty] | 524.16 | 0 | 0