## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2021-2022 | 1632/TD | 18/01/2022 | 07/02/2022 | HORIZEN | 3.35 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-B) | Assistant Engineer | Junior Engineer | ORD/000607/2021-2022 | 2195/TD | 21/03/2022 | 20/04/2022 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 39.96 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-1) | Assistant Engineer | Junior Engineer | ORD/000095/2022-2023 | 455/TD | 01/06/2022 | 16/06/2022 | GRAND CONSTRUCTION | 4.84 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Land filling with earth of approach road and other side of 3rd T/W site at Bishnubar Water Supply scheme of Tamluk Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000206/2022-2023 | 857/TD | 21/07/2022 | 28/07/2022 | KRISHNENDU SEKHAR DAS | 4.82 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR, NANDAKUMAR BLOCK, DIST : PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000174/2022-2023 | 145/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 5 | 0 | 0 | 90
6 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | ADDITIONAL DEVELOPMENT OF TUBE WELL BY AIR COMPRESSOR WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR SCHEME (TW-III) UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000175/2022-2023 | 360/CMSD-II | 15/07/2022 | 25/07/2022 | PADMA ENGINEERING & CO. | 0.99 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR W/S SCH, NANDAKUMAR BLOCK, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000181/2022-2023 | 144/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 5 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BISHNUBAR W/S SCH (TW-III), TAMLIK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000168/2022-2023 | 431/CDD | 23/05/2022 | 22/06/2022 | PADMA ENGINEERING & CO. | 14.26 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Purbakola Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- G ) | Assistant Engineer | Junior Engineer | ORD/000380/2022-2023 | 1364/TD | 22/09/2022 | 17/10/2022 | SOUMYA ENTERPRISE | 30.53 | 0 | 0 | 30
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC (245 nos.) at Jashdumbur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-B) | Assistant Engineer | Junior Engineer | ORD/000022/2022-2023 | 64/TD | 05/04/2022 | 25/04/2022 | PULAK KUMAR SAMANTA | 28.02 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-C) | Assistant Engineer | Junior Engineer | ORD/000608/2021-2022 | 2196/TD | 21/03/2022 | 10/04/2022 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.98 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jashdumber Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-A) | Assistant Engineer | Junior Engineer | ORD/000609/2021-2022 | 2197/TD | 21/03/2022 | 20/04/2022 | GHOSH ENTERPRISE | 45.02 | 0 | 0 | 85
13 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Melahait & Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- E & I) | Assistant Engineer | Junior Engineer | ORD/000611/2021-2022 | 2199/TD | 21/03/2022 | 25/04/2022 | KRISHNENDU SEKHAR DAS | 74.87 | 0 | 0 | 85
14 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Naikuri Jagannath Chak-I & Khas Panchpukhuria Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- F & J) | Assistant Engineer | Junior Engineer | ORD/000612/2021-2022 | 2200/TD | 21/03/2022 | 25/04/2022 | S.K. MONDAL | 77.9 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-B ) | Assistant Engineer | Junior Engineer | ORD/000614/2021-2022 | 2202/TD | 21/03/2022 | 10/04/2022 | DEBDUT CONSTRUCTION | 20.89 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-2) | Assistant Engineer | Junior Engineer | ORD/000096/2022-2023 | 456/TD | 01/06/2022 | 16/06/2022 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.84 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-3) | Assistant Engineer | Junior Engineer | ORD/000097/2022-2023 | 457/TD | 01/06/2022 | 16/06/2022 | MISHRA ENTERPRISE | 4.84 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-4) | Assistant Engineer | Junior Engineer | ORD/000098/2022-2023 | 458/TD | 01/06/2022 | 16/06/2022 | SANTRA ENTERPRISE. | 4.85 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Bishnubar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 2164/TD | 19/12/2022 | 17/02/2023 | SK. SAHALAM | 5.11 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 3nd tube well site under Bishnubar Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/000547/2022-2023 | 2165/TD | 19/12/2022 | 02/02/2023 | SK. SAHALAM | 5.83 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-A-5) | Assistant Engineer | Junior Engineer | ORD/000606/2021-2022 | 2194/TD | 21/03/2022 | 10/04/2022 | MADAN MOHAN MAITY | 23.06 | 0 | 0 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2021-2022 | 2350/TD | 31/03/2022 | 31/03/2022 | Resource Division | 23.8 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 80/TD | 08/04/2022 | 08/04/2022 | Resource Division | 38.98 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Electric quotation for Bishnubar PWSS Tube Well-III WS Scheme Additional TW (Ref. ID - 203930212) |  |  | BILL/00321/2022-2023 | BP-2022-23-140 | 20/03/2023 | 20/03/2023 | WBSEDCL | 3.23 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Hirapur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-A ) | Assistant Engineer | Junior Engineer | ORD/000613/2021-2022 | 2201/TD | 21/03/2022 | 10/04/2022 | G. S. CONSTRUCTION | 20.87 | 0 | 0 | 100
26 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001547/2022-2023 | 405/W/MMD | 16/03/2023 | 12/09/2023 | DAS ENTERPRISE | 35.46 | 0 | 0 | 61
27 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-C-B(PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 335/TD | 25/04/2023 | 15/05/2023 | PULAK KUMAR SAMANTA | 6.91 | 0 | 0 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Repair & renovation of exisiting pump house and boundary wall at OHR site & 2nd tube well site of Bishnubar PWSS Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 934/TD | 01/06/2023 | 01/07/2023 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 18.32 | 0 | 0 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-A(PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 334/TD | 25/04/2023 | 25/05/2023 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 58.58 | 0 | 0 | 100
30 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Maishali Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-D) | Assistant Engineer | Junior Engineer | ORD/000610/2021-2022 | 2198/TD | 21/03/2022 | 25/04/2022 | BIDHAN MONDAL | 74.98 | 0 | 0 | 100
31 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 1117/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | SM/09448 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Bishnubar & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer | Junior Engineer | ORD/000447/2022-2023 | 1820/TD | 14/11/2022 | 02/04/2025 | HARIPADA PATTANAYAK | 163.96 | 0 | 0 | 100
Total | [13 empty] | 870.23 | 0 | 0