## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. | SM/09800 | Retrofitting | Providing FHTC under JJM in Gobra PWSS within Ramnagar-II Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000299/2021-2022 | 1640/TD | 19/01/2022 | 29/04/2022 | M/S CARE | 122.42 | 92.17 | 75.29 | 80
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. | SM/09800 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000075/2021-2022 | 1749/TD | 08/02/2022 | 08/02/2022 | Resource Division | 14.03 | 0 | 0 | 0
Total | [13 empty] | 136.45 | 92.17 | 67.55