## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. | SM/09801 | Retrofitting | Providing 1450 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000615/2021-2022 | 2203/TD | 21/03/2022 | 25/04/2022 | TAPAS SANTRA | 78.78 | 78.78 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. | SM/09801 | Retrofitting | Providing 1412 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000143/2022-2023 | 719/TD | 29/06/2022 | 08/08/2022 | S.D. CONSTRUCTION | 64.5 | 64.48 | 99.98 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. | SM/09801 | Retrofitting | Instalation of display Board at different work site of Paschimbetiya Retrofitting PWSS in Contai - III Block, Mahammadpur Retrofitting PWSS in Bhagwanpur - I Block, Baharampur, Arjunnagar Retrofitting PWSS in Bhagwanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001187/2023-2024 | 2335/CSD | 29/12/2023 | 13/01/2024 | SAURAV HAZRA | 0.83 | 0.83 | 100 | 100
Total | [13 empty] | 144.1 | 144.09 | 99.99