## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. | SM/09802 | Retrofitting | Retrofitting to accommodate FHTC (2753 nos) and laying of left-out uPVC pipeline due to uncovered area of this zone at different nodal point under JJM in Uttar Dhalhara Zone-II Water Supply Scheme for Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in the District of Purba medinipur. | Assistant Engineer | Junior Engineer | ORD/000298/2021-2022 | 1634/TD | 19/01/2022 | 19/05/2022 | M/S CARE | 135.49 | 0 | 0 | 80
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. | SM/09802 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000073/2021-2022 | 2349/TD | 31/03/2022 | 31/03/2022 | Resource Division | 15.14 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. | SM/09802 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1116/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 150.82 | 0 | 0