## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. | SM/09803 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandibeniya Zone-I PWSS within Moyna Dev. Block .in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000297/2021-2022 | 1633/TD | 19/01/2022 | 19/04/2022 | ARABINDA GHOSH | 105.61 | 60.43 | 57.21 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. | SM/09803 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 1100/TD | 19/03/2024 |  | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 105.8 | 60.43 | 57.11