## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | SM/09804 | Retrofitting | Providing FHTC under JJM in Negua PWSS within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000300/2021-2022 | 1641/TD | 19/01/2022 | 19/05/2022 | M/S CARE | 137.35 | 0 | 0 | 85
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | SM/09804 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000074/2021-2022 | 1748/TD | 08/02/2022 | 08/02/2022 | Resource Division | 15.3 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | SM/09804 | Retrofitting | Retrofitting to accommodate FHTC (Phase-II) of Negua PWSS, Egra - I Block under Digha Sub-Division PHE Dte. of Tamluk Division PHE Dte. in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000307/2023-2024 | 621/TD | 17/05/2023 | 11/06/2023 | SOM CONSTRUCTION | 15.44 | 0 | 0 | 100
Total | [13 empty] | 168.1 | 0 | 0