## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhajachauli Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000177/2021-2022 | 1186/TD | 02/12/2021 | 22/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.34 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000128/2022-2023 | 629/TD | 23/06/2022 | 08/07/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.44 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- D [Bamania Jangal(62) part, Chhota Sijua(64) part, Parihara(65), Panchberya(67) part, Dhandali Bar(139) part, Bhaja Chauli(140)]. | Assistant Engineer |  | ORD/000054/2022-2023 | 322/TD | 11/05/2022 | 25/06/2022 | SRIMANTA KUMAR MAITY | 287.16 | 0 | 0 | 92
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART - A [ Bamania(74), Ugalpur(73), Kajli(70), Katmuri(69), Amratalia(68), Panchberya(67) part]. | Assistant Engineer |  | ORD/000081/2022-2023 | 395/TD | 23/05/2022 | 22/06/2022 | PRANAB KUMAR DAS | 118.3 | 0 | 0 | 65
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- B [Dhandi Bar (139) part]. | Assistant Engineer |  | ORD/000080/2022-2023 | 385/TD | 20/05/2022 | 19/06/2022 | SWARUPANANDA DAS | 120.93 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Construction of TW (300mm x 200mm x Depth 250 Mtr.) for Bhajachauli WS Scheme (TW-II), Contai-III block within Purba Midnapur District by utilising Skilled Departmental crew & machineries of CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000332/2022-2023 | 414/CDD | 20/05/2022 | 19/06/2022 | M/S B.P.TRADING CORPORATION | 14.69 | 0 | 0 | 45
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Resistivity Survey & other works of Bhajachauli WS Scheme (TW-III), Contai-III Block under Purba Midnapur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000335/2022-2023 | 1640/CDD | 20/12/2022 | 19/01/2023 | M/S B.P.TRADING CORPORATION | 12.62 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2021-2022 | 644/TD | 27/06/2022 | 27/06/2022 | Resource Division | 23.79 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 101/TD | 11/04/2022 | 11/04/2022 | Resource Division | 21.75 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Electric Quotation for BHAJACHAULI Water Supply Scheme T/W-III, (Ref. ID-204050249) |  |  | BILL/01683/2023-2024 | BP-2023-24-167 | 04/08/2023 | 04/08/2023 | WBSEDCL | 1.74 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Rising main and other allied works of 3rd Tube Well for Augmentation of BHAJACHAULI W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 930/TD | 01/06/2023 | 26/06/2023 | DEBABRATA DAS | 4.31 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for BHAJACHAULI PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-160.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 931/TD | 01/06/2023 | 11/07/2023 | DEBABRATA DAS | 22.69 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Construction of 3.60 mtr. x 3.00 mtr. size switch Room cum chlorine room without sanitary & water supply arrangements including plinth protection at 3rd TW site for Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 929/TD | 01/06/2023 | 26/06/2023 | DEBABRATA DAS | 3.53 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Laying Distribution Pipe Line & Accommodate FHTC (146 nos) under JJM with allied work for Left out Areas of BHAJACHAULI- PWSS in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000576/2023-2024 | 2198/TD | 01/09/2023 | 01/10/2023 | SUBHENDU HAZRA | 19.54 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Repairing of Switch Room cum Chlorin Room at 2nd TW site at Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer |  | ORD/000726/2023-2024 | 2971/TD | 28/11/2023 | 12/01/2024 | SUBHENDU HAZRA | 3.53 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Augmentation of Bhajachauli Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000843/2023-2024 | 2128/CSD | 24/11/2023 | 14/12/2023 | SAURAV HAZRA | 1.22 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 11/01/2025 | B. K. ENTERPRISE | 34.31 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Washout pipeline, Repairing of OHR, Pump House no 1 under JJM with allied work of Bhajachauli PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000291/2024-2025 | 3056/TD | 19/09/2024 | 24/03/2025 | SUBHENDU HAZRA | 31.12 | 0 | 0 | 50
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Augmentation Of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART-C [Bamania Jangal (62) part, Sijua (63), Chhota Sijua (64) part.] | Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 433/TD | 27/05/2022 | 01/02/2025 | SNEHESH SEN | 113.07 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | SM/09912 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001905/2022-2023 | 806/W/MMD | 24/03/2023 | 10/09/2024 | DEBKUMAR BASU | 13.58 | 0 | 0 | 100
Total | [13 empty] | 864.66 | 0 | 0