## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCH, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000220/2022-2023 | 146/CMSD-I | 30/05/2022 | 02/06/2022 | PADMA ENGINEERING & CO. | 0.35 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bargodagodar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000190/2021-2022 | 1199/TD | 02/12/2021 | 22/12/2021 | RADIANT | 8.93 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BATGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000016/2022-2023 | 434/CDD | 23/05/2022 | 22/06/2022 | PADMA ENGINEERING & CO. | 13.86 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Electric Quotation Bill under Nandakumar CCC at Bargodagodar PWSS under Tamluk Division, PHE Dte. within Purba Medinipur District. |  |  | BILL/00135/2022-2023 | BP-2022-23-511 | 22/12/2022 | 22/12/2022 | WBSEDCL | 2.57 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer |  | ORD/000436/2022-2023 | 1208/TSD | 15/09/2022 | 15/10/2022 | S.K. MONDAL | 2.66 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Jungle cutting at Head work site in connection repair & renovation of Boundary of Boargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 1659/TSD | 11/12/2023 | 18/12/2023 | PURNA CHANDRA BARH | 0.24 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 1445/TD | 27/09/2022 | 27/10/2022 | TARUN KHATUA | 4.85 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Land filling work at 3rd tube well site of Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000738/2022-2023 | 74/TSD | 11/01/2023 | 26/01/2023 | TARUN KHATUA | 0.95 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000509/2022-2023 | 146/CMSD-I | 30/05/2022 | 02/06/2022 | PADMA ENGINEERING & CO. | 0.31 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2021-2022 | 645/TD | 27/06/2022 | 27/06/2022 | Resource Division | 37.93 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 97/TD | 11/04/2022 | 11/04/2022 | Resource Division | 41.98 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Restoration estimate with Bituminous Surfacing ,sand filling and jhama -metal consolidation of Tamluk -Moyna road from 10 KM to 11.30 KM due to cutting of Hard shoulder for laying water pipe lines by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 |  |  | BILL/00233/2023-2024 | BP-2023-24-118 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.09 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Payment to WBSEDCL for Quotation Money for Bargodagodar PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00612/2022-2023 | BP-2022-23-820 | 24/03/2023 | 24/03/2023 | WBSEDCL | 8.99 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Restoration estimate with sand filling and jhama -metal consolidation of Thekuabazar- Pursaghat Road due to lcutting of hard shoulder for laying water pipelines by PHE Dte. within Tamluk Highway Sub-Division under Tamluk Highway Division in the district of Purba Medinipur during the year 2022-23 |  |  | BILL/00231/2023-2024 | BP-2023-24-116 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.12 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr.and repairing & renovation of 450 cum OHR and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bargodagodar Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000187/2022-2023 | 812/TD | 12/07/2022 | 08/01/2023 | CONCORD ENGINEERING | 774.2 | 0 | 0 | 76
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Laying left out portion of 90 mm dia UPVC pipe lines with allied works to facilitate the FHTC connection for Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000586/2023-2024 | 2205/TD | 01/09/2023 | 24/12/2024 | SK. NUR ISLAM | 27.66 | 0 | 0 | 60
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at Head work site under Bargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2023-2024 | 2214/TD | 01/09/2023 | 11/10/2023 | BARH CONSTRUCTION | 6.22 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001469/2022-2023 | 207/W/MMD | 10/02/2023 | 09/08/2023 | SOUMEN ELECTRIC | 40.4 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Sinking of 300 mm x 200 mm dia x 240 mtr. deep tube well by direct rotary rig method for Replacement of head work site Tube well of Bargodagudar Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001240/2023-2024 | 1084/TD | 16/03/2024 | 05/04/2024 | MANNA COMPUTER | 17.87 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bargodagodar PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000828/2022-2023 | 3167/TD | 10/03/2023 | 01/12/2024 | BARH CONSTRUCTION | 33.83 | 0 | 0 | 80
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 02/01/2025 | MISHRA ENTERPRISE | 44.78 | 0 | 0 | 100
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 1102/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Functional Household Tap Connection (FHTC-796 nos) of Bargodagodar water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2023-2024 | 2206/TD | 01/09/2023 | 24/12/2024 | SK. NUR ISLAM | 27.14 | 0 | 0 | 60
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Dismentling of existing damaged staff quarter and godown of Bargodagodar and its adjoining mouza Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000604/2024-2025 | 337/TSD | 17/02/2025 | 19/03/2025 | SK. INJAMUL ALI | 2.81 | 0 | 0 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09913 | Augmentation | Laying of 150/200 mm dia DI(K-9) for Rising main line from T/W-1 to Existing delivery main including CI/DI specials supply under Bargodagodar PWSS with in Nandakumar Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000429/2025-2026 | 2828/TSD | 08/09/2025 | 08/10/2025 | BARH CONSTRUCTION | 0.89 | 0 | 0 | 100
Total | [13 empty] | 1121.67 | 0 | 0