## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kulbari Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000186/2021-2022 | 1195/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 10.5 | 10.5 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Supply of DI Specials for Proposed Rejuvenation & Retrofitting of Laying Distribution System of KULBARI PWSS under tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2022-2023 | 1229/TD | 07/09/2022 | 22/09/2022 | BAGLAMUKHI SECURITY SERVICE | 4.81 | 4.81 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 54/TD | 05/04/2022 | 04/07/2022 | HARIPADA PATTANAYAK | 273.36 | 272.86 | 99.82 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Sinking of 1 (One) no Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at OHR Site of Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000236/2022-2023 | 977/TD | 03/08/2022 | 18/08/2022 | PRANTIK DRILLING AGENCY | 17.17 | 16.45 | 95.79 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 60/TD | 05/04/2022 | 04/06/2022 | TAPAS SANTRA | 154.84 | 129.6 | 83.7 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- C) | Assistant Engineer | Junior Engineer | ORD/000039/2022-2023 | 138/TD | 19/04/2022 | 18/06/2022 | BIDHAN MONDAL | 184.94 | 90.33 | 48.84 | 55
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 642/TD | 27/06/2022 |  | Resource Division | 27.12 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 418/TD | 25/05/2022 |  | Resource Division | 4.92 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 96/TD | 11/04/2022 |  | Resource Division | 43.14 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 55/TD | 05/04/2022 | 04/07/2022 | MAA ANANDAMAYEE | 251.38 | 223.45 | 88.89 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Sal-bullah /Eucalyptus bullah piling of pipe line and its allied works to accommodate FHTC at Kulbari water supply scheme in Chandipur Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur(PART-A) | Assistant Engineer | Junior Engineer | ORD/000358/2023-2024 | 926/TD | 01/06/2023 | 21/06/2023 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 99.99 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 1097/TD | 19/03/2024 |  | Resource Division | 0.19 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 |  |  | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 |  | WBSEDCL | 10.34 | 0 | 0 | null
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 |  |  | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 |  | WBSEDCL | 11.01 | 0 | 0 | null
15 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Kulbari Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000132/2023-2024 | 268/TD | 20/04/2023 | 04/06/2023 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.15 | 0 | 0 | 0
Total | [13 empty] | 1032.74 | 760.87 | 73.67