## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kulbari Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000186/2021-2022 | 1195/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 10.5 | 10.5 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 60/TD | 05/04/2022 | 04/06/2022 | TAPAS SANTRA | 154.84 | 129.6 | 83.7 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 54/TD | 05/04/2022 | 04/07/2022 | HARIPADA PATTANAYAK | 273.36 | 272.86 | 99.82 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Sinking of 1 (One) no Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at OHR Site of Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000236/2022-2023 | 977/TD | 03/08/2022 | 18/08/2022 | PRANTIK DRILLING AGENCY | 17.17 | 16.45 | 95.79 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Supply of DI Specials for Proposed Rejuvenation & Retrofitting of Laying Distribution System of KULBARI PWSS under tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2022-2023 | 1229/TD | 07/09/2022 | 22/09/2022 | BAGLAMUKHI SECURITY SERVICE | 4.81 | 4.81 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 642/TD | 27/06/2022 | 27/06/2022 | Resource Division | 27.12 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 418/TD | 25/05/2022 | 25/05/2022 | Resource Division | 4.92 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 96/TD | 11/04/2022 | 11/04/2022 | Resource Division | 43.14 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 55/TD | 05/04/2022 | 04/07/2022 | MAA ANANDAMAYEE | 251.38 | 251.38 | 100 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Sal-bullah /Eucalyptus bullah piling of pipe line and its allied works to accommodate FHTC at Kulbari water supply scheme in Chandipur Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur(PART-A) | Assistant Engineer | Junior Engineer | ORD/000358/2023-2024 | 926/TD | 01/06/2023 | 21/06/2023 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 99.99 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 1097/TD | 19/03/2024 | 19/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 |  |  | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 23/02/2024 | WBSEDCL | 11.01 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 |  |  | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 23/02/2024 | WBSEDCL | 10.34 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Kulbari Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000132/2023-2024 | 268/TD | 20/04/2023 | 22/08/2025 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.15 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Repairing & renovation of Pump House at OHR site & 2nd Pump house and boundary wall at 2nd TW site and new construction of boundary wall at OHR site and renovation works of OHR for Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 925/TD | 01/06/2023 | 27/12/2024 | HARIPADA PATTANAYAK | 44.56 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09914 | Augmentation | Construction of 2(Two) nos M.S. Structure over irrigation canal to support 90 mm dia. UPVC distribution pipe under Kulbari Water Supply Scheme at NP 71-893 & NP 72-475 under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte.(Each length=15.00 Mtr ) | Assistant Engineer | Junior Engineer | ORD/000432/2024-2025 | 3553/TD | 19/11/2024 | 13/12/2024 | MAA ANANDAMAYEE | 4.46 | 0 | 0 | 100
Total | [13 empty] | 896.82 | 698.47 | 77.88