## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2021-2022 | 1694/TD | 31/01/2022 | 20/02/2022 | CONCORD ENGINEERING | 4.2 | 4.02 | 95.65 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2021-2022 | 1695/TD | 31/01/2022 | 20/02/2022 | CONCORD ENGINEERING | 4.47 | 4.47 | 100 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-II, TW-II, BHAGAWANPUR -II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000255/2022-2023 | 375/CDD | 13/05/2022 | 12/06/2022 | MENAKA ENTERPRISE | 14.69 | 5.66 | 38.54 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-I, TW-I, BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000254/2022-2023 | 430/CDD | 23/05/2022 | 22/06/2022 | MENAKA ENTERPRISE | 14.69 | 5.65 | 38.43 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, BLOCK BHAGAWANPUR-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000250/2022-2023 | 151/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 4.99 | 4.97 | 99.45 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI W/S SCH (TW-II), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000264/2022-2023 | 1349/CDD | 24/11/2022 | 24/12/2022 | PADMA ENGINEERING & CO. | 19.77 | 16.95 | 85.73 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SUADIGHI PWSS, ZONE-I, TW-I, BLOCK - KHEJURI, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000252/2022-2023 | 152/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 4.99 | 4.97 | 99.45 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, ZONE-II, TW-II, BLOCK-KHEJURI, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000253/2022-2023 | 150/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 4.91 | 4.88 | 99.44 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL INSUADIGHI PWSS, ZONE-II, TW-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000251/2022-2023 | 149/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 4.98 | 4.95 | 99.45 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000100/2022-2023 | 476/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 1st Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1228) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000105/2022-2023 | 481/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 2266/TD | 30/12/2022 | 19/01/2023 | MAKALI ENGINEERING CORPORATION | 1.01 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements at 1st TW (Head Work) site at Suadighi Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer | Junior Engineer | ORD/000425/2022-2023 | 1594/TD | 18/10/2022 | 17/12/2022 | M/S. NEW DINDA ENTERPRISE | 6.94 | 6.32 | 91.02 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000574/2022-2023 | 2261/TD | 30/12/2022 | 19/01/2023 | SWASTIK ENTERPRISE | 6.18 | 6.18 | 100 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-I Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 1435/TD | 27/09/2022 | 17/10/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.34 | 7.34 | 100 | 100
16 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260mtrs. depth) by utilising Departmental Machineries for Suadighi WS Scheme (TW-I) Bhagwanpur-II block under Purba midnapore Dist., CDD,PHE Dte. | Driller In Charge | Junior Engineer | ORD/000299/2022-2023 | 1348/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 19.77 | 17.03 | 86.1 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for 3rd Tube well J.L no. -257,Plot no. -240, Mouza -Kasba under Suadighi Zone-I Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 2097/TD | 13/12/2022 | 11/02/2023 | SMMD | 3.4 | 3.16 | 92.84 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 2nd Tube well site J.L no. -262,Plot no. -272, Mouza -Keshaidighi under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000531/2022-2023 | 2098/TD | 13/12/2022 | 11/02/2023 | SMMD | 3.46 | 3.45 | 99.67 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2021-2022 | 649/TD | 27/06/2022 | 27/06/2022 | Resource Division | 21.19 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 95/TD | 11/04/2022 | 11/04/2022 | Resource Division | 58.97 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2021-2022 | 648/TD | 27/06/2022 | 27/06/2022 | Resource Division | 21.41 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Electric Quotation for SUADIGHI Water Supply Scheme T/W-II, Zone-II (Ref. ID-204020001) |  |  | BILL/01825/2023-2024 | BP-2023-24-201 | 24/08/2023 | 24/08/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme Zone-I, TW-III (Ref. Id-203950247) |  |  | BILL/00107/2023-2024 | BP-2023-24-38 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) |  |  | BILL/00102/2023-2024 | BP-2023-24-26 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Restoration of Hard shoulder at Heria-Mugberia and Itaberia-Mugberia Road after laying pipe line by PHE under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 |  |  | BILL/00236/2023-2024 | BP-2023-24-121 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.16 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001467/2022-2023 | 205/W/MMD | 10/02/2023 | 09/08/2023 | BALAJI CONSTRUCTION | 40.78 | 34.24 | 83.94 | 70
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 04/10/2023 | PADMA ENGINEERING CO. | 38.21 | 0 | 0 | 44
28 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001470/2022-2023 | 208/W/MMD | 10/02/2023 | 09/08/2023 | NIRMAN | 27.16 | 25.53 | 93.98 | 75
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Left out Portion of uncovered area with upvc pipes with allied works of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/001225/2023-2024 | 1038/TD | 15/03/2024 | 28/02/2025 | S.D. CONSTRUCTION | 43.4 | 9.08 | 20.93 | 50
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Rising main, Boundary Wall under JJM with allied work at 3rd TW site for Augmentation of SUADIGHI ZONE-I PWSS in Bhagwanpur-II Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000646/2023-2024 | 2598/TD | 10/10/2023 | 19/11/2023 | A. R. CONSTRUCTION | 14.76 | 9.66 | 65.48 | 100
31 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Suadighi W/S Scheme( TW-III) , Bhagawanpur-II Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000147/2023-2024 | 1453/CDD | 30/11/2023 | 29/03/2024 | MENAKA ENTERPRISE | 18.35 | 15.83 | 86.28 | 100
32 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) |  |  | BILL/00111/2023-2024 |  | 28/04/2023 | 28/04/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
33 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | quotation for new power connection at newly sunk t/w at Madhakhali w/s scheme zone -II , T/W - I |  |  | BILL/00270/2023-2024 |  | 23/05/2023 | 23/05/2023 | WBSEDCL | 0.59 | 0 | 0 | 0
34 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Suadighi W/S scheme TW no.-III, Z-I Ref.-860286948 ID-100000094898 |  |  | BILL/03153/2023-2024 | BP-2023-24-449 | 19/12/2023 | 19/12/2023 | WBSEDCL | 3.64 | 0 | 0 | 0
35 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of SUADIGHI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004740459/QUOT/03 DT. 17-05-2024 Application NO- 2004740459 Application type-New connection Consumer Id- 204309985 |  |  | BILL/01130/2024-2025 | BP-2024-25-246 | 06/06/2024 | 06/06/2024 | WBSEDCL | 7.11 | 0 | 0 | 0
36 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000190/2022-2023 | 814/TD | 12/07/2022 | 28/08/2025 | JAYANTA KUMAR MONDAL | 584.44 | 426.54 | 72.98 | 80
37 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000189/2022-2023 | 815/TD | 12/07/2022 | 28/12/2025 | JAYANTA KUMAR MONDAL | 565.34 | 490.77 | 86.81 | 88
38 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 3rd Tube well site J.L no. -253,Plot no. -1498, Mouza -Bhupatinagar under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000532/2022-2023 | 2099/TD | 13/12/2022 | 24/11/2024 | SMMD | 3.4 | 0 | 0 | 0
39 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Laying Rising Main, Earth work filling & Construction of Boundary wall at OHR (1st), 2nd & 3rd Tube Well Site Mouza- Bhupatinagar & Keshaidighi, J.L No.-253,262 for Augmentation of Suadighi Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000490/2023-2024 | 1599/TD | 24/07/2023 | 13/02/2025 | JAYANTA KUMAR MONDAL | 45.98 | 0 | 0 | 0
40 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Left-out portion of uncovered area of different dia. uPVC pipeline within Suadighi Zone-II Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2024-2025 | 1910/TD | 07/06/2024 | 01/03/2025 | SETH ENTERPRISE | 48.35 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Suadighi piped water supply scheme. | SM/09919 | Augmentation | Boundary Wall Repair at 2nd TW Site and Construction of Toilet at 1st TW site of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer |  | ORD/000341/2024-2025 | 3339/TD | 22/10/2024 | 01/12/2024 | BIBEKANANDA DAS | 7.03 | 0 | 0 | 0
Total | [13 empty] | 1719.12 | 1111.62 | 64.66