## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000452/2021-2022 | 1696/TD | 31/01/2022 | 20/02/2022 | CONCORD ENGINEERING | 4.15 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000453/2021-2022 | 1697/TD | 31/01/2022 | 20/02/2022 | CONCORD ENGINEERING | 3.42 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCHEME (REPLACEMENT TW, ZONE-I, TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000029/2022-2023 | 385/CDD | 18/05/2022 | 17/06/2022 | MENAKA ENTERPRISE | 14.69 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCH (REPLACEMENT TW, ZONE-I, TW-II) BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHD DTE. |  |  | ORD/000047/2022-2023 | 432/CDD | 23/05/2022 | 22/06/2022 | MENAKA ENTERPRISE | 14.69 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADHAKHALI PWSS, TW-II, BLOCK-BHAGAWANPUR-II UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000135/2022-2023 | 269/CMSD-II (D) | 31/05/2022 | 10/06/2022 | MENAKA ENTERPRISE | 0.69 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL UNDER CDD, PHE DTE. |  |  | ORD/000126/2022-2023 | 171/CMSD-I (D) | 06/06/2022 | 13/06/2022 | MENAKA ENTERPRISE | 0.49 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000099/2022-2023 | 475/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I of Zone - I Madhakhali water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001013/2022-2023 | 1862/W/MMD | 22/09/2022 | 20/01/2023 | M/S B.M. ELECTRICAL | 11.68 | 0 | 0 | 70
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1st Tubewell of Head Works site (Mouza - Baghadanri, JL No. - 246, Plot No. - 1029) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 136/TD | 19/04/2022 | 10/05/2022 | MENAKA ENTERPRISE | 13.26 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000489/2022-2023 | 1929/TD | 28/11/2022 | 18/12/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.64 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000490/2022-2023 | 1930/TD | 28/11/2022 | 18/12/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.42 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Land Development at Head Work Site of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Part-A) | Assistant Engineer | Junior Engineer | ORD/000399/2023-2024 | 1097/CSD | 07/06/2023 | 22/06/2023 | BIBEKANANDA DAS | 0.97 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 20mm x 250 mtrs depth) by utilising Departmental Machineries for Madhakhali W/S scheme(TW-III) ,Bhagawanpur- II Block under Purba Midnapore Dristict ,CDD,P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000447/2022-2023 | 1232/CDD | 16/11/2022 | 16/12/2022 | MENAKA ENTERPRISE | 19.35 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2021-2022 | 646/TD | 27/06/2022 | 27/06/2022 | Resource Division | 23.67 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2021-2022 | 647/TD | 27/06/2022 | 27/06/2022 | Resource Division | 20.06 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 99/TD | 11/04/2022 | 11/04/2022 | Resource Division | 53.75 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Electric Quotiaton for Madhakhali Water Supply Scheme Zone-II, T/W-I (Ref. ID-204004293) |  |  | BILL/00381/2023-2024 | BP-2023-24-67 | 06/06/2023 | 06/06/2023 | WBSEDCL | 0.59 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Electric Quotation for MADHAKHALI Water Supply Scheme Z-II, T/W-II (Ref. ID-204049127 ) |  |  | BILL/01632/2023-2024 | BP-2023-24-138 | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.39 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Laying of distribution pipe line to accommodate 1900 nos FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A). | Assistant Engineer | Junior Engineer | ORD/000199/2022-2023 | 817/TD | 12/07/2022 | 08/01/2023 | DAS ENTERPRISE | 477.83 | 0 | 0 | 98
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Laying of distribution pipe line to accommodate 1933 nos FHTC with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000079/2022-2023 | 384/TD | 20/05/2022 | 04/07/2022 | DAS ENTERPRISE | 223.21 | 0 | 0 | 98
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001515/2022-2023 | 359/W/MMD | 09/03/2023 | 05/09/2023 | AHALYA ENGINEERING WORKS | 27.16 | 0 | 0 | 20
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 04/10/2023 | PADMA ENGINEERING CO. | 38.21 | 0 | 0 | 44
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Laying of Left-Out portion uPVC pipes with allied works due to uncovered area under of Madhakhali Zone-II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part - A + B + C + D). | Assistant Engineer | Junior Engineer | ORD/001209/2023-2024 | 965/TD | 12/03/2024 | 21/04/2024 | DAS ENTERPRISE | 100.28 | 0 | 0 | 90
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | M.S. Structures and allied works under Madhakhali Zone-I Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/001178/2023-2024 | 722/TD | 28/02/2024 | 29/03/2024 | DAS ENTERPRISE | 17.77 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Baghadanri, JL No. - 246, Plot No. -495/1489) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000036/2022-2023 | 135/TD | 19/04/2022 | 10/05/2022 | MENAKA ENTERPRISE | 13.26 | 0 | 0 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-I W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000404/2022-2023 | 1179/TD | 05/09/2022 | 04/11/2022 | M/S. NEW DINDA ENTERPRISE | 3.53 | 0 | 0 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 1177/TD | 05/09/2022 | 04/11/2022 | PARTHA CONSTRUCTION | 3.81 | 0 | 0 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-I PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Laying Rising main and other allied works Augmentation of Madhakhali Zone-I W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000893/2022-2023 | 3393/TD | 24/03/2023 | 06/09/2024 | SWARUPANANDA DAS | 19.31 | 0 | 0 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Land Development at HeadWorks site of Madhakhali Zone-II W/S Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001293/2023-2024 | 375/CSD | 23/02/2024 | 09/03/2024 | PARTHA CONSTRUCTION | 0.97 | 0 | 0 | 100
30 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Madhakhali W/S scheme PH-III, Zone-I Application no-2004427213 Ref.-204078346 |  |  | BILL/03236/2023-2024 | BP-2023-24-501 | 05/01/2024 | 05/01/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
31 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of MADHAKHALI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004826940/QUOT/03 DT. 25-07-2024 Application NO- 2004826940 Application type-New connection Consumer Id- 204360840 |  |  | BILL/01887/2024-2025 | BP-2024-25-551 | 08/08/2024 | 08/08/2024 | WBSEDCL | 3.35 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000243/2022-2023 | 1003/TD | 08/08/2022 | 04/02/2023 | DAS ENTERPRISE | 512.49 | 0 | 0 | 90
33 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | i) Laying Rising main and other allied works Augmentation of Madhakhali Zone-II W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iv) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 878/TD | 01/06/2023 | 28/10/2025 | M/S. PRADIP PRADHAN | 49.33 | 0 | 0 | 70
34 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site at Madhakhali Zone-I Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 1092/TD | 25/08/2022 | 24/10/2022 | SWARUPANANDA DAS | 6.34 | 0 | 0 | 100
35 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW (Head Work) site at Madhakhali Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Low Land) | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 1093/TD | 25/08/2022 | 24/10/2022 | BIBEKANANDA DAS | 6.63 | 0 | 0 | 100
36 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer | Junior Engineer | ORD/000402/2022-2023 | 1178/TD | 05/09/2022 | 23/12/2024 | SWARUPANANDA DAS | 3.81 | 0 | 0 | 100
37 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Madhakhali piped water supply scheme. | SM/09920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001516/2022-2023 | 360/W/MMD | 09/03/2023 | 31/07/2025 | SOUMEN ELECTRIC | 40.74 | 0 | 0 | 75
Total | [13 empty] | 1768.09 | 0 | 0