## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000170/2021-2022 | 1179/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 9.54 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  | Junior Engineer | ORD/000031/2022-2023 | 130/TD | 19/04/2022 | 10/05/2022 | SIMPLEX DRILLING COMPANY | 19.03 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  | Junior Engineer | ORD/000032/2022-2023 | 131/TD | 19/04/2022 | 10/05/2022 | SIMPLEX DRILLING COMPANY | 19.03 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000180/2022-2023 | 2003987573/QUOT/03 | 11/07/2022 | 11/07/2023 | WBSEDCL | 0.7 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte |  |  | VCH/001780/2022-2023 | BP-2022-23-26 | 10/08/2022 | 10/08/2022 | WBSEDCL | 0.7 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Electric quotation MAHISHADAL CCC at Gopalpur, Manashathan Water supply scheme under MMD PHE Dte |  |  | VCH/002769/2022-2023 | BP-2022-23-61 | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.5 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000302/2022-2023 | 1152/TD | 31/08/2022 | 15/10/2022 | RAI CONSTRUCTION | 4.12 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with Water Supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur |  | Junior Engineer | ORD/000316/2022-2023 | 1227/TD | 07/09/2022 | 06/11/2022 | M/S SOURAV MAHAPATRA | 4.84 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No IV under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001142/2022-2023 | 2123/W/MMD | 28/11/2022 | 28/03/2023 | MANORANJAN DEY | 13.12 | 0 | 0 | 75
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | New Construction of boundary wall at 3rd T/W site (50mt) of Gopalpur Water Supply Scheme under Haldia Sub-Division PHE Dte.. |  | Junior Engineer | ORD/000641/2022-2023 | 2352/TD | 10/01/2023 | 24/02/2023 | M/S SOURAV MAHAPATRA | 6.48 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000644/2022-2023 | 2353/TD | 10/01/2023 | 11/03/2023 | GUCHHAIT ENTERPRISE | 4.63 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 1674/TD | 03/11/2022 | 03/11/2022 | Resource Division | 96.09 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 1373/TD | 23/09/2022 | 23/09/2022 | Resource Division | 37.63 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) and construction of new Boundary wall at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001216/2023-2024 | 980/TD | 13/03/2024 | 12/06/2025 | RAJ KUMAR SINGHA | 128.78 | 0 | 0 | 30
15 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2023 to 31/12/2023. (12 Months) | Assistant Engineer |  | ORD/000563/2022-2023 | 815/HSD | 29/12/2022 | 29/12/2023 | SANTANU PATTANAYAK | 1.5 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No III under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001141/2022-2023 | 2122/W/MMD | 28/11/2022 | 28/03/2023 | SOUMEN ELECTRIC | 13.1 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Boundery wall including land development at 4th tube well site of Gopalpur Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000462/2023-2024 | 1492/TD | 17/07/2023 | 16/08/2023 | GUCHHAIT ENTERPRISE | 8.53 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Cannel crossing, Road crossing and Drum sheet pilling of Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000449/2023-2024 | 1470/TD | 13/07/2023 | 22/08/2023 | RAJ KUMAR SINGHA | 71.38 | 0 | 0 | 60
19 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | SM/10030 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 900 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000201/2022-2023 | 832/TD | 15/07/2022 | 01/07/2025 | RAJ KUMAR SINGHA | 838.35 | 0 | 0 | 62
Total | [13 empty] | 1278.04 | 0 | 0