## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2021-2022 | 1177/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 7.73 | 7.73 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well at OHR Site of Mahisda Zone-I Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 479/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.39 | 15.97 | 91.79 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2021-2022 | 640/TD | 27/06/2022 | 27/06/2022 | Resource Division | 31.83 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 651/TD | 27/06/2022 | 27/06/2022 | Resource Division | 22.79 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Additional Electric Quotation for MAHISDA Water Supply Scheme, T/W- III, Zone- I (Ref. ID-860281848) |  |  | BILL/02908/2023-2024 | BP-2023-24-320 | 01/11/2023 | 01/11/2023 | WBSEDCL | 4.8 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Electric Quotiaton for Mahisda Water Supply Scheme zone-I, T/W-III (Ref. ID-204015583) |  |  | BILL/01669/2023-2024 | BP-2023-24-173 | 04/08/2023 | 04/08/2023 | WBSEDCL | 8.05 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Mohisda Zone-I PWSS |  |  | BILL/01193/2023-2024 | BP-2023-24-566 | 07/11/2023 | 07/11/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.6 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Mahisda Zone-I Water Supply Scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000249/2023-2024 | 513/TD | 11/05/2023 | 10/06/2023 | TAPAS SANTRA | 58.58 | 55.7 | 95.08 | 90
9 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Interconnection with laying of 150 mm dia DI(K-9) & 200 mm dia DI (K-9) rising main from 1st.,2nd. & 3rd. T/W to OHR at Mohisda Zone-I PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 1494/TD | 17/07/2023 | 06/08/2023 | TAPAS SANTRA | 3.84 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2022 to 14/07/2023 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Assistant Engineer, Headquaters |  | ORD/000703/2022-2023 | 821/TD | 15/07/2022 | 15/07/2023 | THREE MAA ENTERPRISE | 1.24 | 4.76 | 383.96 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Repairing & renovation of construction of switch room cum Chlorine room at 1 st.T.W. Site and Construction of switch room cum Chlorine room with water supply & sanitary arrangement at 3 rd. Tube Well Site and Repairing & renovation of existing Boundary Wall at 1 st.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer | Junior Engineer | ORD/000852/2022-2023 | 3206/TD | 14/03/2023 | 13/04/2023 | TAPAS SANTRA | 17.08 | 16.83 | 98.52 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site and Construction of Pump House at 3 rd Tube Well site &New construction of Boundary Wall at 3 rd.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer | Junior Engineer | ORD/000853/2022-2023 | 3207/TD | 14/03/2023 | 13/04/2023 | TAPAS SANTRA | 19.48 | 19.29 | 99.05 | 100
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001931/2022-2023 | 850/W/MMD | 24/03/2023 | 20/09/2023 | MUKHERJEE ART CENTRE | 12.37 | 11.32 | 91.5 | 65
14 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 1113/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Net-Metering Solar Power Plant quotation at Mohisda water supply scheme Zone-I, Tube Well-I Matangini CCC Block-Sahid Matangini Application No.-2004795833 Consumer ID.-222091158 Quotation Date.-26/06/2024 |  |  | BILL/01450/2024-2025 | BP-2024-25-446 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Quotation Bill for Net Billing Mahisda Zone-I,T/W-I Matangini CCC Application No=2004795833 Consumer ID=222091158 |  |  | BILL/02430/2024-2025 | BP-2024-25-773 | 28/10/2024 | 28/10/2024 | WBSEDCL | 0.22 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 700 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000075/2022-2023 | 337/TD | 12/05/2022 | 31/03/2025 | TAPAS SANTRA | 417.56 | 274.52 | 65.74 | 70
18 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Laying of distribution pipe line to accommodate FHTC for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-B) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000067/2022-2023 | 338/TD | 12/05/2022 | 26/04/2025 | TAPAS SANTRA | 331.77 | 315.84 | 95.2 | 95
19 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | SM/10031 | Augmentation | Construction of Retaining wall and approach concrete road at OHR site at Mohisda Zone-I Water Supply scheme of Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000617/2023-2024 | 2282/TD | 07/09/2023 | 31/10/2024 | TAPAS SANTRA | 27.97 | 0 | 0 | 100
Total | [13 empty] | 984.51 | 721.95 | 73.33