## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baghaput Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000314/2021-2022 | 1548/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.62 | 3.26 | 90.16 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Repair and Renovation of 136 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Baghaput Water Supply Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000733/2022-2023 | 2563/TD | 24/01/2023 | 25/03/2023 | NARAYAN CHANDRA DAS | 11.29 | 7.54 | 66.83 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Baghaput Water Supply Scheme in Contai II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000488/2022-2023 | 1928/TD | 28/11/2022 | 18/12/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.35 | 5.35 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 406/TD | 25/05/2022 | 25/05/2022 | Resource Division | 22.79 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 1269/TD | 12/09/2022 | 12/09/2022 | Resource Division | 11.27 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000066/2023-2024 | 1225/W/MMD | 25/04/2023 | 22/10/2023 | M/S. JIT ENTERPRISE | 26.93 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Repairing Of Boundary Wall of Head Work site and Pump House No - II under Augmentation of Baghaput Water Supply Scheme within Deshpran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000424/2023-2024 | 493/TD | 10/05/2023 | 09/06/2023 | SUBHENDU HAZRA | 3.73 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Repair And renovation Of Pump House No. I & II under Augmentation of Baghaput Water Supply Scheme within Deshpran( Contai- II) Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000958/2022-2023 | 421/CSD | 17/03/2023 | 16/04/2023 | THE GODFATHER TRADING COMPANY | 2.24 | 1.23 | 55.03 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | SM/10072 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Baghaput Water Supply Scheme within Deshpran ( Contai- II)Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000188/2022-2023 | 813/TD | 12/07/2022 | 01/09/2025 | G. B. CONSTRUCTION & CO. | 378.59 | 267.34 | 70.61 | 70
Total | [13 empty] | 465.8 | 284.72 | 61.12