## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000367/2021-2022 | 1631/TD | 18/01/2022 | 07/02/2022 | HORIZEN | 5.27 | 5.25 | 99.51 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000657/2022-2023 | 2342/TD | 10/01/2023 | 19/02/2023 | TARUN KHATUA | 5.11 | 5.1 | 99.84 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 04/10/2022 | AQUATECH ENGINEERS | 70.49 | 16.11 | 22.85 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 23/10/2022 | PRANTIK DRILLING AGENCY | 49.66 | 15 | 30.21 | 80
5 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000658/2022-2023 | 2343/TD | 10/01/2023 | 19/02/2023 | SUDIP MANNA | 5.11 | 5.11 | 99.9 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 1260/TD | 12/09/2022 | 12/09/2022 | Resource Division | 44.52 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 653/TD | 27/06/2022 | 27/06/2022 | Resource Division | 26.13 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Additional Electric Quotiaton for KAKTIA Water Supply Scheme T/W-III (Ref. ID-860272167) |  |  | BILL/01616/2023-2024 | BP-2023-24-134 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.28 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Electric quotation for Kaktia PWSS Tube Well--IV WS Scheme (Ref. ID - 203931902) |  |  | BILL/00320/2022-2023 | BP-2022-23-139 | 20/03/2023 | 20/03/2023 | WBSEDCL | 2.94 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Electric quotation for Kaktia PWSS Tube Well--III WS Scheme (Ref. ID - 203931856) |  |  | BILL/00319/2022-2023 | BP-2022-23-138 | 20/03/2023 | 20/03/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. and repairing as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kaktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000135/2022-2023 | 690/TD | 27/06/2022 | 26/03/2026 | TAPAS SANTRA | 965.88 | 929.87 | 96.27 | 86
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001474/2022-2023 | 212/W/MMD | 10/02/2023 | 09/08/2023 | WEST BENGAL ENGINEERING CO. | 40.35 | 25.37 | 62.88 | 35
13 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Laying of rising main, Left out pipe line with FHTC (200 nos.) work for Kanktia PWSS in Sahid Matangini Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2022-2023 | 3208/TD | 14/03/2023 | 01/01/2026 | TAPAS SANTRA | 68.55 | 46.63 | 68.01 | 72
14 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division |  |  | BILL/00704/2025-2026 |  | 20/08/2025 | 20/08/2025 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.55 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 2nd. tube well site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000642/2024-2025 | 945/TD | 27/03/2025 | 06/05/2025 | MRITYUNJOY PARIA | 5.31 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Construction of boundary wall (Length-150 m With Double Tie Beam at 01 Longer & 01 Shorter Side) with R.C.C structures including provision of M.S. gate at H/W site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000619/2024-2025 | 696/TD | 05/03/2025 | 13/06/2025 | A. R. CONSTRUCTION | 21.69 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | SM/10120 | Augmentation | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2025 to 31.01.2026.(06 Months) | Assistant Engineer | Junior Engineer | ORD/000480/2025-2026 | 2632/TSD | 30/07/2025 | 27/01/2026 | KISHORE KUMAR SEN | 0.86 | 0 | 0 | 0
Total | [13 empty] | 1315.66 | 1048.44 | 79.69