## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub- Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. |  | Junior Engineer | ORD/000196/2021-2022 | 1228/TD | 08/12/2021 | 17/01/2022 | ANUSKA ENTERPRISE | 17.87 | 17.85 | 99.92 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Thenkuachak (Zone - I & II) Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000391/2021-2022 | 1607/TD | 14/01/2022 | 03/02/2022 | INDRANIL DUTTA & ASSOCIATES | 8.64 | 8.59 | 99.48 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Additional laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. |  | Junior Engineer | ORD/000071/2022-2023 | 292/TD | 06/05/2022 | 21/05/2022 | MALLICK CONSTRUCTION | 3.91 | 3.91 | 100 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, BLOCK-NANDAKUMAR, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000139/2022-2023 | 410/CMSD-II | 12/08/2022 | 22/08/2022 | PADMA ENGINEERING & CO. | 0.93 | 0.91 | 97.07 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL DEPARTMENTAL RIG MACHINE AT NANDAKUMAR BLOCK, DIST. PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000140/2022-2023 | 143/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 5 | 4.4 | 88.05 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | SUPPLY & DELIVERY OF TUBE WELL MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, TW-II, BLOCK- NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000141/2022-2023 | 411/CMSD-II | 12/08/2022 | 22/08/2022 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK [PWSS, TW-II, ZONE-II, BLOCK - NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000142/2022-2023 | 409/CMSD-II | 12/08/2022 | 22/08/2022 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAK W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000226/2022-2023 | 1228/CDD | 16/11/2022 | 16/12/2022 | PADMA ENGINEERING & CO. | 18.84 | 17.18 | 91.2 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH (TW-II), MOYNA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, [PHE DTE. |  |  | ORD/000138/2022-2023 | 387/CDD | 18/05/2022 | 17/06/2022 | PADMA ENGINEERING & CO. | 14.26 | 8.65 | 60.66 | 100
10 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Fuel Charges for the month of November 2022 |  |  | BILL/00039/2022-2023 | BP-2022-23-280 | 21/12/2022 | 21/12/2022 | MIRA SERVICE STATION | 0.22 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District., under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001475/2022-2023 | 213/W/MMD | 10/02/2023 | 09/08/2023 | DAS ENTERPRISE | 40.3 | 37.84 | 93.91 | 60
12 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAUK W/S SCH UNDER PURBA MIDNAPORE DISREICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000320/2022-2023 | 1382/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 19.39 | 16.46 | 84.88 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 413/TD | 25/05/2022 | 25/05/2022 | Resource Division | 121.31 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 414/TD | 25/05/2022 | 25/05/2022 | Resource Division | 46.43 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 1267/TD | 12/09/2022 | 12/09/2022 | Resource Division | 59.51 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Electric Quotation for Tube Well-III, Z-II of Thenkuachak W/S Scheme at Nandakumar CCC (2004173196) |  |  | BILL/00060/2022-2023 | BP-2022-23-110 | 01/03/2023 | 01/03/2023 | WBSEDCL | 8.3 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Electric Quotation for Tube Well-III, Z-I of Thenkuachak W/S Scheme at Nandakumar CCC (2004172999) |  |  | BILL/00061/2022-2023 | BP-2022-23-111 | 01/03/2023 | 01/03/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Payment to WBSEDCL for Quotation Money for Thenkuachak PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00394/2022-2023 | BP-2022-23-755 | 28/02/2023 | 28/02/2023 | WBSEDCL | 4.07 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Pilling work & casing pipe (GI/MS)over khal and Road crossing of various junction of Thekuachak Zone-II water supply scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000341/2023-2024 | 806/TD | 30/05/2023 | 29/06/2023 | GHOSH ENTERPRISE | 14.63 | 5.86 | 40.08 | 50
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer, Headquaters |  | ORD/000831/2022-2023 | 3171/TD | 10/03/2023 | 09/05/2023 | ANIRBAN MONDAL | 4.59 | 4.57 | 99.72 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer, Headquaters |  | ORD/000832/2022-2023 | 3172/TD | 10/03/2023 | 09/05/2023 | TARUN KHATUA | 5.11 | 5.11 | 99.98 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-I PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000176/2023-2024 | 333/TD | 25/04/2023 | 17/08/2024 | GHOSH ENTERPRISE | 15.05 | 5.78 | 38.38 | 70
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Additional works of Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur .( Low Land ) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000466/2023-2024 | 1446/TD | 13/07/2023 | 22/08/2023 | TARUN KHATUA | 1.86 | 1.83 | 98.6 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Cannel crossing for DI and uPVC pipes of Thekua chak Zone-II PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. (Nodal Point 139-140, 410-528, 165-164, 636-448, 675-381, 783-789, 665-214 and 55-221= 8 nos) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000736/2023-2024 | 2986/TD | 29/11/2023 | 29/12/2023 | GHOSH ENTERPRISE | 33.58 | 17.04 | 50.73 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Canel crossing for DI and uPVC pipes of Thekua chak Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. ( Nodal 167-112, 585-327,33-98,337-401 and 213-109 )= 5 nos | Assistant Engineer, Headquaters | Junior Engineer | ORD/000737/2023-2024 | 2985/TD | 29/11/2023 | 29/12/2023 | GHOSH ENTERPRISE | 20.97 | 20.44 | 97.5 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying of DI (K7) ( Nodal point 167 to 627) ,UPVC pipe (Nodal 167-623) & Supply of of DI (Specials) under Thekuachak Zone-I Water Supply Scheme under Tamluk Division, Purba Medinipur, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000111/2024-2025 | 1905/TD | 07/06/2024 | 27/06/2024 | GHOSH ENTERPRISE | 12.87 | 0 | 0 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 670/W | 22/02/2024 | 22/02/2024 | Resource Division | 16.44 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000242/2022-2023 | 1021/TD | 08/08/2022 | 18/03/2026 | ARABINDA GHOSH | 1009.34 | 650.99 | 64.5 | 70
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-II PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000175/2023-2024 | 332/TD | 25/04/2023 | 24/06/2023 | GHOSH ENTERPRISE | 17.82 | 10.35 | 58.09 | 70
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Construction of Concrete road for Kharar Pool ( Mansa Mandir) (Nodal Point -38) to Head work site of Thekuachak Zone -I(Nodal point 1158 )( Length - 350 mtr, width 2.10 mte , Depth of cincrete 150 mm ) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000734/2023-2024 | 2988/TD | 29/11/2023 | 29/12/2023 | KRISHNENDU SEKHAR DAS | 9.63 | 9.11 | 94.65 | 100
31 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2023 to 14/07/2024 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001289/2023-2024 | 1489/TD | 14/07/2023 | 14/07/2024 | THREE MAA ENTERPRISE | 1.24 | 4.56 | 367.91 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well site for Thekuachak Zone-II Water Supply Scheme in Nandakumar Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000464/2024-2025 | 3724/TD | 04/12/2024 | 03/04/2025 | GHOSH ENTERPRISE | 7.83 | 0 | 0 | 100
33 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr. and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000241/2022-2023 | 1020/TD | 08/08/2022 | 23/07/2025 | ARABINDA GHOSH | 705.19 | 617.42 | 87.55 | 90
34 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2024 to 14/07/2025 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000262/2024-2025 | 2227/TD | 11/07/2024 | 11/07/2025 | THREE MAA ENTERPRISE | 1.24 | 3.77 | 304.11 | 0
35 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10121 | Augmentation | Drum sheet walling in different nodal point under Thekuachak Zone-I water supply scheme under Tamluk Division, Purba Medinipur,PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000123/2024-2025 | 1920/TD | 07/06/2024 | 27/06/2024 | GHOSH ENTERPRISE | 13.39 | 0 | 0 | 100
Total | [13 empty] | 2262.82 | 1474.59 | 65.17