## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bainchberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2021-2022 | 1163/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 9.35 | 9.23 | 98.75 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 1232/TD | 07/09/2022 | 22/09/2022 | J.S. CONSTRUCTION | 3.61 | 3.61 | 100 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 0.72 | 15.96 | 0
4 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERYA W/S SCH (REPLACEMENT TW-II) NANDAKUMAR BLOCK PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000010/2022-2023 | 433/CDD | 23/05/2022 | 22/06/2022 | PADMA ENGINEERING & CO. | 13.86 | 12.78 | 92.21 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000324/2022-2023 | 1231/TD | 07/09/2022 | 22/09/2022 | J.S. CONSTRUCTION | 3.14 | 3.14 | 100 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERIA W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000269/2022-2023 | 1231/CDD | 16/11/2022 | 16/12/2022 | PADMA ENGINEERING & CO. | 18.95 | 16.13 | 85.1 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Baichberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 480/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.39 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bahichberia Water Supply Scheme under Tamluk Sub Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000632/2022-2023 | 2482/TD | 16/01/2023 | 15/02/2023 | SK. NUR ISLAM | 4.85 | 4.85 | 100 | 25
9 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 2483/TD | 16/01/2023 | 15/02/2023 | S.K. MONDAL | 3.53 | 3.52 | 99.74 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Land filling work for entrance approach & 3rd tube well site of Bahichberia Water Supply Scheme for augmentation of Bahichberia pwss under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000746/2022-2023 | 1086/TSD | 22/08/2022 | 06/09/2022 | J.S. CONSTRUCTION | 1.72 | 1.54 | 89.19 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 84/TD | 08/04/2022 | 08/04/2022 | Resource Division | 53.93 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 650/TD | 27/06/2022 | 27/06/2022 | Resource Division | 39.34 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Electric quotation for Baichberya PWSS Tube Well- III (Ref. ID - 203911567) |  |  | BILL/00159/2022-2023 | BP-2022-23-129 | 13/03/2023 | 13/03/2023 | WBSEDCL | 8.28 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bahichberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2023-2024 | 270/TD | 20/04/2023 | 09/01/2025 | S.K. MONDAL | 29.92 | 4.51 | 15.09 | 80
15 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Laying left out portion of 90 mm dia UPVC pipe line ( 3991.00 mtr ) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-A) | Assistant Engineer |  | ORD/000289/2024-2025 | 3054/TD | 19/09/2024 | 14/10/2024 | HYDROTECH ASSOCIATES | 17.58 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well - II of Baichberiya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001137/2022-2023 | 2118/W/MMD | 28/11/2022 | 29/02/2024 | RITESH ENTERPRISE | 12.17 | 11.3 | 92.86 | 90
17 | PURBA MEDINIPUR |  | Central Drilling | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries at Baichberia , Nandakumar Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000529/2022-2023 | 1229/CDD | 16/11/2022 | 11/12/2023 | MENAKA ENTERPRISE | 18.61 | 15.55 | 83.55 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 1103/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2024-2025 | 2002/TD | 14/06/2024 | 14/06/2024 | Resource Division | 2.64 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Qoutation bill for T/W -IV of Baichberia water supply scheme |  |  | BILL/03565/2023-2024 | BP-2023-24-608 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Augmentation of ground water based Bahichberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir 900 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 56/TD | 05/04/2022 | 13/10/2024 | JAYANTA KUMAR MONDAL | 952.26 | 917.45 | 96.34 | 99
22 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000615/2022-2023 | 79/TSD | 13/01/2023 | 03/12/2024 | J.S. CONSTRUCTION | 2.61 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000046/2023-2024 | 1219/W/MMD | 25/04/2023 | 01/09/2025 | BHABANI PRASAD MANNA | 27.19 | 12.79 | 47.04 | 50
24 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Dismentling of existing damaged godown at Bainchberia and its adj mouzas Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2024-2025 | 195/TSD | 22/01/2025 | 21/02/2025 | SUDIP MANNA | 2.12 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 01.11.2024 upto 31.10.2025 i.e 12 (Twelve) Months. | Assistant Engineer | Junior Engineer | ORD/000657/2024-2025 | 1636/TSD | 30/10/2024 | 26/06/2025 | TAPAS SANTRA | 1.14 | 0.8 | 70.47 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | SM/10122 | Augmentation | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing Vehicle No-WB-29F-4919 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 07.08.2025 to 06.02.2026.(06 Months) | Assistant Engineer | Junior Engineer | ORD/000404/2025-2026 | 2671/TSD | 06/08/2025 | 06/02/2026 | KHOKAN SAMANTA | 0.87 | 0 | 0 | 10
Total | [13 empty] | 1253.59 | 1017.94 | 81.2