## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) | Assistant Engineer | Junior Engineer | ORD/000228/2022-2023 | 893/TD | 25/07/2022 | 09/08/2022 | SRIMANTA KUMAR MAITY | 4.8 | 4.8 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2021-2022 | 1676/TD | 27/01/2022 | 16/02/2022 | ROY CHOWDHURY ASSOCIATES | 4.46 | 4.46 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000446/2021-2022 | 1677/TD | 27/01/2022 | 16/02/2022 | ROY CHOWDHURY ASSOCIATES | 4.19 | 4.19 | 99.84 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000140/2022-2023 | 691/TD | 27/06/2022 | 24/12/2022 | TAPAS SANTRA | 597.73 | 567.16 | 94.88 | 82
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tube Well site for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land). | Assistant Engineer | Junior Engineer | ORD/000400/2022-2023 | 1344/TD | 19/09/2022 | 18/11/2022 | M/S SOURAV MAHAPATRA | 3.82 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION F TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCHEME, TW-III, Z-I, BLOCK BHAGAWANPUR-I, UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000411/2022-2023 | 2115/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 17.76 | 16.63 | 93.63 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-II W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer | Junior Engineer | ORD/000348/2022-2023 | 1281/TD | 12/09/2022 | 11/11/2022 | BISWA NIRMAN ENTERPRISE. | 3.82 | 3.73 | 97.64 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-II Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) 2nd Call. | Assistant Engineer | Junior Engineer | ORD/000357/2022-2023 | 1299/TD | 13/09/2022 | 28/09/2022 | NANDY UDYOG | 4.83 | 4.83 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-I piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call | Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 1297/TD | 13/09/2022 | 28/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.41 | 3.41 | 100 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-I W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer | Junior Engineer | ORD/000405/2022-2023 | 1345/TD | 19/09/2022 | 18/11/2022 | GIRI CONSTRUCTION | 3.82 | 3.68 | 96.23 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-II piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call. | Assistant Engineer | Junior Engineer | ORD/000406/2022-2023 | 1300/TD | 13/09/2022 | 28/09/2022 | PARTHA CONSTRUCTION | 3.23 | 3.23 | 100 | 100
12 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCH (TW-III), BHAGAWANPUR-II BLOCK UNDER PURBA MEDNAIPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000314/2022-2023 | 1347/CDD | 24/11/2022 | 24/12/2022 | PADMA ENGINEERING & CO. | 19.77 | 17.45 | 88.28 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction and Commissioning of R.C.C. Over Head Reservoir of capacity 500 cum and staging height 20.00 mtr, as per Departmental Drawing no-PC-1/O.H.R./5/2012 for Rejuvination of Bhagwanpur Zone-I Water Supply Scheme under Bhagwanpur-I Block of Contai sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000238/2020-2021 | 2839/TD | 05/02/2021 | 24/08/2021 | DAS CONSTRUCTION | 118.1 | 15.5 | 13.12 | 90
14 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL FOR BHAGAWANPUR W/S SCHEME TW-III, ZONE-I, PURBA MEDINIPU DISTRICT BY UTILISING SKILLED CREW & DEPARTMENTAL MACHINERRIES OF CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000113/2023-2024 | 92/CMSD-II | 17/04/2023 | 02/05/2023 | PADMA ENGINEERING & CO. | 1 | 0.32 | 32.1 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 403/TD | 25/05/2022 | 25/05/2022 | Resource Division | 102.66 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 404/TD | 25/05/2022 | 25/05/2022 | Resource Division | 28.11 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 1272/TD | 12/09/2022 | 12/09/2022 | Resource Division | 59.54 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Electric Quotation for Bhagwanpur Zone-II, TW - III (Ref. ID - 203964030) |  |  | BILL/00108/2023-2024 | BP-2023-24-30 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Electric Quotation for BHAGWANPUR Water Supply Scheme Z-I, T/W-III (Ref. ID-204049532 ) |  |  | BILL/01631/2023-2024 | BP-2023-24-137 | 27/07/2023 | 27/07/2023 | WBSEDCL | 3.34 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-II Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000151/2022-2023 | 726/TD | 04/07/2022 | 31/12/2022 | TARUN KOLEY | 595.09 | 532.66 | 89.51 | 83
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001929/2022-2023 | 848/W/MMD | 24/03/2023 | 20/09/2023 | BHABANI PRASAD MANNA | 59.25 | 18.74 | 31.63 | 35
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of 90 mm dia UPVC pipe lines with allied works to accommodate Total 5666 nos FHTC of Augmentation of Bhagwanpur Zone-I & its adjoining mouzas W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000309/2023-2024 | 623/TD | 17/05/2023 | 16/06/2023 | TAPAS SANTRA | 67.97 | 55.64 | 81.86 | 85
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of Rising Main DI(K9) pipe line with CIDF Pipe & Speacials for interconnection in between 3rd TW & OHR of Augmentation of Bhagabanpur Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000647/2023-2024 | 2597/TD | 10/10/2023 | 30/10/2023 | TAPAS SANTRA | 9.63 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Bhagabanpur Zone-II PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-50.00 mtr.)For Low Land. | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 2696/TD | 17/10/2023 | 16/11/2023 | BHOWMIK & SONS | 8.66 | 6.39 | 73.81 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Boundary Wall, Raising Main, Approch Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001180/2023-2024 | 725/TD | 28/02/2024 | 08/04/2024 | M/S. PRADIP PRADHAN | 32.11 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of 200 mm dia & 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well & 2nd Tube well to 3rd Tube Well (Additional) of Augmentation of Bhagwanpur Zone II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 297/TD | 20/04/2023 | 20/05/2023 | BARH CONSTRUCTION | 11.04 | 8.14 | 73.72 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Laying of 90 mm dia UPVC Pipe Lines With allied works to accommodate Total 4010 nos FHTC of Augementation of Bhagabanpur Zone -II Water Supply Scheme within Bhagabanpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000708/2023-2024 | 2874/TD | 17/11/2023 | 17/12/2023 | TARUN KOLEY | 79.77 | 78.53 | 98.45 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 21/12/2024 | B. K. ENTERPRISE | 34.31 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Boundary Wall, Raising Main, Approach Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 3293/TD | 05/10/2024 | 02/02/2025 | SAMIT KUMAR MONDAL | 31.76 | 0 | 0 | 60
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Repairing of Boundary Wall, and Pump House (1st & 2nd) under JJM with allied work for Augmentation of Bhagabanpur Zone -II PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 3216/TD | 01/10/2024 | 29/01/2025 | SAMIT KUMAR MONDAL | 8.34 | 0 | 0 | 100
31 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Construction of Approach Road at 4th TW site for Augmentation of Bhagabanpur Zone-I PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur.(Length-58 mtr.) |  |  | ORD/000598/2024-2025 | 570/TD | 17/02/2025 | 14/03/2025 | CHANDA AGENCIES | 4.92 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Renovation and new Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Bhagabanpur Zone-II Water Supply Scheme in Bhagabanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer |  | ORD/000020/2025-2026 | 1077/TD | 07/04/2025 | 17/05/2025 | RAI CONSTRUCTION | 18.27 | 0 | 0 | 0
33 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | SM/10125 | Augmentation | Interconection work Between 2nd pump and 3rd pump , of Augementation of Bhagabanpur Zone-II water supply scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000568/2024-2025 | 2445/CSD | 22/10/2024 | 12/11/2024 | BARH CONSTRUCTION | 0.52 | 0 | 0 | 0
Total | [13 empty] | 1946.59 | 1349.48 | 69.33