## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chandiveti Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2021-2022 | 1608/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.99 | 4.29 | 85.84 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur,Basudevberia,Chandivety & Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II).(Supply at Mukutshila Store). | Assistant Engineer | Junior Engineer | ORD/000171/2022-2023 | 775/TD | 08/07/2022 | 23/07/2022 | SRIMANTA KUMAR MAITY | 3.49 | 3.49 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Chandibhetti Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000127/2022-2023 | 627/TD | 23/06/2022 | 08/07/2022 | SRIMANTA KUMAR MAITY | 4.59 | 4.59 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Chandibhetti Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba medinipur. | Assistant Engineer | Junior Engineer | ORD/000115/2022-2023 | 593/TD | 17/06/2022 | 16/08/2022 | RAJ KUMAR SINGHA | 585.56 | 564.09 | 96.33 | 95
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Chandibhetti Water Supply Scheme (Mouza - Banamaliberya, JL No. - 458, Plot No. - 8) within Contai-II (Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 978/TD | 03/08/2022 | 18/08/2022 | PRANTIK DRILLING AGENCY | 12.15 | 11.38 | 93.6 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 405/TD | 25/05/2022 | 25/05/2022 | Resource Division | 42.06 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 1268/TD | 12/09/2022 | 12/09/2022 | Resource Division | 23.08 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Electric quotation for Chandiveti PWSS Tube Well- III in connection Mukundapur CCC (2004186280) |  |  | BILL/00163/2022-2023 | BP-2022-23-131 | 14/03/2023 | 14/03/2023 | WBSEDCL | 0.59 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Construction of (Boundary Wall(as per Departmental Design & Drawing) at 3rd TW Site for Augmentation of Chandibhetty PWSS in Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Length 65.00 mtr.) For Low Land. | Assistant Engineer | Junior Engineer | ORD/000471/2023-2024 | 1497/TD | 17/07/2023 | 15/09/2023 | SUBHENDU HAZRA | 10.3 | 8.31 | 80.66 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Chandibhetti W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/000725/2023-2024 | 2970/TD | 28/11/2023 | 27/01/2024 | BISWA NIRMAN ENTERPRISE. | 3.73 | 3.72 | 99.65 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Laying of Rising Main including interconnection of Chandibhetty PWSS in Deshapran Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 928/TD | 01/06/2023 | 01/07/2023 | SUDIP MANNA | 6.09 | 3.05 | 50.04 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | SM/10126 | Augmentation | Repairing of OHR, Pump House no 1, Pump House No. 2, Head Work site Boundary Wall and Boundary Wall of 2nd Tubewell Site under JJM with allied work of Chandivetty PWSS within Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000344/2024-2025 | 3329/TD | 22/10/2024 | 01/12/2024 | SUBHENDU HAZRA | 18.38 | 0 | 0 | 0
Total | [13 empty] | 715.03 | 602.91 | 84.32