## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Junbani Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2021-2022 | 1547/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.58 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional (3rd) Tubewell of Augmentation of Junbani Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000238/2022-2023 | 979/TD | 03/08/2022 | 18/08/2022 | PRANTIK DRILLING AGENCY | 12.15 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tubewell of Augmentation of Junbani Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000209/2023-2024 | 473/TD | 10/05/2023 | 09/07/2023 | SUBHENDU HAZRA | 3.68 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Supply & Delivery of different dia Sluice Valve for Junbani Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store) | Assistant Engineer | Junior Engineer | ORD/000221/2022-2023 | 493/CSD | 02/08/2022 | 17/08/2022 | GIRI CONSTRUCTION | 2.47 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 102/TD | 11/04/2022 | 11/04/2022 | Resource Division | 51.5 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 1270/TD | 12/09/2022 | 12/09/2022 | Resource Division | 32.32 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Electric quotation for Junboni PWSS Tube Well-IV WS Scheme (Ref. ID-203911303) |  |  | BILL/00318/2022-2023 | BP-2022-23-137 | 20/03/2023 | 20/03/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Boundary wall and Rising Main and under JJM with allied work for Jubani PWSS within Contai-I Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 3224/TD | 13/12/2023 | 22/01/2024 | MAHAPRABHU ENTERPRISE | 35.37 | 0 | 0 | 16
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000132/2022-2023 | 693/TD | 27/06/2022 | 26/08/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 736.14 | 0 | 0 | 98
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Additional Quotation Bill for T/W NO-IV Of JUNBONI W/S Scheme under MMD, PHE, Dte. Block- Contai-I, PICHABANI C.C.C. Ref. Memo No- 2004620649/QUOT/03 DT. 27-02-2024 Application NO- 2004620649 Reference Id- 204229267 |  |  | BILL/04304/2023-2024 | BP-2023-24-798 | 07/03/2024 | 07/03/2024 | WBSEDCL | 6.88 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000202/2023-2024 | 1482/W/MMD | 21/06/2023 | 30/09/2024 | MAA KALI ENTERPRISE | 11.4 | 0 | 0 | 25
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Continuation W/O for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2024 to 30/06/2025. (12 Months), Vehicle no.-WB-31/6974 | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 1788/CSD | 28/06/2024 | 28/06/2025 | SABITA PRADHAN | 1.49 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Repairing of R.C.C. Elevated Reservoir of capacity with allied works of Junbani PWSS within Contai - I Block including supply of all labour & materials under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000447/2024-2025 | 3614/TD | 27/11/2024 | 06/01/2025 | CHARUBALA ENTERPRISE | 11.14 | 0 | 0 | 97
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | SM/10127 | Augmentation | Left Out pipeline, Piling and Road Restoration work for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur |  |  | ORD/000638/2024-2025 | 850/TD | 19/03/2025 | 18/04/2025 | BASANTA KUMAR MAITY | 41.02 | 0 | 0 | 0
Total | [13 empty] | 951.71 | 0 | 0