## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Laying of Distribution pipe line And FHTC ( Functional Household tap connection ) with allied works including all for Augmentation of Kumirda Water Supply Scheme within Contai- III under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000117/2022-2023 | 601/TD | 20/06/2022 | 30/01/2026 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 799.74 | 517.9 | 64.76 | 70
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kumirda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2021-2022 | 1613/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.66 | 5.64 | 99.74 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000266/2022-2023 | 157/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.98 | 4.98 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kumirda Water Supply Scheme in Contai III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 2262/TD | 30/12/2022 | 19/01/2023 | CASTING CORPORATION OF INDIA | 8.5 | 8.5 | 100 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000265/2022-2023 | 156/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 100 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000267/2022-2023 | 158/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.99 | 4.95 | 99.16 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 98/TD | 11/04/2022 | 11/04/2022 | Resource Division | 40.13 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 1274/TD | 12/09/2022 | 12/09/2022 | Resource Division | 33.04 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Repairing and Renovation Of Pump House No. I , II & III under Augmentation of Kumirda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000960/2022-2023 | 422/CSD | 17/03/2023 | 16/04/2023 | PARIA ENTERPRISE | 2.89 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for Additional Tube well site J.L no. -155, Plot no. -1245, Mouza -Panichiary under Augmentation of Kumirda W/S Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 490/TD | 10/05/2023 | 09/07/2023 | PARIA ENTERPRISE | 4.09 | 3.58 | 87.72 | 100
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001930/2022-2023 | 849/W/MMD | 24/03/2023 | 13/03/2025 | SUJOY RANJAN BHOWMICK | 13.58 | 9.63 | 70.92 | 60
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir ( OHR) & 1st.Tube Well , 2nd , 3rd , Additional Tube Well Site, Mouza -kumirda under Augmentation of Kumirda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 230.00 mtr. | Assistant Engineer | Junior Engineer | ORD/000732/2022-2023 | 2562/TD | 24/01/2023 | 25/03/2023 | M/S. PRADIP PRADHAN | 32.65 | 20.96 | 64.18 | 90
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Electric Quotation for KUMIRDA Water Supply Scheme T/W-IV, (Ref. ID-204050266) |  |  | BILL/01684/2023-2024 | BP-2023-24-166 | 04/08/2023 | 04/08/2023 | WBSEDCL | 5.19 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Kumirda Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer | ORD/000150/2024-2025 | 1736/CSD | 20/06/2024 | 10/07/2024 | M/S. NEW DINDA ENTERPRISE | 1.16 | 1.16 | 100 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Rising main with laying of 150 mm dia DI (K-9) from 4th Tube Well site to OHR site and other allied works for Kumirda in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 2357/CSD | 26/09/2024 | 26/10/2024 | BISWA NIRMAN ENTERPRISE. | 1.61 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Jack Pushing of Railway Track from station henria and nachinda of augmentation of Kumirda Piped Water Supply scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 44/15 to mast no 44/16 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer | Junior Engineer | ORD/000120/2024-2025 | 1916/TD | 07/06/2024 | 03/12/2024 | ROY CONSTRUCTION | 61.73 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-46) |  |  | BILL/00134/2024-2025 | BP-2024-25-77 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.35 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Draning out of washout & over flow water from 500 Cum Capacity Over Head Reservoir to the near by natural ditch of Augmentation of Kumirda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2025-2026 | 1162/TD | 22/04/2025 | 16/07/2026 | SAURAV HAZRA | 4.34 | 0 | 0 | 0
Total | [13 empty] | 1034.61 | 582.28 | 56.28