## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000265/2022-2023 | 156/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 100 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000267/2022-2023 | 158/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.99 | 4.95 | 99.16 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000266/2022-2023 | 157/S&WSD | 12/08/2022 | 27/08/2022 | PADMA ENGINEERING & CO. | 4.98 | 4.98 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kumirda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2021-2022 | 1613/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.66 | 5.64 | 99.74 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kumirda Water Supply Scheme in Contai III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 2262/TD | 30/12/2022 | 19/01/2023 | CASTING CORPORATION OF INDIA | 8.5 | 8.5 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 98/TD | 11/04/2022 | 11/04/2022 | Resource Division | 40.13 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 1274/TD | 12/09/2022 | 12/09/2022 | Resource Division | 33.04 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Electric Quotation for KUMIRDA Water Supply Scheme T/W-IV, (Ref. ID-204050266) |  |  | BILL/01684/2023-2024 | BP-2023-24-166 | 04/08/2023 | 04/08/2023 | WBSEDCL | 5.19 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Repairing and Renovation Of Pump House No. I , II & III under Augmentation of Kumirda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000960/2022-2023 | 422/CSD | 17/03/2023 | 16/04/2023 | PARIA ENTERPRISE | 2.89 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for Additional Tube well site J.L no. -155, Plot no. -1245, Mouza -Panichiary under Augmentation of Kumirda W/S Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 490/TD | 10/05/2023 | 09/07/2023 | PARIA ENTERPRISE | 4.09 | 3.58 | 87.72 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Payment of wayleave facility charges(SER-KGP-2024-WL-46) |  |  | BILL/00134/2024-2025 | BP-2024-25-77 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.35 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Laying of Distribution pipe line And FHTC ( Functional Household tap connection ) with allied works including all for Augmentation of Kumirda Water Supply Scheme within Contai- III under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000117/2022-2023 | 601/TD | 20/06/2022 | 03/08/2025 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 799.74 | 517.9 | 64.76 | 70
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir ( OHR) & 1st.Tube Well , 2nd , 3rd , Additional Tube Well Site, Mouza -kumirda under Augmentation of Kumirda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 230.00 mtr. | Assistant Engineer | Junior Engineer | ORD/000732/2022-2023 | 2562/TD | 24/01/2023 | 25/03/2023 | M/S. PRADIP PRADHAN | 32.65 | 20.96 | 64.18 | 90
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Rising main with laying of 150 mm dia DI (K-9) from 4th Tube Well site to OHR site and other allied works for Kumirda in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 2357/CSD | 26/09/2024 | 26/10/2024 | BISWA NIRMAN ENTERPRISE. | 1.61 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Draning out of washout & over flow water from 500 Cum Capacity Over Head Reservoir to the near by natural ditch of Augmentation of Kumirda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2025-2026 | 1162/TD | 22/04/2025 | 21/06/2025 | SAURAV HAZRA | 4.34 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | SM/10128 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001930/2022-2023 | 849/W/MMD | 24/03/2023 | 13/03/2025 | SUJOY RANJAN BHOWMICK | 13.58 | 9.63 | 70.92 | 60
Total | [13 empty] | 971.72 | 581.12 | 59.8