## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. |  |  | ORD/000023/2022-2023 | 77/S&WSD | 27/05/2022 | 03/06/2022 | SUMAN KUMAR DEY | 0.9 | 0 | 0 | 67
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | LOADING UNLOADING & SHIFTING DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM DURMUT PWSS, BLOCK-CONTAI-III, PURBA MEDINIPUR DISTRICT TO PANCHLA STORE, HOWRAH UNDER CDD, PHE DTE. |  |  | ORD/000200/2022-2023 | 371/CMSD-I | 04/08/2022 | 11/08/2022 | M/S B.P.TRADING CORPORATION | 0.47 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Durmut Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2021-2022 | 1612/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.09 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (REPLACEMENT TW-II), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000044/2022-2023 | 410/CDD | 20/05/2022 | 19/06/2022 | M/S B.P.TRADING CORPORATION | 14.69 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (TW-III), DESHPRAN BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000045/2022-2023 | 411/CDD | 20/05/2022 | 19/06/2022 | ASHUTOSH DAS & CO | 14.67 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE FOR CONSTRUCTION OF TUBE WELL WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000046/2022-2023 | 227/CMSD-I (D) | 20/06/2022 | 05/07/2022 | M/S B.P.TRADING CORPORATION | 5 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROAD FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT DURMUT PWSS CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000197/2022-2023 | 296/CMSD-I | 08/07/2022 | 15/07/2022 | M/S B.P.TRADING CORPORATION | 0.81 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000063/2022-2023 | 228/CMSD-I (D) | 20/06/2022 | 05/07/2022 | M/S B.P.TRADING CORPORATION | 4.05 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Car Oil Bill for the month of October 2022 |  |  | BILL/00009/2022-2023 | BP-2022-23-246 | 29/11/2022 | 29/11/2022 | MIRA SERVICE STATION | 0.13 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Payment for Railway Application Fees. for Durmut PWSS. |  |  | VCH/000450/2022-2023 |  | 01/08/2022 | 01/08/2022 | FA & CAO, S.E. RAILWAY, GRC. | 17.19 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Charges for Way Leave Permission under railway track permission for Durmut PWSS under Tamluk Division, PHE Dte. |  |  | VCH/000520/2022-2023 | BP-2022-23-271 | 29/08/2022 | 29/08/2022 | FA & CAO, S.E. RAILWAY, GRC. | 3.15 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000216/2021-2022 | 55/CMSD-II (D) | 31/01/2022 | 07/02/2022 | ASHUTOSH PAL | 0.86 | 0 | 0 | 64
13 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000065/2022-2023 | 301/CMSD-I (D) | 08/07/2022 | 23/07/2022 | CHANDA ENTERPRISE | 4.69 | 0 | 0 | 50
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under durmut water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001220/2022-2023 | 2162/W/MMD | 08/12/2022 | 07/04/2023 | DEBJYOTI BASU | 11.13 | 0 | 0 | 70
15 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Loading unloading & Shifting of Drilling Accessories, Supporting Vehicles along with rig machine JOHN/DR/1500-I from Durmut PWSS, block Contai-III, Purba Medinipur dist. to Panchla store, Howrah under CDD PHE Dte. |  |  | ORD/000302/2022-2023 | 371/CMSD-I(D) | 04/08/2022 | 11/08/2022 | M/S B.P.TRADING CORPORATION | 0.47 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Supply & delivery of submersible pump motor set & other electromechanical accessories at P/H No-I, under DURMUT Water Supply Scheme under MMD , P.H.E. Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000174/2023-2024 | 462/HESD | 13/06/2023 | 28/06/2023 | DEBJYOTI BASU | 7.25 | 0 | 0 | 60
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 91/TD | 11/04/2022 | 11/04/2022 | Resource Division | 210.65 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 1271/TD | 12/09/2022 | 12/09/2022 | Resource Division | 23.95 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 150 mm dia MS Carrier Pipe in between Mast NO 54/9 TO Mast NO 54/8 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =45 M) Section 482 TO 486. | Assistant Engineer | Junior Engineer | ORD/000514/2023-2024 | 1744/TD | 01/08/2023 | 31/08/2023 | ROY CONSTRUCTION | 72.22 | 0 | 0 | 64
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 100 mm dia MS Carrier Pipe in between Mast NO 55/17 TO Mast NO 55/16 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =127M) Section 209 TO 231. | Assistant Engineer | Junior Engineer | ORD/000515/2023-2024 | 1745/TD | 01/08/2023 | 31/08/2023 | ROY CONSTRUCTION | 75.01 | 0 | 0 | 71
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Hade work site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000901/2023-2024 | 248/TD | 11/01/2024 | 05/04/2025 | ANIRBAN MONDAL | 11.93 | 0 | 0 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Construction of Pump House , Tube well , Boundary Wall, Rising main for Durmuth PWSS in Deshpran & Contai III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001109/2023-2024 | 559/TD | 15/02/2024 | 26/03/2024 | DEVEN ENTERPRISES | 33.8 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 31/10/2023 | MISHRA ENTERPRISE | 9.53 | 0 | 0 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000744/2023-2024 | 3133/TD | 07/12/2023 | 27/12/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.6 | 0 | 0 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000746/2023-2024 | 3134/TD | 07/12/2023 | 27/12/2023 | ABHIJIT BERA | 3.85 | 0 | 0 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Tube Well (2nd Tube Well) site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000904/2023-2024 | 249/TD | 11/01/2024 | 10/02/2024 | BISWA NIRMAN ENTERPRISE. | 5.73 | 0 | 0 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 05/12/2023 | MISHRA ENTERPRISE | 9.53 | 0 | 0 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Repairing and Renovation of pump house 1 and boundary wall in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001372/2023-2024 | 240/CSD | 07/02/2024 | 23/03/2024 | BISWA NIRMAN ENTERPRISE. | 0.71 | 0 | 0 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Durmut Water Supply Scheme within Despran & Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000082/2022-2023 | 394/TD | 23/05/2022 | 19/12/2025 | MAHAVIR PUMPS MFG. PVT. LTD. | 430.39 | 0 | 0 | 81
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Repairing and Renovation of over head reservoir in Durmuth Water Supply Scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000491/2024-2025 | 3771/TD | 10/12/2024 | 30/09/2025 | BISWA NIRMAN ENTERPRISE. | 7.05 | 0 | 0 | 100
31 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | SM/10323 | Augmentation | Repairing and Renovation of pump house 2 in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001373/2023-2024 | 241/CSD | 07/02/2024 | 05/08/2024 | RABINDRANATH DAS | 0.92 | 0 | 0 | 100
Total | [13 empty] | 987.44 | 0 | 0