## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shankarpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000316/2021-2022 | 1609/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 628/TD | 23/06/2022 | 08/07/2022 | BIBEKANANDA DAS | 4.21 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Shankarpur Water Supply Scheme (Mouza - Kukraul, JL No. - 468, Plot No. - 66) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000239/2022-2023 | 980/TD | 03/08/2022 | 18/08/2022 | PRANTIK DRILLING AGENCY | 12.15 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Renovation work of spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum for Augmentation of Sankarpur Water Supply Scheme within Block Contai- III under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 392 / CSD | 12/07/2022 | 11/08/2022 | LAKSHMI NARAYAN ENTERPRISE | 2.43 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/000427/2023-2024 | 717/TD | 24/05/2023 | 23/07/2023 | JASODA ENTERPRISE | 3.73 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 411/TD | 25/05/2022 | 25/05/2022 | Resource Division | 18.52 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 1265/TD | 12/09/2022 | 12/09/2022 | Resource Division | 13.3 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Electric Quotation for SHANKARPUR Water Supply Scheme T/W-III, (Ref. ID-204049544) |  |  | BILL/01682/2023-2024 | BP-2023-24-168 | 04/08/2023 | 04/08/2023 | WBSEDCL | 4.93 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,P.H.E. Dte., Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000313/2022-2023 | 1226/TD | 07/09/2022 | 22/10/2022 | PATHIK PABAN NANDI | 359.47 | 0 | 0 | 99
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Continuation work order for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2022 to 30/06/2023. (12 Months) Vehicle No-WB-31/6974 | Assistant Engineer | Junior Engineer | ORD/000222/2022-2023 | 357/CSD | 30/06/2022 | 30/06/2023 | SABITA PRADHA | 1.49 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Rising main and other allied works Augmentation of Shankarpur W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000494/2023-2024 | 1092/CSD | 06/06/2023 | 06/07/2023 | LAKSHMI NARAYAN ENTERPRISE | 2.58 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000064/2023-2024 | 1223/W/MMD | 25/04/2023 | 22/10/2023 | THE GODFATHER TRADING COMPANY | 11.96 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 |  |  | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 15/02/2024 | WBSEDCL | 7.83 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Augmentation of Shankarpur & adjoining mouzas Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000418/2024-2025 | 3476/TD | 06/11/2024 | 26/11/2024 | KOUSHIK MALLICK | 7.56 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd Tube Well site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000201/2024-2025 | 2323/TD | 23/07/2024 | 20/11/2024 | DIPANKAR MAITY | 4.96 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | SM/10342 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-104.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/001199/2023-2024 | 820/TD | 05/03/2024 | 01/09/2024 | S R TRADING CORPORATION | 12.57 | 0 | 0 | 100
Total | [13 empty] | 472.06 | 0 | 0