## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | SM/10345 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PASCHIM KAMARDA PWSS ( Phase- II) Block - Contai-III in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000545/2021-2022 | 2005/TD | 08/03/2022 | 02/04/2022 | RAJ KUMAR SINGHA | 39.32 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | SM/10345 | Retrofitting | Supply & Delivery of different dia Sluice Valves for Paschim Kamarda Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000659/2021-2022 | 889 / CSD | 23/03/2022 | 07/04/2022 | PARTHA CONSTRUCTION | 1.3 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | SM/10345 | Retrofitting | Repairing of inlet, outlet, washout pipe and allied works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for PASHIM KAMARDA W/S Scheme in Contai- III Block Of Purba Medinipur District under Contai Sub Division within Tamluk division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 394 / CSD | 12/07/2022 | 11/08/2022 | GIRI CONSTRUCTION | 2.26 | 0 | 0 | 100
Total | [13 empty] | 42.88 | 0 | 0