## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. | SM/10346 | Retrofitting | Retrofitting to accommodate FHTC (410 Nos.) under JJM in Keshabpur Jalpai PWSS (Balance Part : Phase-II) Block - Mahisadal in the District of Purba Medinipur | Assistant Engineer |  | ORD/000546/2021-2022 | 2006/TD | 08/03/2022 | 02/04/2022 | RAJ KUMAR SINGHA | 23.33 | 0 | 0 | 100
Total | [13 empty] | 23.33 | 0 | 0