## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Erasole Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2021-2022 | 1646/TD | 19/01/2022 | 08/02/2022 | HORIZEN | 5.37 | 5.37 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 04/10/2022 | AQUATECH ENGINEERS | 70.49 | 33.7 | 47.81 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 409/TD | 25/05/2022 | 25/05/2022 | Resource Division | 114.93 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1263/TD | 12/09/2022 | 12/09/2022 | Resource Division | 44.05 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Electric Quotiaton for Erashal Water Supply Scheme TW-IV (Ref. ID-203949710) |  |  | BILL/00109/2023-2024 | BP-2023-24-36 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.5 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 under Tamluk Division, PHE Dte. |  |  | BILL/01676/2023-2024 | BP-2023-24-737 | 29/12/2023 | 29/12/2023 | FA & CAO, S.E. RAILWAY, GRC. | 0.07 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Electric Quotiaton for Erashal Water Supply Scheme TW-III (Ref. ID-203949718) |  |  | BILL/00110/2023-2024 | BP-2023-24-37 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.5 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Repairing & Renovation of Construction of switch Room cum Chlorine Room at OHR site and 2 nd.Tube Well site and Renovation of existing Boundary Wall at OHR site and 2 nd.Tube Well site and New construction of Boundary Wall at 3rd.& 4 th Tube Well site for Erasal Water Supply Scheme under Tamluk Sub Division,PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 3019/TD | 27/02/2023 | 28/04/2023 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.17 | 39.66 | 98.73 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000061/2023-2024 | 1226/W/MMD | 25/04/2023 | 22/10/2023 | SOUMEN ELECTRIC | 26.95 | 26.58 | 98.65 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Jack Pushing of Railway Track Between NANDAKUMAR P.H. & LAVAN SATYAGARH SMARAK P.H. Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of ERASOLE Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia DI (K7) Carrier Pipe within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =48 Mtr) Nodal Point J393 to J338. | Assistant Engineer | Junior Engineer | ORD/000720/2023-2024 | 2942/TD | 23/11/2023 | 13/12/2023 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 68.57 | 53.19 | 77.56 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 of Erashole PWSS under Tamluk Division, PHE Dte. |  |  | BILL/01896/2023-2024 | BP-2023-24-853 | 08/02/2024 | 08/02/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Augmentation of ground water based Erasol Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 1888/TD | 24/11/2022 | 27/09/2025 | TARUN KOLEY | 1110.82 | 768.23 | 69.16 | 80
13 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | Interconnection with laying of 150 mm dia,200 mm dia & 250 mm dia DI(K-9) rising main from 3rd & 4th. T/W to OHR at Erasole PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000452/2023-2024 | 1476/TD | 14/07/2023 | 03/11/2025 | SAYAN MAITY | 10.15 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | SM/10396 | Augmentation | MS structure for canel crossing, NH road boring with casing and concrete piller for Laying distribution system and rising main pipe line at Erasole Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 3105/TD | 23/09/2024 | 04/11/2025 | TARUN KOLEY | 28.12 | 0 | 0 | 100
Total | [13 empty] | 1526.07 | 926.73 | 60.73