## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | SM/10431 | Retrofitting | TRIAL RUN work of distribution system and rising main pipe line etc. of Baranalgeriya (Zone - II) W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. For the period of 90 (Ninety) Days. (01/04/2022 to 29/06/2022 | Assistant Engineer | Junior Engineer | ORD/000660/2021-2022 | 778/DSD | 31/03/2022 | 29/06/2022 | BIBEKANANDA DAS | 0.72 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | SM/10431 | Retrofitting | Retrofitting to accommodate FHTC (1718 nos.) under JJM in Baranalgeria Zone -II PWSS Block - EGRA -II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000042/2022-2023 | 173/TD | 25/04/2022 | 25/05/2022 | FIROZ KHAN | 82.65 | 82.65 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | SM/10431 | Retrofitting | Land development at 1st tube well site of Baranalgeria ( Zone-II ) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 1595/TD | 18/10/2022 | 07/11/2022 | PULAK KUMAR SAMANTA | 3.51 | 3.5 | 99.69 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | SM/10431 | Retrofitting | Laying ( Left out ) HDPE pipe lineto accommodated FHTC under JJM in Baranalgeria (Zone-II) PWSS within Egra-II Block( to Support Phase -I FHTC ( part -B ) under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000201/2023-2024 | 402/TD | 27/04/2023 | 27/05/2023 | DEBDUT CONSTRUCTION | 32.43 | 17.71 | 54.6 | 100
Total | [13 empty] | 119.31 | 103.86 | 87.05