## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 350 Cum at Contai-II Block within Baharchandberya W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer |  | ORD/000253/2021-2022 | 516 / CSD | 29/11/2021 | 20/12/2021 | LAKSHMI NARAYAN ENTERPRISE | 0.55 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEERS | 55.36 | 0.5 | 0.9 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Laying Distribution pipe line to accommodate FHTC with allied works for Retrofitting in Baharchandberya Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000227/2022-2023 | 969/TD | 03/08/2022 | 27/09/2024 | DIPAK KUMAR BAKLY | 92.52 | 71.22 | 76.97 | 70
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002025/2022-2023 | 884/W/MMD | 27/03/2023 | 23/09/2023 | UTTAM KUMAR CHATTERJEE | 12.39 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Land Development for approach road for entry of Rig Machine for Replacement of 2nd Tube Well of Baharchandberya W/S Scheme within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000609/2023-2024 | 1583/CSD | 16/08/2023 | 31/08/2023 | ABHIJIT BERA | 0.49 | 0.48 | 99.09 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | SM/10433 | Retrofitting | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Baharchandberya PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000343/2024-2025 | 3328/TD | 22/10/2024 | 01/12/2024 | S R TRADING CORPORATION | 12.55 | 0 | 0 | 0
Total | [13 empty] | 173.86 | 72.2 | 41.53