## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, | SM/10434 | Retrofitting | Laying damage portion of different dia. UPVC pipes within Surface Water Based Water Supply Scheme for Zone- VIII of Kolaghat Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 63/TD | 05/04/2022 | 25/04/2022 | CONCORD ENGINEERING | 12.59 | 12.58 | 99.9 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, | SM/10434 | Retrofitting | Retrofitting to accommodate FHTC(Balance work) (200 nos.) and laying of left-out portion with uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone- VIII, Block-Kolaghat in the District of Purba Medinipur(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000124/2022-2023 | 616/TD | 21/06/2022 | 11/07/2022 | ARABINDA GHOSH | 78.41 | 67.03 | 85.48 | 100
Total | [13 empty] | 91.01 | 79.61 | 87.48