## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl | SM/10436 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (620 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000123/2022-2023 | 615/TD | 21/06/2022 | 16/07/2022 | MAA ANANDAMAYEE | 65.39 | 65.43 | 100.06 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl | SM/10436 | Retrofitting | Balance work for Retrofitting to accommodate FHTC (345 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-A] | Assistant Engineer | Junior Engineer | ORD/000121/2022-2023 | 614/TD | 21/06/2022 | 11/07/2022 | ARABINDA GHOSH | 30.95 | 30.93 | 99.94 | 100
Total | [13 empty] | 96.34 | 96.36 | 100.02