## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -B). | Assistant Engineer | Junior Engineer | ORD/000248/2022-2023 | 1039/TD | 16/08/2022 | 30/09/2022 | I. S. ENTERPRISE. | 154.56 | 102.85 | 66.54 | 70
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -J) | Assistant Engineer | Junior Engineer | ORD/000366/2022-2023 | 1333/TD | 16/09/2022 | 06/10/2022 | SUBRATA KUMAR BERA | 35.6 | 23.71 | 66.6 | 70
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -F) | Assistant Engineer | Junior Engineer | ORD/000564/2022-2023 | 2241/TD | 29/12/2022 | 18/01/2023 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LIMITED | 32.16 | 19.73 | 61.33 | 65
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -E) | Assistant Engineer | Junior Engineer | ORD/000374/2022-2023 | 1338/TD | 16/09/2022 | 16/10/2022 | A. K. SIKDAR | 69.34 | 36.22 | 52.24 | 60
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 1195/TD | 06/09/2022 | 06/09/2022 | Resource Division | 186.74 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 1197/TD | 06/09/2022 | 06/09/2022 | Resource Division | 47.95 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Electric Quotation for Chargeable Head, MUKUTSHILA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049562) |  |  | BILL/01680/2023-2024 | BP-2023-24-160 | 04/08/2023 | 04/08/2023 | WBSEDCL | 1.51 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Electric Quotation for MUKUTSHILA, Water Supply Scheme T/W-V, Zone-II (Ref. ID-204049558) |  |  | BILL/01672/2023-2024 | BP-2023-24-162 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.26 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer | Junior Engineer | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 25/02/2023 | M/S. CARE | 361.65 | 60.86 | 16.83 | 18
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -K) | Assistant Engineer | Junior Engineer | ORD/000529/2022-2023 | 2100/TD | 13/12/2022 | 04/12/2024 | M/S. NEW DINDA ENTERPRISE | 41.85 | 39.6 | 94.62 | 85
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -G) | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 1387/TD | 23/09/2022 | 18/10/2022 | NEW STAR CONSTRUCTION | 76.73 | 68.22 | 88.91 | 85
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -L) | Assistant Engineer | Junior Engineer | ORD/000367/2022-2023 | 1334/TD | 16/09/2022 | 11/10/2022 | THREE MAA ENTERPRISE | 41.22 | 29.45 | 71.46 | 85
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -M) | Assistant Engineer | Junior Engineer | ORD/000368/2022-2023 | 1335/TD | 16/09/2022 | 11/10/2022 | ANUSKA ENTERPRISE | 51.96 | 38.82 | 74.71 | 75
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -I) | Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 2341/TD | 10/01/2023 | 04/02/2023 | MRINAL KANTI PRADHAN | 44.01 | 32.43 | 73.69 | 0
15 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2)under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000149/2023-2024 | 1377/W/MMD | 30/05/2023 | 26/11/2023 | MENAKA ENTERPRISE | 35.5 | 31.24 | 88.01 | 75
16 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Land Filling & allied works for Boosting Tube Well (5Th TW) site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000546/2023-2024 | 1488/A/CSD | 03/08/2023 | 18/08/2023 | KAMAL KUMAR BERA | 0.72 | 0.71 | 99.01 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Bill for Restoration of damage of Heria Mugberia Road at 1.80 KM caused due to lying of PHE water pipe line across the road under Tamluk Highway Division of Mukutshilla Zone-II PWSS |  |  | BILL/00989/2024-2025 | BP-2024-25-495 | 01/10/2024 | 01/10/2024 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.19 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -D) | Assistant Engineer | Junior Engineer | ORD/000245/2022-2023 | 1002/TD | 08/08/2022 | 21/01/2025 | GIRI CONSTRUCTION | 106.79 | 92.03 | 86.17 | 88
19 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -C) | Assistant Engineer | Junior Engineer | ORD/000258/2022-2023 | 1079/TD | 23/08/2022 | 06/01/2025 | RELIABLE CONSTRUCTIONS | 130.52 | 103.15 | 79.03 | 80
20 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | SM/10588 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -H) | Assistant Engineer | Junior Engineer | ORD/000365/2022-2023 | 1332/TD | 16/09/2022 | 06/10/2022 | PULAK KUMAR SAMANTA | 28 | 23.39 | 83.54 | 85
Total | [13 empty] | 1449.26 | 702.4 | 48.47