## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 17/10/2022 | KALPANA BUILDERS | 71.97 | 0 | 0 | 48
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. |  |  | ORD/000723/2023-2024 | 0 | 28/11/2023 | 12/01/2024 | GIRI CONSTRUCTION | 0 | 0 | NAN | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1193/TD | 06/09/2022 | 06/09/2022 | Resource Division | 97.03 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID ¿ SER-KGP-2023-WL-33 |  |  | BILL/00373/2023-2024 | BP-2023-24-204 | 25/07/2023 | 25/07/2023 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID-SER-KGP-2023-WL-34 |  |  | BILL/00493/2023-2024 | BP-2023-24-256 | 10/08/2023 | 10/08/2023 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-32 |  |  | BILL/00375/2023-2024 | BP-2023-24-203 | 25/07/2023 | 25/07/2023 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-30 |  |  | BILL/00376/2023-2024 | BP-2023-24-201 | 25/07/2023 | 25/07/2023 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-31 |  |  | BILL/00374/2023-2024 | BP-2023-24-202 | 25/07/2023 | 25/07/2023 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer | Junior Engineer | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 25/02/2023 | M/S. CARE | 361.65 | 0 | 0 | 18
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART Work Order- B) |  |  | ORD/000848/2023-2024 | 59/TD | 05/01/2024 | 25/01/2024 | MAJI ENGINEERING WORKS | 0.96 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-B for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000131/2024-2025 | 1911/TD | 07/06/2024 | 02/07/2024 | DEBABRATA DAS | 14.72 | 0 | 0 | 90
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Land Filling & allied works for 3rd TW site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000606/2023-2024 | 1490/CSD | 04/08/2023 | 19/08/2023 | GIRI ENTERPRISE | 0.96 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO 32/4 & 32/5 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =46 Mtr) Nodal Point 18 to 19. | Assistant Engineer | Junior Engineer | ORD/000713/2023-2024 | 2945/TD | 23/11/2023 | 18/12/2023 | ROY CONSTRUCTION | 64.87 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/1 & 33/2 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 5 to 109. | Assistant Engineer | Junior Engineer | ORD/000716/2023-2024 | 2947/TD | 23/11/2023 | 18/12/2023 | BISWAJIT BAG | 71.16 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/17 & 33/18 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 55 to 58. | Assistant Engineer | Junior Engineer | ORD/000717/2023-2024 | 2948/TD | 23/11/2023 | 18/12/2023 | ROY CONSTRUCTION | 68.36 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 34/2 & 34/3 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =54 Mtr) Nodal Point 253 to 182. | Assistant Engineer | Junior Engineer | ORD/000718/2023-2024 | 2949/TD | 23/11/2023 | 18/12/2023 | ZENITH CONSTRUCTION | 69.67 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 31/13 & 31/14 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =38 Mtr) Nodal Point 64 to 68. | Assistant Engineer | Junior Engineer | ORD/000714/2023-2024 | 2946/TD | 23/11/2023 | 18/12/2023 | JOY GURU TRADING | 65.18 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District.(PART Work Order - A) | Assistant Engineer | Junior Engineer | ORD/000847/2023-2024 | 58/TD | 05/01/2024 | 25/01/2024 | SSPR VALVE MANUFACTURING PVT. LTD. | 8.43 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000842/2023-2024 | 2157/CSD | 04/12/2023 | 18/04/2024 | GIRI CONSTRUCTION | 2.26 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-G for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/001149/2023-2024 | 569/TD | 15/02/2024 | 06/03/2024 | NEW STAR CONSTRUCTION | 9.63 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 1000 cum RCC OHR at Mukutshila Z-II Water Supply Scheme at Khejuri-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001274/2023-2024 | 1048/TD | 15/03/2024 | 25/03/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. |  |  | ORD/000012/2022-2023 | 46/TD | 05/04/2022 | 25/04/2022 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-H for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/001150/2023-2024 | 570/TD | 15/02/2024 | 06/03/2024 | PULAK KUMAR SAMANTA | 6.98 | 0 | 0 | 80
24 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-C for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 577/TD | 15/02/2024 | 06/03/2024 | RELIABLE CONSTRUCTIONS | 13.64 | 0 | 0 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-L for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/001280/2023-2024 | 726/TD | 28/02/2024 | 29/03/2024 | ROY BISWAS CONSTRUCTION | 4.8 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-D for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000137/2024-2025 | 1948/TD | 10/06/2024 | 09/02/2025 | DEBABRATA DAS | 10.35 | 0 | 0 | 80
27 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of PART-J for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000417/2024-2025 | 2184/CSD | 05/09/2024 | 02/02/2025 | GIRI ENTERPRISE | 1.85 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying Distribution pipe line by HDPE pipes with allied works for Left Out Area of PART-K for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 3051/TD | 19/09/2024 | 16/02/2025 | M/S. NEW DINDA ENTERPRISE | 49.94 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Laying of HDPE pipes with allied works at Left Out Portion of (PART M) for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri I Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE II) | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 3036/TD | 18/09/2024 | 15/02/2025 | M/S. NEW DINDA ENTERPRISE | 4.18 | 0 | 0 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10589 | Augmentation | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 4th Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000600/2024-2025 | 590/TD | 19/02/2025 | 21/03/2025 | M/S. NEW DINDA ENTERPRISE | 4.09 | 0 | 0 | 0
Total | [13 empty] | 1018.99 | 0 | 0