## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10590 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2021-2022 | 1678/TD | 27/01/2022 | 16/02/2022 | ROY CHOWDHURY ASSOCIATES | 4.72 | 4.71 | 99.83 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 1196/TD | 06/09/2022 | 06/09/2022 | Resource Division | 29.7 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10590 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001926/2022-2023 | 845/W/MMD | 24/03/2023 | 20/09/2023 | DEBJYOTI BASU | 35.54 | 24.61 | 69.23 | 50
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10590 | Augmentation | Quotation for new service connection at Mukutshila Zone I w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671631, Ref ID 204266595) |  |  | BILL/03075/2024-2025 | C112443271348 | 02/12/2024 | 02/12/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10590 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 28/02/2025 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 286.59 | 35.98 | 50
Total | [13 empty] | 871.1 | 315.91 | 36.27